## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 27 | C1800 | HAYNES BRIDGE ROAD CAPACITY IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Design | The Haynes Bridge Corridor is an important collector connecting neighborhoods to the south with schools, GA 400, employment and commercial centers. This project widens Haynes Bridge Road from Mansell Road to Old Alabama Road and will entail a partnership with the City of Johns Creek with Johns Creek having lead role. Proposed improvements consist of adding an additional lane in each direction, landscaping medians, adding turn lanes where appropriate, and adding a multi-use trail to connect to the Big Creek Greenway. |  | Lowe Engineers |  |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $69,303 | $59,075 | $10,228 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-13 13:14:16
ALP- 28 | C1631 | MCGINNIS FERRY ROAD CAPACITY IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Design | The proposed project would widen McGinnis Ferry Road from Sargent Road to Union Hill Road/Ronald Reagan Boulevard - a distance of approximately 4.58 miles. The proposed design includes two lanes in each direction with a 20-foot wide raised median, a 16 foot wide urban shoulder along the north with a 10-foot wide multi-use path and a 12-foot wide urban shoulder along the south with a 6-foot wide sidewalk. Stage construction and traffic control devices will be utilized to maintain traffic during construction and may require temporary lane closures. Forsyth County is overseeing the design of the widening project with the Georgia Department of Transportation (GDOT), the City of John''s Creek and the City of Alpharetta providing review and comments on the design. |  | Atlas |  |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $8,900,000 | $2,690,654 | $6,209,346 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2023-02-17 18:53:46
ALP- 29 | C1715 | BETHANY ROAD AT MAYFIELD ROAD INTERSECTION IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Completed | This project involves intersection operational improvements incorporating a roundabout at the intersection of Bethany Road and Mayfield Road. The design of this project was awarded to Tetra Tech, Inc. in the amount of $127,670 by City Council on December 12, 2016. The conceptual design for this project was presented to City Council on June 5, 2017. As the acquisition of right of way progressed, it became necessary to revise the eastern leg of the roundabout. Change Order #1 was issued on April 2, 2018 which increased the design cost by $9,950 to $137,620. Final plans were delivered to the City on June 22, 2018. City Council awarded this project on November 5, 2018 to CMES. City Council also awarded the construction project management, inspection, and engineering to Atkins North America, Inc. Notice to proceed with construction was issued for July 24, 2019. Construction was delayed due to weather and utility relocations. Construction is complete and contractor has completed punchlist items related to sod and pavement markings. | CMES, Inc. | Tetra Tech, Inc. | June, 2018 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $2,258,335 | $2,256,294 | $2,041 | Green | Red | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-12 13:33:56
ALP- 30 | C1716 | MORRIS ROAD OPERATIONAL IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Completed | This project provides the appropriate auxiliary lanes to accommodate the heavy traffic flow from both Old Milton Parkway and Webb Bridge Road, as well as pedestrian and bicycle accommodations. The volume of traffic along Morris Road between Old Milton Parkway and Webb Bridge Road has made turning movements difficult and backed-up traffic during peak times. | Vertical Earth, Inc. | Pond & Company | December, 2017 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $3,215,476 | $3,215,476 | $0 | Green | Red | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-12 13:16:22
ALP- 31 | C1717 | OLD MILTON PARKWAY CAPACITY IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Design | This Project consists of widening Old Milton Parkway (SR 120) between GA 400 and State Bridge Road to provide a 6-lane divided section. The city is working with GDOT to expedite the project using mostly state and local funds. |  | AECOM | September, 2025 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $5,579,474 | $1,482,208 | $4,097,266 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2024-01-09 09:57:11
ALP- 32 | C1714 | BETHANY ROAD AT MID-BROADWELL ROAD INTERSECTION IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Completed | This project involves intersection operational improvements incorporating a roundabout at the intersection of Bethany Road and Mid Broadwell Road. The City has received numerous complaints regarding left turns onto Mid Broadwell Road from motorists traveling south on Bethany Road and from residents of Pindell Glen Subdivision trying to leave their subdivision. Residents have complained about the speed of vehicles on Mid Broadwell Road and have requested a reduction of the speed limit or the installation of a traffic signal or four-way stop. As these options do not meet warrants, a roundabout is proposed to reduce speeds in the area and assist in left-turn movements. The preliminary cost estimate for this project was $1.28 million with funding provided through T-SPLOST (transportation special purpose local option sales tax). The design of this project was awarded to Tetra Tech, Inc. in the amount of $131,170 by City Council on December 12, 2016. The conceptual design for this project was presented to City Council on June 5, 2017. | CMES, Inc. | Tetra Tech, Inc. | January, 2018 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $1,368,453 | $1,368,302 | $151 | Green | Red | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-12 13:54:18
ALP- 33 | C1713 | KIMBALL BRIDGE ROAD BICYCLE/PEDESTRIAN/OPERATIONAL IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Concept | This project involves pedestrian, bike, and operational improvements along Kimball Bridge Road between Westside Parkway and North Point Parkway connecting residential neighborhoods to Downtown Alpharetta, Avalon, schools, and parks. |  | AECOM |  |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $1,359,742 | $1,077,773 | $281,969 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2024-01-09 09:58:44
ALP- 34 | C1935 | WINDWARD PARKWAY WESTBOUND WIDENING - NORTH POINT PARKWAY TO GEORGIA 400 | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Completed | This is one of two projects which evolved from the conceptual design work comprising the "Windward Parkway Business District/Union Hill Road Capacity Improvements - TSPLOST Project". The project limits are from North Point Parkway to the northbound Georgia 400 on-ramp. Improvements will include: (1) The installation of a third travel lane from North Point Parkway to the northbound Georgia 400 on-ramp. All travel lanes will be 11'' wide. (2) The installation of a 4'' bike lane. (3) The installation of a 6'' wide sidewalk. (4) The lengthening of the existing dual left-turn lanes from westbound Windward Parkway to southbound North Point Parkway. The typical section will seek to match that of the "Windward Parkway Triple Left-Turn Lane at Georgia 400 Interchange" project. On Monday, May 6, 2019 design of the project was awarded to Tetra Tech, Inc. in the amount of $210,500.00. Bids were received on Thursday, May 14, 2020. The project was awarded to Sol Construction, LLC by City Council on Monday, June 15, 2020. | Sol Construction LLC | Tetra Tech, Inc. | February, 2020 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $1,302,037 | $1,182,286 | $119,751 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-11 14:52:06
ALP- 35 | C1934 | WINDWARD PARKWAY EASTBOUND WIDENING - WESTSIDE PARKWAY TO NORTH POINT PARKWAY | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Construction | This is one of two projects which evolved from the conceptual design work comprising the "Windward Parkway Business District/Union Hill Road Capacity Improvements - TSPLOST Project". The project limits are from Westside Parkway to North Point Parkway. Improvements will include: (1) The installation of a third travel lane from Westside Parkway to the southbound Georgia 400 on-ramp. All travel lanes will be 11'' wide. (2) The installation of a 4'' bike lane. (3) The installation of a 6'' wide sidewalk. The typical section will seek to match that of the "Windward Parkway Triple Left-Turn Lane at Georgia 400 Interchange" project. On Monday, May 6, 2019 design of the project was awarded to Tetra Tech, Inc. in the amount of $302,830.00. Design is complete. Bids were received on Thursday, May 14, 2020. Project was awarded to Sol Construction, LLC by City Council on Monday, June 15, 2020. The Notice to Proceed was issued August 8, 2020 and the project duration is anticipated to be 365 days. | Sol Construction LLC | Tetra Tech, Inc. | February, 2020 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $1,639,117 | $1,275,417 | $363,700 | Green | Yellow | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-12 12:56:26
ALP- 36 | C1933 | WEBB BRIDGE ROAD BIKE/PED/OPERATIONAL IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Design | This is one of two projects which evolved from the conceptual design work and community meetings comprising the "Academy Street/Webb Bridge Road: Bike/Ped/Operational Improvements - TSPLOST Project". The project limits are from the Big Creek Greenway crossing to Webb Bridge Way. Improvements include: (1) The installation of 8'' wide sidewalks along both sides of Webb Bridge Road. (2) The installation of 4'' bike lanes in both directions of travel along Webb Bridge Road. (3) A 3'' wide "beauty" strip will be provided on each side of Webb Bridge Road between the sidewalk and curb line. 5''x5'' tree wells/grates will be incorporated into this area and adjacent sidewalk. (4) The evaluation of a single-lane roundabout with slip lanes at the intersection with Southlake Drive / Park Bridge Park way. (5) The installation of a single-lane roundabout at the intersection with Webb Bridge Way. (6) The installation of pedestrian lighting along both sides of Webb Bridge Road and roadway lighting at the roundabouts. |  | Pond & Company | April, 2021 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $875,796 | $814,855 | $60,941 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-13 13:19:05
ALP- 37 | C1932 | ACADEMY STREET BIKE/PED/OPERATIONAL IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Design | This is one of two projects which evolved from the conceptual design work and community meetings comprising the "Academy Street/Webb Bridge Road: Bike/Ped/Operational Improvements - TSPLOST Project". The project limits are from Loxford Lane to Fire Station 81. Improvements will include: (1) The installation of a 6'' wide sidewalk with a 2'' grass strip along the north side of Academy Street to fill the gap between Alpharetta Presbyterian Church. The existing sidewalk along the south side will be maintained though limited portions may require reconstruction. (2) The installation of a 3'' striped shoulder to accommodate bicycles in both directions of travel from Loxford Lane to Wedgewood Drive. (3) The installation of left turn lanes between Loxford Lane and Wedgewood Drive where possible and the installation of landscaped medians between Loxford Lane and Wedgewood Drive where possible. The existing right-turn lanes at Dancliff Lane and Jamestown Trail will remain. |  | Pond & Company | August, 2020 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $289,575 | $275,490 | $14,085 | Green | Yellow | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-13 13:10:33
ALP- 38 | C1708 | GREENWAY EXTENSION TO FORSYTH COUNTY | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Alpharetta | Completed | This project involves the extension of the Big Creek Greenway north from Windward Parkway to connect to Forsyth County's greenway trail system. Completing this leg of the Big Creek Greenway will result in a trail system that runs more than 14 miles through Roswell, Alpharetta, and Forsyth County. Ultimately the trail system will span from the Chattahoochee River in Roswell to Bethelview Road in Forsyth County. | Integrated Construction and Nobility Inc | Pond & Company | April, 2019 | February, 2020 | June, 2021 | May, 2021 | https://alpharetta.projects.socrata.com/projects/C1708?stageId=Construction&tab=list | Sales Tax | $1,000,000 | $799,437 | $200,563 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2017 | 2021-10-13 13:13:19
ALP- 39 | C1638 | ACADEMY STREET/WEBB BRIDGE ROAD OPERATIONAL AND PEDESTRIAN/BICYCLE IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Completed | This is the parent project of the Academy Street Bike/Ped/Operational Improvements, Webb Bridge Road Bike/Ped/Operational Improvements and Webb Bridge Road (North Point Parkway to Greenway) projects. This project was for the conceptual layouts preparation for Academy Street and Webb Bridge Road from Alpharetta Presbyterian Church to Webb Bridge Way. |  | Pond & Company | January, 2019 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $451,828 | $451,828 | $0 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2023-02-17 19:36:37
ALP- 40 | C1718 | WINDWARD PARKWAY BUSINESS DISTRICT/UNION HILL ROAD CAPACITY IMPROVEMENTS | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Completed | This project was for conceptual layouts preparation on Windward Parkway from Highway 9 to Union Hill Road, and also on Union Hill Road from Windward Parkway to McGinnis Ferry Road. |  | Tetra Tech, Inc. | June, 2018 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $185,100 | $185,100 | $0 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2023-02-17 19:39:13
ALP- 41 | C2104 | WEBB BRIDGE ROAD (NORTH POINT PARKWAY TO GREENWAY) | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Construction | This project will include the design of a new bridge over Big Creek to replace the existing vehicular and pedestrian bridges and of a 10'' wide multi-use trail with a 6'' wide planting strip along Webb Bridge Road from east of North Point Parkway to the Big Creek Greenway culvert under Webb Bridge Road. Street trees and pedestrian lighting will be provided along the shoulders. The design will seek to preserve the existing streetscape along the frontage of East Gate Subdivision. The new bridge will provide two 10.5'' travel lanes, header curb, 2'' separation (stamped concrete or concrete pavers) and a 10'' multi-use trail. Bike accommodations will be provided on the roadway from east of North Point Parkway to west of the proposed new bridge over Big Creek. At that point, bicyclists will be merged onto the multi-use trails. Refined concept plans and decision matrix were submitted on February 15, 2021. The design team was given direction to move forward with the "Alternate 3" concept based on this information. | Excellere Construction LLC | Pond & Company | February, 2022 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $692,508 | $382,143 | $310,365 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-13 13:20:05
ALP- 42 | C2054 | GA 400 BRIDGES | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Bidding | This project will add aesthetic elements to the bridges over GA 400 along Tradewinds Parkway, Kimball Bridge Road and Webb Bridge Road following the design of Encore Parkway. | [6 empty] | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $4,886,000 | $737,429 | $4,148,571 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2021-10-13 13:07:37
ALP- 43 | C2113 | ENCORE GREENWAY GATEWAY | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Design | The goal of the Encore Greenway Gateway project is to improve the connectivity (safety and simplicity) to the Big Creek Greenway from the intersection of Encore Parkway and North Point Parkway. Project will provide connectivity of the Big Creek Greenway to the west side of GA 400 and introduce a gateway feature to bring attention to the greenway. Project status meeting was held on January 10, 2022. AECOM is working on the construction plans and Design team is communicating with Recreation/Parks/Cultural Services and NFCID regarding the selection of railing, benches, garbage cans, bike racks, etc. A revised completion date of design will be examined once the City obtains access to the property and the design teams finishes all of the necessary soil borings. Design of the project is currently on-hold. |  | AECOM |  |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $628,096 | $155,569 | $472,527 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2026-05-04 15:23:46
ALP- 44 | C0000 | Adaptive Traffic Signals/ITS | Tier 2 | Maintenance and Safety Enhancements | TSPLOST | Alpharetta | Completed | Adaptive Traffic Signals/ITS |  |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable |  | Sales Tax | $0 | $0 | $0 |  |  | Inactive | kmcdowell@alpharetta.ga.us |  | 2021-05-05 13:19:36
ALP- 45 | C0001 | Milling/Resurfacing | Tier 2 | Maintenance and Safety Enhancements | TSPLOST | Alpharetta | Completed | Milling and Resurfacing | N/A | N/A | Not Applicable | Not Applicable | Not Applicable | Not Applicable |  | Sales Tax | $0 | $0 | $0 |  |  | Inactive | kmcdowell@alpharetta.ga.us |  | 2021-05-05 13:19:08
ALP- 46 | C0002 | Sidewalks | Tier 2 | Pedestrian and Bike Improvements | TSPLOST | Alpharetta | Completed | Sidewalks | N/A | N/A | Not Applicable | Not Applicable | Not Applicable | Not Applicable |  | Sales Tax | $0 | $0 | $0 |  |  | Inactive | kmcdowell@alpharetta.ga.us |  | 2021-05-05 13:20:13
ALP- 47 | C0003 | Commuter Bike Corridor | Tier 3 | Pedestrian and Bike Improvements | TSPLOST | Alpharetta | Completed | Commuter Bike Corridor | N/A | N/A | Not Applicable | Not Applicable | Not Applicable | Not Applicable |  | Sales Tax | $0 | $0 | $0 |  |  | Inactive | kmcdowell@alpharetta.ga.us |  | 2021-05-05 13:25:14
ALP- 48 | C0004 | Academy Street/Webb Bridge Road GA400 Bridge Improvements | Tier 1 | Bridges | TSPLOST | Alpharetta | Completed | This project has been combined under the GA400 Bridges project per IGA with GDOT. | N/A | N/A | Not Applicable | Not Applicable | Not Applicable | Not Applicable |  | Sales Tax | $0 | $0 | $0 |  |  | Inactive | kmcdowell@alpharetta.ga.us |  | 2021-05-03 19:29:47
ALP- 49 | C0005 | Kimball Bridge Road/GA 400 Bridge Improvements | Tier 1 | Bridges | TSPLOST | Alpharetta | Completed | This project has been combined with GA400 Bridges project, per IGA with GDOT. | N/A | N/A | Not Applicable | Not Applicable | Not Applicable | Not Applicable |  | Sales Tax | $0 | $0 | $0 | Gray | Gray | Inactive | imisbach@alpharetta.ga.us |  | 2026-05-04 15:25:23
ALP- 50 | C0006 | GA 400 Bottlenecks | Tier 1 | Congestion Relief | TSPLOST | Alpharetta | Bidding | This project has been combined with GA400 Bridges, per IGA with GDOT. | N/A | N/A | Not Applicable | Not Applicable | Not Applicable | Not Applicable |  | Sales Tax | $0 | $0 | $0 | Gray | Gray | Inactive | kmcdowell@alpharetta.ga.us |  | 2023-02-13 16:21:08
ALP- 51 | C2223 | Improved Crossing from Parking Deck to north side of Milton Ave | Tier 1 | Pedestrian Improvements | TSPLOST2 | Alpharetta | Completed | This project is for the construction of a midblock pedestrian crossing on Milton Avenue at Teasley Street, including a refuge area for pedestrians and installation of rectangular rapid flashing beacons (RRFBs). | Excellere Construction, LLC | PW | February, 2022 | October, 2022 | November, 2022 | November, 2022 | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3799/mid_block-crosswalk:-parking-deck-to-north-side-of-milton-ave-(tsplost_2;-tier_1) | Sales Tax | $212,300 | $212,300 | $0 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2022 | 2024-01-09 10:39:39 | Georgia | Milton Ave | 2022-03-31
ALP- 52 | C2222 | Mid-Block Crosswalk (Manning Oaks Elementary School) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Alpharetta | Planning | Fulton County Schools did not support the installation of mid-block crosswalk. | TBD | TBD | Not Applicable | Not Applicable | Not Applicable | Not Applicable |  | TSPLOST 2 | $150,000 | $0 | $150,000 | Gray | Gray | Inactive | kmcdowell@alpharetta.ga.us | 2022 | 2023-02-17 19:35:07 | Georgia | Manning Oaks Elementary School | 2022-03-31
ALP- 53 | C2221 | Mid-Block Crosswalk (Alpharetta Elementary School) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Alpharetta | Completed | This project is for the construction of a midblock pedestrian crossing on Mayfield Road at the intersection with the school entrance. The design includes installation of rectangular rapid flashing beacons (RRFBs). | Excellere Construction, LLC | PW | May, 2022 | July, 2022 | November, 2022 | August, 2022 | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3797/mid_block-crosswalk:-alpharetta-elementary-school-(tsplost_2,-tier_1) | Sales Tax | $113,037 | $113,037 | $0 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2022 | 2023-07-27 09:53:53 | Georgia | Alpharetta Elementary School | 2022-03-31
ALP- 54 | C2225 | Improved Pedestrian Crossings from City Center to Churches | Tier 1 | Pedestrian Improvements | TSPLOST2 | Alpharetta | Design | This proposed project would review the section of Academy Street from SR-9 to Haynes Bridge Road for improvements that would reduce vehicle speeds, improve visibility, shorten the distance to cross the street and provide pedestrian refuge areas. | TBD | Moffatt & Nichol | August, 2023 | January, 2023 | Not Applicable | Not Applicable | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3801/improved-pedestrian-crossing-from-city-center-to-churches-(tsplost_2,-tier_1) | Sales Tax | $750,000 | $118,690 | $631,310 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2021 | 2024-01-09 10:36:31 | Georgia | Alpharetta City Center | 2022-03-31
ALP- 55 | C2305 | Alpha Loop (Old Milton Pkwy to Northwinds Pkwy) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Alpharetta | Construction | This project is for the design and construction of the Alpha Loop Trail from the existing trail adjacent to the Chelsea Walk Subdivision to the existing trail off Northwinds Parkway. The trail is 12' wide and this particular section will consist of multiple bridges and a tunnel under Westisde Parkway. | Integrated Construction & Nobility (ICAN) |  | January, 2022 | September, 2022 | April, 2024 | April, 2024 | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3815/alpha-loop:-old-milton-pkwy-to-northwinds-(tsplost_2,-tier_1) | Sales Tax | $12,000,000 | $11,759,500 | $240,500 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2022 | 2024-01-09 10:22:36 | Georgia | Alpha Loop | 2022-03-31
ALP- 56 | C2228 | Mid-Block Crosswalk (Mid Broadwell Rd at Charlotte Dr) | Tier 1 | Pedestrian Improvements | TSPLOST2 | Alpharetta | Completed | This project is for the construction of a midblock pedestrian crossing on Mid Broadwell Road at the intersection of Charlotte Drive. It includes a refuge area for pedestrians, installation of rectangular rapid flashing beacons (RRFBs), and 6' wide sidewalk along Mid Broadwell Road with approximately 70' length to provide connection to Charlotte Drive sidewalk. | Excellere Construction, LLC | PW | February, 2022 | August, 2022 | October, 2022 | September, 2022 | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3803/mid_block-crosswalk:-mid_broadwell-rd-at-charlotte-dr-(tsplost_2,-tier_1) | Sales Tax | $146,000 | $146,000 | $0 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2022 | 2024-01-09 10:34:02 | Georgia | Broadwell Rd | 2022-03-31
ALP- 57 | C2227 | Mid-Block Crosswalk (Cogburn Road Park) | Tier 1 | Pedestrian Improvements | TSPLOST2 | Alpharetta | Completed | This project is for the construction of a midblock pedestrian crossing on Cogburn Road, in front of the Gatewood subdivision and Cogburn Road park. This includes a refuge area for pedestrians and installation of rectangular rapid flashing beacons (RRFBs). | Excellere Construction, LLC | PW | February, 2022 | September, 2022 | October, 2022 | October, 2022 | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3802/mid_block-crosswalk:-cogburn-rd-park-(tsplost_2,-tier_1) | Sales Tax | $149,401 | $149,391 | $10 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2022 | 2023-02-13 16:22:15 | Georgia | Cogburn Road Park | 2022-03-31
ALP- 58 | C2224 | Raised intersection at Marietta St and Roswell St | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Alpharetta | Design | This is for safety improvements on Roswell Street between Old Roswell Street and Old Milton Pkwy. Some of the main elements included in this project are: wide sidewalk and pedestrian light poles on the east side of Roswell Street, and safety improvements at the intersection of Roswell Street and Marietta Street (4-way STOP controlled). | TBD | Moffatt & Nichol | January, 2024 | September, 2022 | Not Applicable | Not Applicable | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3800/pedestrian-safety-improvements:-marietta-st-and-roswell-st-(tsplost_2,-tier_1) | Sales Tax | $350,000 | $350,000 | $0 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2022 | 2025-07-15 14:22:02 | Georgia | Marietta St | 2022-03-31
ALP- 59 | C2226 | 4 Pedestrian Bridges (Windward Pkwy over Big Creek; Greenway access | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Alpharetta | Construction | This is for the design and construction of 4 pedestrian bridges over Big Creek and Big Creek Tributary along Windward Parkway. The pedestrian bridges will provide connections between the existing sidewalks, facilitating pedestrian movement and crossing over the Creeks. Four bridges are with the following general specifications: 1. Two pedestrian bridges over Big Creek between Union Hill Road and Clubhouse Drive. It consists of an 8' pedestrian bridge (6' clear width) on the north side of Windward Parkway; and another same type of bridge with an additional 10' multi-use trail on the south side of Windward Parkway to connect the existing sidewalk to Big Creek Greenway. 2. Two 8' pedestrian bridges (6' clear width) over Big Creek Tributary between Clubhouse Drive and Admiral Crossing on both sides of Windward Parkway. | Vertical Earth | Moffatt & Nichol | April, 2024 | September, 2024 |  | February, 2026 | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3817/four-pedestrian-bridges-along-windward-pkwy-over-big-creek-greenway-(tsplost_2,-tier_1) | Sales Tax | $4,000,000 | $3,774,500 | $225,500 | Green | Green | Active | imisbach@alpharetta.ga.us | 2022 | 2026-02-18 13:13:38 | Georgia | Windward Pkwy | 2022-03-31
ALP- 60 | C2107 | North Point Pkwy Corridor | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Alpharetta | Design | This is to improve the safety, accessibility, and walkability of pedestrians along the North Point Parkway corridor from Mansell Road to Haynes Bridge Road. Some of the major elements that are considered in this project include reducing the number of travel lanes from 6 to 4 (both sides), 10' curb planter median bioswales, 12' multi-use trail, and 10' planting strip on both sides of the roadway. Also, energy efficient lighting, roadway condition monitoring, and green infrastructure monitoring systems are considered for this project. | TBD | Columbia Engineering | September, 2025 | November, 2022 | Not Applicable | Not Applicable | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3818/north-point-pkwy-corridor-(tsplost_2,-tier_1) | Sales Tax | $13,250,000 | $2,738,300 | $10,511,700 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2021 | 2024-01-09 10:19:35 | Georgia | North Point Pkwy | 2022-03-31
ALP- 61 | C2040 | Tradewinds Ripple Effect Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Alpharetta | Planning | This project includes the design of a series of traffic improvements at multiple intersections due to GA 400 Express Lanes and Tradewinds Parkway access point. Some of the major improvements include dual southbound left turn lanes at the intersection of Westside Parkway and Webb Bridge Road, a roundabout at the intersection of Westside Parkway and Tradewinds Parkway, a traffic signal at the intersection of North Point Parkway and Tradewinds Parkway, and closing roadway median on North Point Parkway at the intersection with Morris Road. | TBD | TBD | Not Applicable | February, 2024 | Not Applicable | Not Applicable | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3805/tradewinds-ripple-effect-improvements-(tsplost_2,-tier_1) | Sales Tax | $432,815 | $10,715 | $422,100 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2020 | 2024-01-09 10:33:11 | Georgia | Tradewinds | 2022-03-31
ALP- 62 | C2230 | Cumming St Corridor Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Alpharetta | Design | The project consists of design and construction of pedestrian and bike safety improvements along Cumming Street, between Highway 9 and Westside Parkway. The proposed project would add a sidewalk on the south side of Cumming Street: 1) from Cricket Lane to Clairmonte Ave, and 2) from where the sidewalk stops on the east side of Henderson Pkwy to Westside Pkwy. | Sol Construction LLC | Moffatt & Nichol | March, 2025 | July, 2022 | Not Applicable | August, 2026 | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3806/cumming-st-corridor-improvements-(tsplost_2,-tier_1) | Sales Tax | $7,758,000 | $4,562,000 | $3,196,000 | Green | Green | Active | imisbach@alpharetta.ga.us | 2022 | 2026-05-04 15:12:59 | Georgia | Cumming St | 2022-03-31
ALP- 63 | C2003 | Milton Ave Improvements (cost is an allocation) | Tier 2 | Operation and Safety Improvements | TSPLOST2 | Alpharetta | Design | This 400-foot roadway improvement will provide operational enhancements as well as bicycle and pedestrian accommodation along Milton Avenue between Old Roswell Street and Roswell Street. This project complements improvements being implemented on the north side of Milton Avenue by the Private Developer. Improvements include correcting excessive cross slope and widening the sidewalk along the south side of the road. Reconfiguring much of the south side parking to parallel parking on paver material, and modifying drainage as needed to accommodate the new configuration. Lighting with hanging baskets and new trees in tree wells are also being proposed. This project will also incorporate utility relocations. Since this project is a Tier 2 Project in the TSPLSOT Program, projects in Tier 1 are accomplished first prior to moving onto Tier 2 or 3 projects, unless there is a re-allocation of funds or revenue collected permits moving onto the other tiers. | TBD | TBD | Not Applicable | Not Applicable | Not Applicable | Not Applicable | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3809/milton-ave-streetscape-(tsplost_2,-tier_2) | Sales Tax | $3,935,740 | $0 | $3,935,740 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2022 | 2024-01-09 10:29:06 | Georgia | Milton Ave | 2022-03-31
ALP- 64 | C2002 | Academy St Improvements | Tier 2 | Operation and Safety Improvements | TSPLOST2 | Alpharetta | Planning | This project is for construction of a series of improvements on Academy Street with the following elements: 6' wide sidewalk on the north side of Academy Street from Loxford Lane to Fire Station 81; inclusion of left turn lanes between Loxford Lane and Wedgewood Drive where possible; inclusion of landscape medians between Loxford Lane and Wedgewood Drive where possible; creation of bike lanes on both sides of Academy Street; Addition of pedestrian lighting along the north side of Academy Street from the driveway of Alpharetta Presbyterian to Fire Station 81; and installation of an emergency traffic signal on Academy Street at Fire Station 81. Design work has been completed. Since this project is a Tier 2 Project in the TSPLSOT Program, projects in Tier 1 are accomplished first prior to moving onto Tier 2 or 3 projects, unless there is a re-allocation of funds or revenue collected permits moving onto the other tiers. |  | TBD | September, 2022 | Not Applicable | Not Applicable | Not Applicable | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3808/academy-st-improvements-(tsplost_2,-tier_2) | Sales Tax | $3,250,000 | $0 | $3,250,000 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2022 | 2024-01-09 10:29:51 | Georgia | Academy St | 2022-03-31
ALP- 65 | C3002 | Roundabout (Mayfield Rd at Canton St) | Tier 3 | Operation and Safety Improvements | TSPLOST2 | Alpharetta | Planning | This project is to perform necessary studies, evaluations, and analysis for replacement of the existing traffic signal at the intersection of Mayfield Road at Canton Street with a single-lane roundabout. Improved traffic flow and safety benefits are potential advantages of a roundabout compared to the existing traffic signal at this location. Since this project is a Tier 3 Project in the TSPLSOT Program, projects in Tier 1 are accomplished first prior to moving onto Tier 2 or 3 projects, unless there is a re-allocation of funds or revenue collected permits moving onto the other tiers. | TBD | TBD | Not Applicable | Not Applicable | Not Applicable | Not Applicable | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3811/roundabout:-mayfield-rd-at-canton-st-(tsplost_2,-tier_3) | Sales Tax | $2,000,000 | $0 | $2,000,000 | Gray | Gray | Active | kmcdowell@alpharetta.ga.us | 2022 | 2024-01-09 10:26:34 | Georgia | Mayfield Rd at Canton St | 2022-03-31
ALP- 66 | C3001 | Roundabout (Hopewell Rd at Vaughan Dr) | Tier 3 | Operation and Safety Improvements | TSPLOST2 | Alpharetta | Design | Design of a roundabout at the intersection of Hopewell Road and Vaughan Drive was funded in FY 2020 and is complete. The roundabout would serve to assist in the following: denote one is entering into Alpharetta; aid in slowing traffic entering into the Downtown area; and assist in turning onto/off of Vaughan Drive. Since this project is a Tier 3 Project in the TSPLSOT Program, projects in Tier 1 are accomplished first prior to moving onto Tier 2 or 3 projects, unless there is a re-allocation of funds or revenue collected permits moving onto the other tiers. |  | TBD | March, 2022 | March, 2022 | Not Applicable | Not Applicable | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3810/roundabout:-hopewell-rd-at-vaughan-dr-(tsplost_2,-tier_3) | Sales Tax | $1,500,000 | $0 | $1,500,000 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2022 | 2024-01-09 10:27:40 | Georgia | Hopewell Rd at Vaughan Dr | 2022-03-31
ALP- 67 | C2104 | WEBB BRIDGE ROAD (NORTH POINT PARKWAY TO GREENWAY) | Tier 1 | Operation and Safety Improvements | TSPLOST | Alpharetta | Construction | This project will include the design of a new bridge over Big Creek to replace the existing vehicular and pedestrian bridges and of a 10'' wide multi-use trail with a 6'' wide planting strip along Webb Bridge Road from east of North Point Parkway to the Big Creek Greenway culvert under Webb Bridge Road. Street trees and pedestrian lighting will be provided along the shoulders. The design will seek to preserve the existing streetscape along the frontage of East Gate Subdivision. The new bridge will provide two 10.5'' travel lanes, header curb, 2'' separation (stamped concrete or concrete pavers) and a 10'' multi-use trail. Bike accommodations will be provided on the roadway from east of North Point Parkway to west of the proposed new bridge over Big Creek. At that point, bicyclists will be merged onto the multi-use trails. Refined concept plans and decision matrix were submitted on February 15, 2021. The design team was given direction to move forward with the "Alternate 3" concept based on this information. | Excellere Construction LLC | Pond & Company | February, 2022 |  |  |  | http://alpharetta.maps.arcgis.com/apps/MapJournal/index.html?appid=c2930590bb57457b908c8d9ec82caba0&section=38 | Sales Tax | $692,508 | $382,143 | $310,365 | Green | Green | Active | psewczwicz@alpharetta.ga.us |  | 2026-03-16 09:52:38 | Georgia | Webb Bridge Rd | 2022-03-31
ALP- 68 | C2001 | Kimball Bridge Rd Widening (Verizon to Georgia Power driveways) | Tier 2 | Congestion Relief | TSPLOST2 | Alpharetta | Land | The project consists of widening Kimball Bridge Road between Verizon and Georgia Power driveways, on the west side of North Point Parkway, to provide a 4-lane section with appropriate pedestrian and bicycle facilities. Design, right-of-way and construction costs are estimated at $2 million and would be part of a future funding request. This improvement is on the approved TSPLOST 2 project list and funding may be available through TSPLOST 2 proceeds if revenue trends highlight collections in excess of what is needed to fund the currently appropriated TSPLOST 2 projects (Tier-1). | Gloson Enterprises | AECOM | February, 2024 | Not Applicable | Not Applicable | February, 2026 | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3807/kimball-bridge-rd-widening-_-verizon-to-georgia-power-driveways-(tsplost_2,-tier_2) | Sales Tax | $2,000,000 | $0 | $2,000,000 | Gray | Green | Active | imisbach@alpharetta.ga.us | 2022 | 2026-02-11 15:22:38 | Georgia | Kimball Bridge Rd | 2022-03-31
ALP- 69 | C3003 | Roundabout (Mayfield Rd at Providence Rd) | Tier 3 | Operation and Safety Improvements | TSPLOST2 | Alpharetta | Planning | This project is to perform necessary studies, evaluations, and analysis for replacement of the existing traffic signal at the intersection of Mayfield Road at Providence Road with a single-lane roundabout. Improved traffic flow and safety benefits are potential advantages of a roundabout compared to the existing traffic signal at this location. Since this project is a Tier 3 Project in the TSPLSOT Program, projects in Tier 1 are accomplished first prior to moving onto Tier 2 or 3 projects, unless there is a re-allocation of funds or revenue collected permits moving onto the other tiers. | TBD | TBD | Not Applicable | Not Applicable | Not Applicable | Not Applicable | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3812/roundabout:-mayfield-rd-at-providence-rd-(tsplost_2,-tier_3) | Sales Tax | $2,000,000 | $0 | $2,000,000 | Gray | Gray | Active | kmcdowell@alpharetta.ga.us | 2022 | 2024-01-09 10:25:54 | Georgia | Mayfield Rd at Providence Rd | 2022-03-31
ALP- 70 | C3005 | Milling and Resurfacing | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | Alpharetta | Planning | This request is for the on-going maintenance of milling and resurfacing and preservation of city streets, funded through TSPLOST II. | Allied Paving | TBD | Not Applicable | Not Applicable | June, 2023 | Not Applicable | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3813/milling-and-resurfacing-(tsplost_2,-tier_3) | Sales Tax | $2,500,000 | $0 | $2,500,000 | Gray | Gray | Active | kmcdowell@alpharetta.ga.us | 2022 | 2023-07-27 11:16:07 | Georgia | City of Alpharetta | 2022-03-31
ALP- 71 | C3004 | Pedestrian Tunnel under Haynes Bridge Rd at GA 400 (Design Concept) | Tier 3 | Pedestrian and Bike Improvements | TSPLOST2 | Alpharetta | Design | This project is for the construction of a pedestrian tunnel as part of the Alpha Loop trail system under Haynes Bridge Road to connect developments on the northern and southern sides of Haynes Bridge Road. Project is under design, managed by the North Fulton Community Improvement District (NFCID). | TBD | TBD | Not Applicable | Not Applicable | Not Applicable | Not Applicable | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3816/alpha-loop:-pedestrian-tunnel-under-haynes-bridge-rd-at-ga-400-(2022-parks-bond) | Sales Tax | $500,000 | $0 | $500,000 | Gray | Gray | Active | kmcdowell@alpharetta.ga.us | 2022 | 2024-01-09 10:20:57 | Georgia | Haynes Bridge Rd | 2022-03-31
CH- 10 |  | City Wide | Tier 1 | Project Management | TSPLOST2 | Chattahoochee Hills | Planning | traffic control, single pass chip seal, microsurfacing, thermoplastic solid traffic striping 5” white, thermoplastic solid traffic striping 5” yellow, thermoplastic traffic striping 24” white, thermoplastic skip traffic striping 5” white, and raised pavement markers single indicated on centerline for roadways identified by the engineers and public works director | Asphalt Paving Systems | Keck & Wood | June, 2024 | April, 2024 | June, 2024 | June, 2024 | https://www.chatthillsga.us/ | Sales Tax | $60,689 | $777 | $59,912 | Green | Green | Active | robbie.rokovitz@chatthillsga.us | 2024 | 2024-04-23 16:29:47 | Georgia | City of Chattahoochee Hills | 2024-04-23
CH- 11 |  | City Wide | Tier 2 | Maintenance and Safety Enhancements | TSPLOST2 | Chattahoochee Hills | Construction | traffic control, single pass chip seal, microsurfacing, thermoplastic solid traffic striping 5” white, thermoplastic solid traffic striping 5” yellow, thermoplastic traffic striping 24” white, thermoplastic skip traffic striping 5” white, and raised pavement markers single indicated on centerline for roadways identified by the engineers and public works director | Asphalt Paving Systems | Keck & Wood | June, 2024 | April, 2024 | June, 2024 | June, 2024 | https://www.chatthillsga.us/ | Sales Tax | $1,213,788 | $0 | $1,213,788 | Green | Green | Active | robbie.rokovitz@chatthillsga.us | 2024 | 2024-04-23 16:26:13 | Georgia | City of Chattahoochee Hills | 2024-04-23
CH- 12 |  | City Wide | Tier 2 | Quick Response Projects | TSPLOST2 | Chattahoochee Hills | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Chattahoochee Hills | 2022-03-31
CH- 13 |  | City Wide | Tier 2 | Project Management | TSPLOST2 | Chattahoochee Hills | Planning | deep patching on Rico Road (SFP to Hutcheson Ferry Road) utilizing 19mm asphalt, a 4” wide milling head at a depth of 4”, as well as 4” paint to repair existing striping damaged during construction | Piedmont Paving | Keck & Wood | August, 2024 | May, 2024 | August, 2024 | August, 2024 | https://www.chatthillsga.us/ | Sales Tax | $88,459 | $777 | $87,682 | Green | Green | Active | robbie.rokovitz@chatthillsga.us | 2024 | 2024-04-23 16:29:23 | Georgia | City of Chattahoochee Hills | 2024-04-23
CH- 14 |  | City Wide | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | Chattahoochee Hills | Construction | deep patching on Rico Road (SFP to Hutcheson Ferry Road) utilizing 19mm asphalt, a 4” wide milling head at a depth of 4”, as well as 4” paint to repair existing striping damaged during construction | Piedmont Paving | Keck & Wood | August, 2024 | May, 2024 | August, 2024 | August, 2024 | https://www.chatthillsga.us/ | $269,180 from TSPLOST & $1,500.000 from Capital | $1,769,180 | $0 | $1,769,180 | Green | Green | Active | robbie.rokovitz@chatthillsga.us | 2024 | 2024-04-23 16:38:59 | Georgia | City of Chattahoochee Hills | 2024-04-23
CH- 15 |  | City Wide | Tier 3 | Quick Response Projects | TSPLOST2 | Chattahoochee Hills | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Chattahoochee Hills | 2022-03-31
CH- 16 |  | City Wide | Tier 3 | Project Management | TSPLOST2 | Chattahoochee Hills | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Chattahoochee Hills | 2022-03-31
CH- 2 | CH-101 | Rico Road Part A Maintenance and Improvements | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Chattahoochee Hills | Completed | The project consists of Hot Mix Asphalt (HMA) patching, HMA leveling, HMA topping, striping, shoulder building, and grassing on 1.4 miles of Rico Road beginning at South Fulton Parkway and ending at Campbellton Redwine Road. | ER Snell |  | August, 2017 | September, 2017 | December, 2017 | December, 2017 |  | Sales Tax | $304,770 | $301,469 | $3,301 | Green | Green | Active | robbie.rokovitz@chatthillsga.us | 2017 | 2021-12-13 18:29:50
CH- 3 | CH-102 | Quick Response Projects | Tier 1 | Quick Response | TSPLOST | Chattahoochee Hills | Completed | Location #1 û Wilkerson Mill Road: This portion of the project consists of Hot Mix Asphalt (HMA) patching, HMA leveling, HMA topping, striping, raised pavement markers, shoulder building, and grassing on approx. 2.5 miles of Wilkerson Mill Road beginning at Cochran Mill Road and ending at Cascade Palmetto Highway. Location #2 û Atlanta Newnan Road: This portion of the project consists of Full Depth Reclamation of the existing road bed, HMA binder and topping course, shoulder building, grassing, striping and raised pavement markers on 1.5 miles of roadway beginning at Hutcheson Ferry Road and ending at the bridge at the Coweta County line. | Atlanta Paving | DWS | September, 2018 | October, 2018 | December, 2018 | February, 2019 |  | $470,233 TSPLOST & $663,154 Capital Fund | $1,176,646 | $1,133,387 | $43,259 | Green | Green | Active | robbie.rokovitz@chatthillsga.us | 2018-2019 | 2021-12-13 18:30:01
CH- 4 | CH-201 | Maintenance and Safety Enhancements | Tier 2 | Maintenance and Safety Enhancements | TSPLOST | Chattahoochee Hills | Completed | The project consists of ôdeep patchingö (mill & inlay) repair of various roads as outlined in the bid packet. All milling quantities are based on the use of a 4Æ wide milling head. All patching asphalt quantities are based on an average depth of 3.5ö of asphalt binder. Precise locations have not been determined but will be marked in conjunction with Contractor prior to commencement of actual work. The tonnage shown for each road is an estimate and may be adjusted as required to match field conditions. | Blount Construction | DW Smith | June, 2019 | September, 2019 | October, 2019 | October, 2019 |  | Sales Tax ($365,000 TSPLOST/$52,8836 Capital Fund) | $418,322 | $417,836 | $486 | Green | Green | Active | robbie.rokovitz@chatthillsga.us | 2018-2019 | 2021-12-13 18:30:13
CH- 5 | CH-202 | Maintenance and Safety Enhancements | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Chattahoochee Hills | Construction | This project consists of deep patching South Fulton Parkway at the bridge/County line, Two locations on Campbellton-Redwine (approx. 1,000 lf), Cochran Mill @ Woodruff, Rivertown @ Campbellton-Redwine, Complete work begun on Rivertown, Hutcheson Ferry (approx. 1,000 lf). Crack sealing South Fulton Parkway (areas not addressed by GDOT), Hutcheson Ferry (from The Inn to Cochran Mill), Campbellton-Redwine, and striping South Fulton Parkway, Hutcheson Ferry, Rico Road (southern portion), Cochran Mill Road, Rivertown Road and Campbellton-Redwine | ER Snell | DWS | August, 2021 | September, 2021 | November, 2021 | December, 2021 | www.chatthillsga.us | Sales Tax | $1,251,765 | $1,211,895 | $39,870 | Green | Green | Active | robbie.rokovitz@chatthillsga.us | 2021 | 2021-12-13 18:29:16
CH- 6 | CH-301 | Maintenance and Safety Enhancements | Tier 2 | Maintenance and Safety Enhancements | TSPLOST | Chattahoochee Hills | Planning | Maintenance and Safety Enhancements in City of Chattahoochee Hills | [7 empty] | Sales Tax | $369,464 | $0 | $369,464 | Gray | Gray | Active | wsmith@designgi.com
CH- 7 | CH-302 | Quick Response Projects in City of Chattahoochee Hills | Tier 2 | Quick Response | TSPLOST | Chattahoochee Hills | Planning | Quick Response Projects in City of Chattahoochee Hills | [7 empty] | Sales Tax | $9,514 | $0 | $9,514 | Gray | Gray | Active | wsmith@designgi.com
CH- 8 |  | City Wide | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | Chattahoochee Hills | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Chattahoochee Hills | 2022-03-31
CH- 9 |  | City Wide | Tier 1 | Quick Response Projects | TSPLOST2 | Chattahoochee Hills | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Chattahoochee Hills | 2022-03-31
CP- 10 | CP-109 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | College Park | Planning | Operations and Safety in City of College Park - Virginia Avenue at Adams Street | [7 empty] | Sales Tax | $176,000 | $0 | $176,000 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 11 | CP-110 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | College Park | Planning | Operations and Safety in City of College Park - Virginia Avenue at Madison Street | [7 empty] | Sales Tax | $176,000 | $0 | $176,000 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 12 | CP-111 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | College Park | Planning | Operations and Safety in City of College Park - Conley Street at Columbia Avenue | [7 empty] | Sales Tax | $176,000 | $0 | $176,000 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 13 | CP-112 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | College Park | Planning | Operations and Safety in City of College Park - Old National Highway at Godby Road | [7 empty] | Sales Tax | $1,000,000 | $0 | $1,000,000 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 14 | CP-113 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | College Park | Planning | Operations and Safety in City of College Park - Rhodes Street Ext. from Camp Creek Parkway to Yale Avenue | [7 empty] | Sales Tax | $1,600,000 | $0 | $1,600,000 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 15 | CP-114 | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | College Park | Planning | Pedestrian / Bike Improvements in City of College Park - Old National Highway at I/285 (intersection only) | [7 empty] | Sales Tax | $156,000 | $0 | $156,000 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 16 | CP-115 | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | College Park | Planning | Pedestrian / Bike Improvements in City of College Park - Virginia Avenue bike lanes (Main Street to Harrison Road) | [7 empty] | Sales Tax | $166,000 | $0 | $166,000 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 17 | CP-116 | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | College Park | Planning | Pedestrian / Bike Improvements in City of College Park - Lake Shore Drive/Janice Drive (Herschel to Sun Valley) | [7 empty] | Sales Tax | $374,000 | $0 | $374,000 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 18 | CP-117 | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | College Park | Planning | Pedestrian / Bike Improvements in City of College Park - Camp Truitt (Herschel Road to Airport Drive) | [7 empty] | Sales Tax | $515,872 | $0 | $515,872 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 19 | CP-118 | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | College Park | Planning | Pedestrian / Bike Improvements in City of College Park - College Street (Harvard Avenue to Oxford Avenue) | [7 empty] | Sales Tax | $908,000 | $0 | $908,000 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 2 | CP-101 | Maintenance and Safety Enhancements | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | College Park | Completed | Maintenance and Safety Enhancements in City of College Park -Resurfacing | Mullins Brother Paving |  | Not Applicable | September, 2019 | April, 2020 |  |  | Sales Tax | $716,447 | $450,801 | $265,646 | Green | Green | Active | rcotton@collegeparkga.com | 2019 | 2021-03-17 16:06:34
CP- 20 | CP-119 | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | College Park | Planning | Pedestrian / Bike Improvements in City of College Park - Virginia Avenue (Lee Street to Atlanta Street) | [7 empty] | Sales Tax | $1,288,000 | $0 | $1,288,000 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 21 | CP-120 | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | College Park | Planning | Landscape/Streetscape in City of College Park - Buffington Road at South Fulton Parkway (PARTIAL FUNDING) | [7 empty] | Sales Tax | $502,500 | $0 | $502,500 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 22 | CP-121 | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | College Park | Planning | Pedestrian/Bike/Landscape/Streetscape in City of College Park -Old National Highway at I/285 (PARTIAL FUNDING) | [7 empty] | Sales Tax | $502,500 | $0 | $502,500 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 23 | CP-121 | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | College Park | Planning | Pedestrian/Bike/Landscape/Streetscape in City of College Park - Old National Highway at I/285 (PARTIAL FUNDING) | [7 empty] | Sales Tax | $502,500 | $0 | $502,500 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 24 | CP-122 | Quick Response Projects | Tier 1 | Quick Response | TSPLOST | College Park | Planning | Quick Response Projects in City of College Park - Quick Response Projects - To Be Determined | [7 empty] | Sales Tax | $819,231 | $0 | $819,231 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 25 | CP-202 | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 2 | Pedestrian and Bike Improvements | TSPLOST | College Park | Planning | Landscape/ Streetscape in City of College Park - Camp Creek Parkway at I/85 (PARTIAL FUNDING) | [7 empty] | Sales Tax | $502,500 | $0 | $502,500 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 26 | CP-203 | Operations and Safety | Tier 2 | Operation and Safety Improvements | TSPLOST | College Park | Planning | Operations and Safety in City of College Park - College Street at Harvard Avenue | [7 empty] | Sales Tax | $176,000 | $0 | $176,000 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 27 | CP-204 | Operations and Safety | Tier 2 | Operation and Safety Improvements | TSPLOST | College Park | Planning | Operations and Safety in City of College Park - Washington Rd From Carriage Way to Lyle Terrace (along College Park city boundary) | [7 empty] | Sales Tax | $352,000 | $0 | $352,000 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 28 | CP-205 | Quick Response Projects | Tier 2 | Operation and Safety Improvements | TSPLOST | College Park | Planning | Quick Response Projects in City of College Park - Quick Response Projects - To Be Determined | [7 empty] | Sales Tax | $423,793 | $0 | $423,793 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 29 | CP-103 | Quick Response Projects | Tier 3 | Quick Response | TSPLOST | College Park | Planning | Quick Response Projects in City of College Park - Quick Response Projects - To Be Determined | [7 empty] | Sales Tax | $1,887,271 | $0 | $1,887,271 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 3 | CP-102 | Bridges | Tier 1 | Bridges | TSPLOST | College Park | Planning | Bridge Improvement in City of College Park - Herschel Road at Camp Creek, South Fork | [7 empty] | Sales Tax | $544,500 | $0 | $544,500 | Gray | Gray | Active | melissa.echevarria@collegeparkga.com |  | 2021-11-10 18:10:33
CP- 30 | CP-101 | Maintenance and Safety Enhancements | Tier 2 | Maintenance and Safety Enhancements | TSPLOST | College Park | Completed | TSplost resurfacing Project is now completed | Mullins Brother Paving |  | September, 2019 | September, 2019 | April, 2020 | April, 2020 |  | Sales Tax | $716,447 | $246,072 | $470,375 | Green | Green | Active | rcotton@collegeparkga.com | 2019 | 2020-11-19 20:16:10
CP- 31 | CP-101 | Herschel Road Pedestrian Sidewalk Improvement project | Tier 1 | Pedestrian Improvements | TSPLOST | College Park | Completed | Pedestrian Sidewalk Improvement project on Herschel Road From Roosvelt Hwy(us29) to Colonial Drive | Pentagon 540, LLC | City of College Park engineering Department | September, 2018 | September, 2018 | November, 2018 | November, 2018 |  | Sales Tax | $170,220 | $167,992 | $2,228 | Green | Green | Active | rcotton@collegeparkga.com | 2018 | 2021-10-21 19:57:12
CP- 32 |  | City Wide | Tier 1 | Quick Response Projects | TSPLOST2 | College Park | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of College Park | 2022-03-31
CP- 33 |  | Rhodes St | Tier 1 | Quick Response Projects | TSPLOST2 | College Park | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Rhodes St | 2022-03-31
CP- 34 |  | Columbia Ave | Tier 2 | Roadway Project | TSPLOST2 | College Park | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Columbia Ave | 2022-03-31
CP- 35 |  | City Wide | Tier 2 | Operation and Safety Improvements | TSPLOST2 | College Park | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of College Park | 2022-03-31
CP- 36 |  | Global Gateway | Tier 2 | Operation and Safety Improvements | TSPLOST2 | College Park | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Global Gateway | 2022-03-31
CP- 37 |  | City Wide | Tier 3 | Roadway Project | TSPLOST2 | College Park | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of College Park | 2022-03-31
CP- 4 | CP-103 | Bridges | Tier 1 | Bridges | TSPLOST | College Park | Planning | Bridge Improvement in City of College Park - Camp Creek Parkway Frontage Road at Camp Creek,South Fork | [7 empty] | Sales Tax | $356,400 | $0 | $356,400 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 5 | CP-104 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | College Park | Planning | Old National Highway planning study (I/285 to Surrey Trail) | [7 empty] | Sales Tax | $45,280 | $0 | $45,280 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 6 | CP-105 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | College Park | Planning | Old National Highway signal timing maintenance | [7 empty] | Sales Tax | $100,000 | $0 | $100,000 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 7 | CP-106 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | College Park | Planning | Operations and Safety in City of College Park - Main Street at Virginia Avenue | [7 empty] | Sales Tax | $176,000 | $0 | $176,000 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 8 | CP-107 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | College Park | Planning | Operations and Safety in City of College Park - Main Street at Harvard Avenue | [7 empty] | Sales Tax | $176,000 | $0 | $176,000 | Gray | Gray | Active | jmyers@collegeparkga.com
CP- 9 | CP-108 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | College Park | Planning | Operations and Safety in City of College Park - Virginia Avenue at College Street | [7 empty] | Sales Tax | $176,000 | $0 | $176,000 | Gray | Gray | Active | jmyers@collegeparkga.com
CSF- 1 | RC 100 | Bethsaida Road (Jonesboro Rd to Clayton County Ln) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The Bethsaida Road (Jonesboro Rd to Clayton County Ln) to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | November, 2018 |  |  | Sales Tax | $697,059 | $614,322 | $82,737 | Green | Green | Inactive | steve.williams@fultoncountyga.gov | 2018 | 2021-10-12 13:20:26
CSF- 10 | RC 109 | Rivertown Road (Chattahoochee Hills City limits to Fairburn City Limits) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The Rivertown Road (Chattahoochee City Limits to Fairburn City Limits) to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable | March, 2019 | August, 2019 |  |  | Sales Tax | $872,352 | $726,550 | $145,802 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 16:16:33
CSF- 100 | RST 208 | Merrywood I-III (LL 159/162 Dist 13) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The primary work is to resurface the final asphalt topping layer. The roads (Merrywood Ct, Merrywood Dr, and Smokeridge Dr) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. Milling of the existing asphalt surface is not expected to be required for these roadways. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $94,383 | $97,351 | $-2,968 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 16:40:02
CSF- 101 | RST 209 | Overlook Camp Creek 1/1A | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The primary work is to resurface the final asphalt topping layer. The roads (Lost Cove Dr, Minkslide Dr, and War Trace Dr) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. Milling of the existing asphalt surface is not expected to be required for these roadways. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $95,530 | $88,501 | $7,029 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 20:32:52
CSF- 102 | RST 210 | Parks at Cedar Grove 1/2 of Subdivision | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The primary work is to resurface the final asphalt topping layer. The roads (Fairmont Way, Misty Walk, Parkland Bend, and Parks Trl) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. Milling of the existing asphalt surface is not expected to be required for these roadways. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $175,000 | $192,027 | $-17,027 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 20:33:33
CSF- 103 | RST 211 | Preston's Vineyard, (LL 169, Dist 9F) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The primary work is to resurface the final asphalt topping layer. The road (Preston's Estates) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. Milling of the existing asphalt surface is not expected to be required for these roadways. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $19,830 | $26,667 | $-6,837 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 20:34:01
CSF- 104 | RST 212 | Providence Glen < (LL 188 Dist 13) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The primary work is to resurface the final asphalt topping layer. The roads within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. Milling of the existing asphalt surface is not expected to be required for these roadways. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $42,960 | $50,772 | $-7,812 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 20:34:18
CSF- 105 | RST 213 | Renaissance at South Park | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The primary work is to resurface the final asphalt topping layer. The roads (Avalon Sq, Avalon Blvd, Bucknell Ter, Cabrini Pl, Radford Loop, Rutgers Cir, and Westwood Trl) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. Milling of the existing asphalt surface is not expected to be required for these roadways. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $141,831 | $177,351 | $-35,520 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 20:34:30
CSF- 106 | RST 214 | Stoneridge 3 | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | Garnet Ave, Sapphire Bend, Topaz Rd and Feldspar Way) within the subdivision will have their final asphalt topping layer resurfaced. The work will include all the necessary preparation work which may include full depth of pavement patching and a surface treatment prior to final topping. Removal of the top asphalt layer (milling) is not expected to be required for these roadways. The roads will then be resurfaced with a uniform layer of asphalt in manner so as to provide uniformity of depth and a smooth transition to existing pavement. After resurfacing, all existing pavement markings such as line striping, crosswalks etc. will be reinstalled. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $168,840 | $89,782 | $79,058 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 20:34:55
CSF- 107 | RST 216 | Thornwood Park , (LL 132/133 Dis 13) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The primary work is to resurface the final asphalt topping layer. The roads (Bigwood Trl, Splitpine Ct, and Old Madison Pl) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. Milling of the existing asphalt surface is not expected to be required for these roadways. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $101,920 | $129,142 | $-27,222 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 20:13:48
CSF- 108 | RST 215 | St. Joseph Phase 1 | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Saint Peter Way, Saint Thomas Court, and Saint Judes Drive) within the subdivision is to resurface the final asphalt topping layer. The roads within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. The subject subdivison was topped through an earlier contract outside TSPLOST funding. | E R Snell | Not Applicable | Not Applicable |  | August, 2017 | Not Applicable |  | Sales Tax | $101,920 | $129,142 | $-27,222 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 16:49:07
CSF- 109 | RST 217 | Towncreek @ Cedar Grove PH2 | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The primary work is to resurface the final asphalt topping layer. The roads (Locherby Dr and Lochley Dr) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. Milling of the existing asphalt surface is not expected to be required for these roadways. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $45,998 | $46,579 | $-581 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 20:14:04
CSF- 11 | RS 367 | Oakley Township | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Oakley Road and Red Hawk Run) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $459,740 | $336,295 | $123,445 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 19:56:29
CSF- 110 | RS 300 | Ashley Downs | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Ashington Court, Ashley Downs Lane, Circle Court, Fox Hall Lane South, Green Bower Lane, Hallie Mill Road, Marcliff Court, Marley Drive, Thornbury Way I) to be resurfaced within the subdivision may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | May, 2018 |  |  | Sales Tax | $431,006 | $377,254 | $53,752 | Green | Green | Inactive | roussan.francois@fultoncountyga.gov | 2018 | 2021-02-06 23:39:18
CSF- 111 | RS 301 | Beacon Hills | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Berry Hill Court, Diann Court, Dianne Court, Dianne Drive, Green Trail, and Greentree Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $124,513 | $89,983 | $34,530 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-02 14:13:31
CSF- 112 | RS 302 | Beaver Creek | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Beaver Creek Trail and Kimberly Mill Lane) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | June, 2018 |  |  | Sales Tax | $76,623 | $60,231 | $16,392 | Green | Green | Inactive | roussan.francois@fultoncountyga.gov | 2018 | 2021-02-06 23:39:45
CSF- 113 | RS 303 | Benchmark | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Azimuth Court, Bearing Way, Benchmark Drive, Transit Circle, and Traverse Court) within he subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | November, 2018 |  |  | Sales Tax | $130,260 | $166,456 | $-36,196 | Red | Green | Inactive | roussan.francois@fultoncountyga.gov | 2018 | 2021-02-06 23:40:44
CSF- 114 | RS 304 | Bentwood Trace | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Brentwood Court, Fruitwood Trace, and Teakwood Lane) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | May, 2018 |  |  | Sales Tax | $76,623 | $98,773 | $-22,150 | Red | Green | Inactive | roussan.francois@fultoncountyga.gov | 2018 | 2021-02-06 23:41:04
CSF- 115 | RS 305 | Bethsaida West | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Dawn Drive, Lori Lane, Renee Dawn Court, and Sandy Circle) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | May, 2018 |  |  | Sales Tax | $394,610 | $82,362 | $312,248 | Green | Green | Inactive | roussan.francois@fultoncountyga.gov | 2018 | 2021-02-06 23:41:39
CSF- 116 | RS 306 | Big Creek | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Ann Arbor Drive and Arbor Shores Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | August, 2022 |  |  | Sales Tax | $95,779 | $88,571 | $7,208 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:36:56
CSF- 117 | RS 307 | Bon Haven Estates | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Granada Drive, Granada Lane, Valley Brook Drive, Valley Brook Lane, and Valley Brook Terrace) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $425,260 | $226,363 | $198,897 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:37:44
CSF- 118 | RS 308 | Brentwood Place | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Carisbrook Drive, Carisbrook Lane, Shenfield Drive, and Shenfield Lane) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | May, 2021 |  |  | Sales Tax | $130,260 | $126,786 | $3,474 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:38:18
CSF- 119 | RS 309 | Canaan Glen | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Canaan Glen Way, Waterway Crossing, and Waterway Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | July, 2021 |  |  | Sales Tax | $78,539 | $132,342 | $-53,803 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-02 14:14:00
CSF- 12 | RS 368 | Old National East | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Britley Terrace, Montilly Circle, Montilly Place, Penfield Place, Pleasant Hill Road, Scofield Road, Shancey Lane, and Surrey Trail) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | August, 2019 |  |  | Sales Tax | $990,357 | $765,093 | $225,264 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 19:57:25
CSF- 120 | RS 310 | Canaan Trace | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Branch View Drive, Clearbrook Place, Pebblecreek Place, and Poplar Way) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | May, 2021 |  |  | Sales Tax | $95,779 | $211,791 | $-116,012 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:38:54
CSF- 121 | RS 311 | Canaan Walk | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Ivy Glen Court and Wind Crest Place) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | June, 2021 |  |  | Sales Tax | $78,539 | $144,544 | $-66,005 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:39:17
CSF- 122 | RS 312 | Canaan Woods | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The road (Canaan Woods Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | June, 2021 |  |  | Sales Tax | $53,636 | $95,656 | $-42,020 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2021-10-12 17:19:03
CSF- 123 | RS 313 | Carlo Woods | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Carlo Court, Carlo Terrace, and Carlo Woods Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | October, 2021 |  |  | Sales Tax | $137,922 | $173,483 | $-35,561 | Yellow | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:40:12
CSF- 124 | RS 314 | Cascade Hills | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Cascade Crossing, Cascade Hill Drive, Cascade Hills Circle, Cascade Rise, and Cascade Rise Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $379,286 | $492,532 | $-113,246 | Yellow | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:40:52
CSF- 125 | RS 315 | Cascade Knolls | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Garr Circle, Shadybrook Lane, Timbergrove Drive, Wilson Mill Road, and Greenwood Lane) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $136,006 | $78,266 | $57,740 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:41:23
CSF- 126 | RS 316 | Cascade Knolls Drive | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The road (Glenwood Lake) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $47,890 | $48,131 | $-241 | Yellow | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:41:54
CSF- 127 | RS 317 | Central Park | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The road (Central Park Place) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $32,565 | $24,972 | $7,593 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:42:39
CSF- 128 | RS 318 | Chippewa Forest | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Chippewa Court, Chippewa Drive, Oswego Trail, and Owatonna Circle) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $212,630 | $240,953 | $-28,323 | Yellow | Green | Inactive | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 19:23:56
CSF- 129 | RS 319 | Cliftondale | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Cliftondale Place, Hershel Place, and Newborn Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | August, 2022 |  |  | Sales Tax | $522,955 | $757,915 | $-234,960 | Yellow | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:43:41
CSF- 13 | RS 370 | Park Village | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Planning | Project not planned for resurfacing since it belongs to the city of Fairburn. |  | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $128,344 | $0 | $128,344 | Green | Green | Inactive | roussan.francois@fultoncountyga.gov |  | 2023-03-02 14:20:38
CSF- 130 | RS 320 | Creel & Bethsaida Corner | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Planning | The road (Lupine Ridge Lane) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | July, 2020 |  |  | Sales Tax | $9,578 | $67,533 | $-57,955 | Green | Green | Inactive | roussan.francois@fultoncountyga.gov | Duplicate project with RS 321 | 2021-05-03 19:27:02
CSF- 131 | RS 321 | Creel Crossing | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Planning | The roads (Lupine Court, Lupine Court Cul-de-Sac, Lupine Ridge Lane, Woodhue Court, and Woodhue Forest Lane) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | July, 2020 |  |  | Sales Tax | $80,455 | $67,533 | $12,922 | Green | Green | Inactive | roussan.francois@fultoncountyga.gov | 2019 | 2021-02-07 00:00:42
CSF- 132 | RS 322 | Deerwood Park | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Buck Creek Court, Buck Creek Drive, Connell Road I, Doe Run, White Trail Lane, Yearling Court, and Doe Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | May, 2018 |  |  | Sales Tax | $206,883 | $207,837 | $-954 | Yellow | Green | Inactive | roussan.francois@fultoncountyga.gov | 2018 | 2021-02-06 23:42:28
CSF- 133 | RS 323 | Derrick Creek | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The road (Raventree Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | August, 2021 |  |  | Sales Tax | $76,623 | $74,994 | $1,629 | Yellow | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:44:27
CSF- 134 | RS 324 | Devonshire | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Chesterfield Court, Downey Drive, Dunbritan Lane, Heatherly Drive, Knighton Circle, Knighton Drive, Sandgate Circle, Sandgate Drive, Sandgate Road, andWexford Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | August, 2018 |  |  | Sales Tax | $432,922 | $297,506 | $135,416 | Green | Green | Inactive | roussan.francois@fultoncountyga.gov | 2018 | 2021-02-06 23:43:07
CSF- 135 | RS 325 | Edgewater | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Canyon Lake Court and Canyon Lake Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $93,864 | $116,466 | $-22,602 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-02 14:14:38
CSF- 136 | RS 326 | Emerald Pointe | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Emerald Green Court, Emerald Pointe Circle, Gemstone Court, Gemstone Place, Crystal Green Court, and Hemperly Road) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | July, 2018 |  |  | Sales Tax | $314,156 | $230,653 | $83,503 | Green | Green | Inactive | roussan.francois@fultoncountyga.gov | 2018 | 2021-02-06 23:43:30
CSF- 137 | RS 327 | Enon Forest | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Datona Drive, Happy Valley Circle, and Orange Road) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | May, 2021 |  |  | Sales Tax | $362,045 | $265,342 | $96,703 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2021-10-12 18:18:19
CSF- 138 | RS 328 | Estes Drive | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The road (Estes Drive) with the subdivisionto be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | November, 2018 |  |  | Sales Tax | $57,468 | $29,728 | $27,740 | Red | Green | Inactive | roussan.francois@fultoncountyga.gov | 2018 | 2021-02-06 23:44:07
CSF- 139 | RS 329 | Falcon Forest | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Kelden Circle and Kelden Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $113,019 | $93,426 | $19,593 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:45:31
CSF- 14 | RS 371 | Parkland Woods | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Marsh Drive, Marshwood Trace II, and Westcliffe Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | August, 2021 |  |  | Sales Tax | $70,877 | $427,564 | $-356,687 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 14:08:04
CSF- 140 | RS 330 | Feldwood Pines | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Bearing Way II and Morning Creek Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | May, 2021 |  |  | Sales Tax | $65,130 | $65,130 | $0 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:46:09
CSF- 141 | RS 331 | Flat Shoals Estates | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Beethoven Circle, Beethoven Court, Liszt Lane, Mozart Court, and Mozart Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | July, 2020 |  |  | Sales Tax | $279,675 | $210,978 | $68,697 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 19:32:04
CSF- 142 | RS 332 | Forest Downs | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Forest Crossing Way, Forest Downs Circle, Forest Downs Lane, Wolf Down Court, and Wolf Downs Way) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | November, 2019 |  |  | Sales Tax | $319,903 | $339,214 | $-19,311 | Yellow | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 19:33:13
CSF- 143 | RS 333 | Fox Fire S/D | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Blue Fox Circle, Sable Fox Rd, Grey Fox Way, and Polar Fox Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | June, 2021 |  |  | Sales Tax | $377,370 | $205,805 | $171,565 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:46:46
CSF- 144 | RS 334 | Gladstone Hills | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Gage Court, Galena Court, Garvey Drive, Gladden Road, Gledstone Way, and Gledstone Way) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | August, 2021 |  |  | Sales Tax | $172,403 | $370,153 | $-197,750 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2021-10-12 18:45:36
CSF- 145 | RS 335 | Granada | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Casa Verde Drive and San Costa Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $76,623 | $62,018 | $14,605 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:47:24
CSF- 146 | RS 336 | Guilford Pointe | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Birdie Lane II, Brightwood Lane, and Ninas Trace) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $65,130 | $107,303 | $-42,173 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 14:15:32
CSF- 147 | RS 337 | Hallie Hills | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Ansted Lane, Butterfield Court, Butterfield Lane, Carisbrook Court, Earlhurst Road, Fox Hall Court, Greenbower Court, Greenbower Lane, Hallie Lane, Hickory Fox Court, Mapledale Lane, Marlborough Circle, Millsboro Lane, Neola Lane, Pennfair Lane, Peppermill Court, Peppermill Lane, Ravencliff Lane, Ravencliff Road, Rimel Lane, Rocky Springs Court, Shoppers Lane, Spicewood Court, Spicewood Court North, Spicewood Court South, Spicewood Lane, Stockdale Court, Turtle Bend Lane, and Winterside Lane) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $733,669 | $1,649,962 | $-916,293 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-02 14:16:04
CSF- 148 | RS 338 | Hania Flowers Estates | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Darry Court, Hania Drive, Hassana Lane, Hussamy Lane, and Imad Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | April, 2018 |  |  | Sales Tax | $281,591 | $212,601 | $68,990 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 19:36:31
CSF- 149 | RS 339 | Happy Hollow | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Happy Hollow Court and Pullen Lane) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $57,468 | $66,586 | $-9,118 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-02 14:18:32
CSF- 15 | RS 372 | Picardy Circle South | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Lantern Lane II, Picardy Circle North, and Picardy Circle South) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | July, 2019 |  |  | Sales Tax | $61,299 | $47,859 | $13,440 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 19:59:53
CSF- 150 | RS 340 | Hidden Valley | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Hidden Court and Hidden Valley Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $86,201 | $136,845 | $-50,644 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:49:15
CSF- 151 | RS 341 | Highpoint | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The road (North Close) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $9,578 | $221,507 | $-211,929 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-02 14:19:10
CSF- 152 | RS 342 | Hillandale | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Beacon Drive, Carriage Court I, Carriage Lane, Cedar Wood Drive, Cedarwood Court, Cheryl Lynne Lane, Green Trail Drive, Guilford Lane, Hillandale Drive, La Jean Drive, Middleburg Drive, Ocean Valley Drive, Old Carriage Drive, Old Farm Road, Pineside Drive, and Spruce Point Road(Beacon Drive, Carriage Court I, Carriage Lane, Cedar Wood Drive, Cedarwood Court, Cheryl Lynne Lane, Green Trail Drive, Guilford Lane, Hillandale Drive, La Jean Drive, Middleburg Drive, Ocean Valley Drive, Old Carriage Drive, Old Farm Road, Pineside Drive, and Spruce Point Road) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | July, 2018 |  |  | Sales Tax | $865,844 | $424,896 | $440,948 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 19:38:40
CSF- 153 | RS 343 | Huntington Estates | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Fox Lane Drive, Fox Trail Drive, Hunters Forest Court, and Hunters Forest Lane) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | November, 2019 |  |  | Sales Tax | $76,623 | $160,756 | $-84,133 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 19:39:42
CSF- 154 | RS 344 | Jamaica | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Montego Bay Drive and Port Antonio Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $116,851 | $100,639 | $16,212 | Yellow | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:49:44
CSF- 155 | RS 345 | Kensington Woods | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The road (Kenwood Trail) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $53,636 | $31,866 | $21,770 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:50:26
CSF- 156 | RS 346 | Kimberly | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Bellburn Road, Birling Drive, Cadiz Circle, Cadiz Lane North, Cadiz Lane South, Glace Road, Keenan Court West, Keenan Lane, Keenan Road, Kimberly Mill Road, Piney Fork Lane, and Valleybend Lane) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | June, 2019 |  |  | Sales Tax | $840,941 | $533,321 | $307,620 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 19:41:25
CSF- 157 | RS 347 | Kimberly Forest | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Kimberly Creek Place, Kimberly Forest Way, and Onyx Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | June, 2018 |  |  | Sales Tax | $76,623 | $39,346 | $37,277 | Green | Green | Inactive | roussan.francois@fultoncountyga.gov | 2018 | 2021-02-06 23:46:48
CSF- 158 | RS 348 | Kings Crest Court | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The road (Kings Crest) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $24,903 | $0 | $24,903 | Green | Green | Inactive | roussan.francois@fultoncountyga.gov | 2019 | 2023-03-02 13:51:06
CSF- 159 | RS 349 | Kings Ridge | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The road (Kings Crest Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | May, 2019 |  |  | Sales Tax | $38,312 | $327,732 | $-289,420 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 19:45:38
CSF- 16 | RS 373 | Pointe Verda | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Case Domain Court, Lynfield Court, Lynfield Drive, and Pontevedra Place) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $109,188 | $384,653 | $-275,465 | Green | Green | Active | roussan.francois@fultoncountyga.gov |  | 2023-03-02 14:08:47
CSF- 160 | RS 350 | Lake Feldwood | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Pebble Beach Court, Pebble Beach Drive, Tate Road, and Vernier Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | November, 2018 |  |  |  |  | Sales Tax | $132,175 | $177,660 | $-45,485 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 19:45:54
CSF- 161 | RS 351 | Lake Royale | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Kings Place, Lake Royale Drive, Lake Royale Place, Marla Circle, Queens Court, Royal Lane, Royale Court, Royale Lane, and Sylvia Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | June, 2021 |  |  | Sales Tax | $304,578 | $164,673 | $139,905 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:51:32
CSF- 162 | RS 352 | Lattimore Park | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The road (Buffington Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $53,636 | $174,195 | $-120,559 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 19:47:08
CSF- 163 | RS 353 | Marion Woods Estates | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Cascade Overlook, Ellen Place, and Louise Terrace) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $65,130 | $81,957 | $-16,827 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:52:01
CSF- 164 | RS 354 | Melanie Manor | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The road (Melanie Way) wihin the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | November, 2019 |  |  | Sales Tax | $19,156 | $190,980 | $-171,824 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 19:48:28
CSF- 165 | RS 355 | Melanie Woods | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Hodge Drive and Melanie Woods Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $26,818 | $104,604 | $-77,786 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 19:49:01
CSF- 166 | RS 356 | Milam Manor | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Autumn Green Drive, Bradley Court, and Garvey Drive II) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | August, 2021 |  |  | Sales Tax | $105,357 | $70,629 | $34,728 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-02 14:19:37
CSF- 167 | RS 357 | Milam Park | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Planning | The roads (Milam Loop and Milam Way) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | November, 2019 |  |  | Sales Tax | $128,344 | $0 | $128,344 | Green | Green | Inactive | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 19:50:53
CSF- 168 | RS 358 | Mitchell Crossing | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The road (Mitchell Crossing Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | November, 2019 |  |  | Sales Tax | $36,396 | $30,064 | $6,332 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 19:51:34
CSF- 169 | RS 359 | Montclair Estates | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Bellecour Court, Bordeaux Court, Collines Avenue, Collines Court, Colonade Avenue, Esprit Court, Lyon Avenue, Lyon Court, Montague Avenue, and Montcalm Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $348,636 | $278,761 | $69,875 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:52:46
CSF- 17 | RS 374 | Pointer Ridge | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Ashdale Drive, Basswood Court, Buckhurst Drive, Buckhurst Trail, Buckhurst Way, Cedar Hurst Court, Cedar Hurst Trail, Cedar Hurst Way, Connell Road, Foxlair Drive, Foxlair Trail, Hidden Brook Court, Hidden Brook Trail, Hurst Point, Leisure Court, Leisure Lane, Leisure Trail, Medway Court, Pointer Court, Rockfort Court, Rockfort Drive, and Woodford Road) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | July, 2020 |  |  | Sales Tax | $1,879,188 | $1,364,734 | $514,454 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 20:02:29
CSF- 170 | RS 360 | Monterey | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Barcelona Court, Cadera Court, Carriage Court ll, Cocina Court, Crestwood Circle, Lantern Lane I, Old Carriage Drive II, and Old Spanish Trail) within the subdivsion to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | July, 2019 |  |  | Sales Tax | $346,721 | $271,513 | $75,208 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 19:52:59
CSF- 171 | RS 361 | Morning Creek Estates | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Clearwater Drive, Creekview Circle, Hovey Court, Morning Creek Circle, Morning Creek Court, Rill Court, Springside Lane, and Traverse Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | November, 2019 |  |  | Sales Tax | $409,935 | $379,484 | $30,451 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 19:53:21
CSF- 172 | RS 362 | Morning Creek | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Hemperly Road, Le Jean Drive, and Morning Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | May, 2021 |  |  | Sales Tax | $86,201 | $143,152 | $-56,951 | Green | Green | Active | roussan.francois@fultoncountyga.gov |  | 2023-03-02 14:20:07
CSF- 173 | RS 363 | Muirwoods | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Shandra Way, Avenue of Redwoods, Burls Court, Russian River, and Vallejo Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | June, 2020 |  |  | Sales Tax | $308,409 | $184,040 | $124,369 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 19:53:54
CSF- 174 | RS 364 | Nassau Village | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Lakes Trace and Twin Lakes Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | August, 2021 |  |  | Sales Tax | $57,468 | $64,112 | $-6,644 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 13:53:12
CSF- 175 | RS 365 | Normandy | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Brittany Trail, Louis XIV Lane, Orly Terrace, Rochelle Way, St. Lo Lane, and The Savoy) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $356,299 | $460,747 | $-104,448 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 14:07:20
CSF- 176 | RS 366 | Oak Ridge | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Loverwood Court and Whirlwind) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | May, 2019 |  |  | Sales Tax | $44,058 | $19,148 | $24,910 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 19:55:43
CSF- 177 | UFC-131 | Quick Response Projects | Tier 1 | Quick Response | TSPLOST | City of South Fulton | Planning | Quick Response Projects in Unincorporated Fulton | [7 empty] | Sales Tax | $1,648,045 | $0 | $1,648,045 | Gray | Gray | Active | roussan.francois@fultoncountyga.gov
CSF- 178 | UFC-209 | Operations and Safety | Tier 2 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | Operations and Safety Improvements in Unincorporated Fulton, Flat Shoals Road ATMS | [7 empty] | Sales Tax | $1,000,000 | $0 | $1,000,000 | Gray | Gray | Active | roussan.francois@fultoncountyga.gov
CSF- 179 | UFC-303 | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 3 | Pedestrian and Bike Improvements | TSPLOST | City of South Fulton | Planning | Pedestrian / Bike Improvements in Unincorporated Fulton, Stonewall Tell Sidewalks | [7 empty] | Sales Tax | $2,995,641 | $0 | $2,995,641 | Gray | Gray | Active | roussan.francois@fultoncountyga.gov
CSF- 18 | RS 375 | Ponderosa Pines | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | Bluebonnet Circle, Bluebonnet Court, Bluebonnet Trail and Devilla Court within the subdivision will be resurfaced. The work will include all the necessary preparation work which may include full depth of pavement patching, removal of the top asphalt layer (milling), and a surface treatment prior to final topping. The road will then be resurfaced with a uniform layer of asphalt in manner so as to provide uniformity of depth and a smooth transition to existing. After resurfacing, all existing pavement markings such as line striping, crosswalks etc. will be reinstalled. |  | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $97,695 | $81,583 | $16,112 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 20:02:51
CSF- 180 | UFC-304 | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 3 | Pedestrian and Bike Improvements | TSPLOST | City of South Fulton | Planning | Pedestrian / Bike Improvements in Unincorporated Fulton, Creel Road Sidewalks | [7 empty] | Sales Tax | $1,995,643 | $0 | $1,995,643 | Gray | Gray | Active | roussan.francois@fultoncountyga.gov
CSF- 181 | UFC-305 | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 3 | Pedestrian and Bike Improvements | TSPLOST | City of South Fulton | Planning | Pedestrian / Bike Improvements in Unincorporated Fulton, Bethsaida Road Bike/Sidewalks | [7 empty] | Sales Tax | $1,995,643 | $0 | $1,995,643 | Gray | Gray | Active | roussan.francois@fultoncountyga.gov
CSF- 182 | UFC-306 | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 3 | Pedestrian and Bike Improvements | TSPLOST | City of South Fulton | Planning | Pedestrian / Bike Improvements in Unincorporated Fulton - Welcome All Road Sidewalks | [7 empty] | Sales Tax | $2,995,643 | $0 | $2,995,643 | Gray | Gray | Active | roussan.francois@fultoncountyga.gov
CSF- 183 | UFC-307 | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 3 | Pedestrian and Bike Improvements | TSPLOST | City of South Fulton | Planning | Pedestrian / Bike Improvements in Unincorporated Fulton, Cascade Road Sidewalks | [7 empty] | Sales Tax | $2,995,643 | $0 | $2,995,643 | Gray | Gray | Active | roussan.francois@fultoncountyga.gov
CSF- 184 |  | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | City of South Fulton | Planning | Pedestrian / Bike Improvements in Unincorporated Fulton, Danforth Road (Rehoboth Circle to Cascade Road) | [7 empty] | Sales Tax | $2,300,000 | $0 | $2,300,000 | Gray | Gray | Active | roussan.francois@fultoncountyga.gov
CSF- 185 |  | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | City of South Fulton | Planning | Pedestrian / Bike Improvements in Unincorporated Fulton - Welcome All Road Sidewalks | [7 empty] | Sales Tax | $3,000,000 | $0 | $3,000,000 | Gray | Gray | Active | roussan.francois@fultoncountyga.gov
CSF- 186 |  | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | City of South Fulton | Planning | Pedestrian / Bike Improvements in Unincorporated Fulton. Bethsaida Road Bike/Sidewalks | [7 empty] | Sales Tax | $2,000,000 | $0 | $2,000,000 | Gray | Gray | Active | roussan.francois@fultoncountyga.gov
CSF- 187 |  | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | City of South Fulton | Planning | Pedestrian / Bike Improvements in Unincorporated Fulton, Creel Road Sidewalks | [7 empty] | Sales Tax | $2,000,000 | $0 | $2,000,000 | Gray | Gray | Active | roussan.francois@fultoncountyga.gov
CSF- 188 |  | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | City of South Fulton | Planning | Pedestrian / Bike Improvements in Unincorporated Fulton, Stonewall Tell Sidewalks | [7 empty] | Sales Tax | $3,000,000 | $0 | $3,000,000 | Gray | Gray | Active | roussan.francois@fultoncountyga.gov
CSF- 189 |  | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | City of South Fulton | Planning | Pedestrian / Bike Improvements in Unincorporated Fulton, Enon Road (Lynarbor Lane to Sanford J. Jones) | [7 empty] | Sales Tax | $2,000,000 | $0 | $2,000,000 | Gray | Gray | Active | roussan.francois@fultoncountyga.gov
CSF- 19 | RS 376 | Ponderosa | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Devilla Trace, El Caudillo Court, El Monte Court, Grande Court, Mesa Verde Drive, Ponderosa Court, Redona Drive, San Mario Court, San Remo Court, and Tahoe Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | June, 2018 |  |  | Sales Tax | $325,649 | $221,685 | $103,964 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 20:03:18
CSF- 190 |  | Pedestrian/Bike/Lanscape/Streetscape Projects | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | City of South Fulton | Planning | Pedestrian / Bike Improvements in Unincorporated Fulton, Cascade Road Sidewalks | [7 empty] | Sales Tax | $3,000,000 | $0 | $3,000,000 | Gray | Gray | Active | roussan.francois@fultoncountyga.gov
CSF- 191 |  | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | Operations and Safety Improvements in Unincorporated Fulton, Flat Shoals Road ATMS | [7 empty] | Sales Tax | $100,000 | $0 | $100,000 | Gray | Gray | Active | roussan.francois@fultoncountyga.gov
CSF- 192 |  | Pedestrian/Bike/Landscape/ Streetscape Projects | Tier 2 | Pedestrian and Bike Improvements | TSPLOST | City of South Fulton | Planning | Pedestrian/Bicycle in City of College Park - South Fulton Parkway (Buffington Road to Welcome All Road) | [7 empty] | Sales Tax | $425,248 | $0 | $425,248 | Gray | Gray | Active | roussan.francois@fultoncountyga.gov
CSF- 193 | QRP 1100 | Derrick Road, Jones Rd to Union City limits | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The Derrick Road, Jones Rd to Union City limits to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | [5 empty] | Sales Tax | $169,219 | $169,219 | $0 | Green |  | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-10-12 19:50:35
CSF- 194 |  | Derrick Road | Tier 1 | Quick Response | TSPLOST | City of South Fulton | Completed | Derrick Road to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  |  |  | March, 2019 | August, 2019 |  |  | Sales Tax | $0 | $169,219 | $-169,219 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 17:02:54
CSF- 195 |  | Hunter Rd | Tier 1 | Quick Response | TSPLOST | City of South Fulton | Completed | Hunter Rd to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  |  |  |  | August, 2019 |  |  | Sales Tax | $433,648 | $433,648 | $0 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-02-27 01:09:52
CSF- 196 |  | Striping | Tier 1 | Quick Response | TSPLOST | City of South Fulton | Completed | Striping- FY 2019 Overall Projects |  |  |  | March, 2019 | August, 2019 |  |  | Sales Tax | $0 | $180,581 | $-180,581 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 17:03:43
CSF- 197 |  | Cascade Rd over Utoy- CEI Services | Tier 1 | Project Management | TSPLOST | City of South Fulton | Construction | PM/CM |  |  |  |  | April, 2021 |  |  | Sales Tax | $101,744 | $101,744 | $0 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 23:20:38
CSF- 198 |  | TSPLOST CEI Services | Tier 1 | Project Management | TSPLOST | City of South Fulton | Design | PM Services |  |  |  |  | December, 2020 |  |  | Sales Tax | $323,616 | $323,616 | $0 |  |  | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-02-27 01:15:54
CSF- 199 |  | TSPLOST CEI Services- 2021 | Tier 1 | Project Management | TSPLOST | City of South Fulton | Design | PM |  |  |  |  | December, 2021 |  |  | Sales Tax | $321,725 | $321,725 | $0 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2021-02-27 01:18:26
CSF- 2 | RC 101 | Butner Road (Campbellton Fairburn Rd to City of Atlanta Limits) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The Butner Road (Campbellton Fairburn Rd to City of Atlanta Limits) to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable | May, 2020 | October, 2021 |  |  | Sales Tax | $2,579,872 | $1,287,708 | $1,292,164 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2022-09-22 13:18:26
CSF- 20 | RC 110 | Welcome All Road (Roosevelt Hwy to South Meadow Pkwy) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The Welcome All Road (Roosevelt Hwy to South Meadow Pkwy) to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable | March, 2020 | August, 2020 |  |  | Sales Tax | $507,504 | $506,377 | $1,127 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2021-05-03 16:18:27
CSF- 200 |  | Butner Rd at Stonewall Tell CEI Services | Tier 1 | Project Management | TSPLOST | City of South Fulton | Construction | Construction Management |  |  |  |  | April, 2022 |  |  | Sales Tax | $286,513 | $286,513 | $0 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2021-02-27 01:20:12
CSF- 201 |  | Autumn Lakes | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | Resurfacing |  |  |  |  | August, 2020 |  |  | Sales Tax | $0 | $57,431 | $-57,431 |  |  | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 23:14:58
CSF- 202 |  | Waverly Park | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | Subdivision resurfacing |  |  |  |  | August, 2020 |  |  | Sales Tax | $0 | $224,546 | $-224,546 |  |  | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 23:16:25
CSF- 203 | QRP 1101 | Striping | Tier 1 | Quick Response | TSPLOST | City of South Fulton | Completed | Striping of corridors (Bethsaida Rd, Cascade Rd, Enon Rd, Rivertown Rd, and Derrick Rd) | ER Snell |  |  |  | November, 2018 |  |  | Sales Tax | $153,927 | $404,501 | $-250,574 |  |  | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-10-12 19:51:45
CSF- 204 | QRP 1102 | Hunter Rd | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | Road Resurfacing- Hunter Rd | CW Matthews |  |  |  | August, 2019 |  |  | Sales Tax | $323,146 | $433,648 | $-110,502 |  |  | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-10-12 19:57:45
CSF- 205 | QRP 1103 | Striping | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | Striping of Corridors | CW Matthews |  | August, 2019 |  |  |  |  | Sales Tax | $0 | $180,581 | $-180,581 |  |  | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-10-12 20:00:40
CSF- 206 | QRP 1104 | Wolf Creek Subdivision | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | Subdivision Resurfacing | CW Matthews |  |  |  | May, 2021 |  |  | Sales Tax | $323,146 | $45,935 | $277,211 |  |  | Active | roussan.francois@fultoncountyga.gov | 2020 | 2021-10-12 20:01:52
CSF- 207 | QRP 1105 | Brown Drive South Subdivision | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | Subdivision Resurfacing | CW Matthews |  |  |  | June, 2021 |  |  | Sales Tax | $141,318 | $141,318 | $0 |  |  | Active | roussan.francois@fultoncountyga.gov | 2021 | 2021-10-12 20:04:05
CSF- 208 | QRP 1106 | Mallory Walk Subdivision | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | Subdivision Resurfacing | CW Matthews |  |  |  | June, 2021 |  |  | Sales Tax | $114,142 | $114,142 | $0 |  |  | Active | roussan.francois@fultoncountyga.gov | 2021 | 2021-10-12 20:06:18
CSF- 209 | QRP 11056 | Old Jonesboro Landing | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | Subdivision Resurfacing | CW Matthews |  | June, 2021 |  |  |  |  | Sales Tax | $176,348 | $176,348 | $0 |  |  | Active | roussan.francois@fultoncountyga.gov | 2021 | 2021-10-12 20:07:24
CSF- 21 | RS 377 | Pontevedra | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Planning | The road (Tortosa Place) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $385,033 | $0 | $385,033 | Green | Green | Inactive | roussan.francois@fultoncountyga.gov |  | 2021-05-03 20:05:05
CSF- 210 | QRP 1108 | Jennah Village | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | Subdivision Resurfacing | CW Matthews |  | June, 2021 |  |  |  |  | Sales Tax | $113,673 | $113,673 | $0 |  |  | Active | roussan.francois@fultoncountyga.gov | 2021 | 2021-10-12 20:08:34
CSF- 211 | PMCM 1200 | T278 CEI Services | Tier 1 | Project Management | TSPLOST | City of South Fulton | Completed | PM/CM- CEI Services | JACOBS |  |  |  | July, 2021 |  |  | Sales Tax | $101,744 | $101,744 | $0 |  |  | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-10-12 20:11:33
CSF- 212 | PMCM 1201 | TSPLOST | Tier 1 | Project Management | TSPLOST | City of South Fulton | Design | PM/CM- CEI Services |  | ATLAS | [5 empty] | Sales Tax | $323,616 | $323,616 | $0 |  |  | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-10-12 20:14:14
CSF- 213 | PMCM 1202 | 2021 PM SERVICES | Tier 1 | Project Management | TSPLOST | City of South Fulton | Design | PM/CM |  | ATLAS | [5 empty] | Sales Tax | $321,725 | $321,725 | $0 |  |  | Active | roussan.francois@fultoncountyga.gov | 2020 | 2021-10-12 20:15:58
CSF- 214 | PMCM 1203 | T242 CEI SERVICES | Tier 1 | Project Management | TSPLOST | City of South Fulton | Construction | CEI SERVICES | [7 empty] | Sales Tax | $286,513 | $286,513 | $0 |  |  | Active | roussan.francois@fultoncountyga.gov | 2020 | 2021-10-12 20:17:21
CSF- 215 |  | Resurfacing of Corridors | Tier 2 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax | $0 | $0 | $0 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov |  | 2023-03-02 15:17:45 | Georgia | City of South Fulton | 2022-03-31
CSF- 216 | RC 113 | Albania Drive | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Jonesboro Road to Bethsaida Drive |  |  | Not Applicable | April, 2024 | August, 2024 | August, 2024 |  | Sales Tax | $90,000 | $0 | $90,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-02-27 21:08:15 | Georgia | Albania Drive | 2022-03-31
CSF- 217 | RC 116 | Bishop Rd | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Herndon Road to Rivertown Road |  |  | Not Applicable | April, 2024 | August, 2024 | August, 2024 |  | Sales Tax | $370,000 | $0 | $370,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-02-27 22:00:46 | Georgia | Bishop Rd | 2022-03-31
CSF- 218 | RC 114 | Bakers Ferry Rd SW | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Boat Rock Road to Fulton Industrial Boulevard |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $163,000 | $0 | $163,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-27 21:35:17 | Georgia | Bakers Ferry Rd SW | 2022-03-31
CSF- 219 | RC 120 | Derrick Road | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and stripe South Fulton Parkway to Koweta Road |  |  | Not Applicable | April, 2024 | August, 2024 | August, 2024 |  | Sales Tax | $390,000 | $0 | $390,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-02-28 22:03:36 | Georgia | Derrick Road | 2022-03-31
CSF- 22 | RS 378 | Promenade | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Birchberry Court, Birchberry Terrace, Birchmere Close, Bramante Circle, Claudel Court, Promenade Drive, and Promenade Way) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $302,662 | $422,376 | $-119,714 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-02 14:17:01
CSF- 220 | RC 119 | Delano Road | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and stripe Roosevelt Highway to end |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $520,000 | $0 | $520,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-28 22:01:46 | Georgia | Delano Road | 2022-03-31
CSF- 221 | RC 117 | Boat Rock Rd SW | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Campbellton Road to Fulton Industrial Boulevard |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $470,000 | $0 | $470,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-27 22:02:37 | Georgia | Boat Rock Rd SW | 2022-03-31
CSF- 222 | RC 118 | Colonist Drive | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling and resurface Line Creek Rd to Mcclure Lake Rd |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $93,000 | $0 | $93,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-28 21:25:14 | Georgia | Colonist Drive | 2022-03-31
CSF- 223 | RC 124 | Feldwood Pl | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and stripe Feldwood Road to end |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $60,000 | $0 | $60,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-27 20:31:39 | Georgia | Feldwood Pl | 2022-03-31
CSF- 224 | RC 126 | Graham Dr | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repairs, milling, resurface and striping Oakley Industrial Boulevard to City Limits |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $198,000 | $0 | $198,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-27 20:31:22 | Georgia | Graham Dr | 2022-03-31
CSF- 225 | RC 125 | Garrison Drive | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and stripe Austin Road to end |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $56,000 | $0 | $56,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-28 22:06:37 | Georgia | Garrison Drive | 2022-03-31
CSF- 226 | RC 121 | Dodd Road | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and stripe Old National Highway to Camp Valley Road |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $42,000 | $0 | $42,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-28 22:05:07 | Georgia | Dodd Road | 2022-03-31
CSF- 227 | RC 127 | Gullatt Road | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Planning | Deep base repair, milling, resurface and striping McLarin (RR) to City Limits Project to be constructed by the City of Fairburn through an IGA (intergovernmental agreement) | [7 empty] | Sales Tax | $258,000 | $0 | $258,000 | Green |  | Active | jeff.mueller@cityofsouthfultonga.gov |  | 2023-02-27 20:35:19 | Georgia | Gullatt Road | 2022-03-31
CSF- 228 | RC 128 | Gwendoline Drive | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping End to end |  |  | Not Applicable | April, 2024 | August, 2024 | August, 2024 |  | Sales Tax | $97,000 | $0 | $97,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-02-27 20:37:09 | Georgia | Gwendoline Drive | 2022-03-31
CSF- 229 | RC 133 | Hobgood Rd | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repairs, milling, resurface and striping Roosevelt Highway to Rivertown Road |  |  | Not Applicable | April, 2024 | August, 2024 | August, 2024 |  | Sales Tax | $483,000 | $0 | $483,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-02-27 20:41:44 | Georgia | Hobgood Rd | 2022-03-31
CSF- 23 | RS 379 | Providence Glen | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Addison Park, Catlyn Court, Dalton Park, and Madeline) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | March, 2020 |  |  | Sales Tax | $61,299 | $61,299 | $0 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 20:11:56
CSF- 230 | RC 135 | Jones Road | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repairs, milling, resurface and striping Campbellton - Fairburn Road to Stonewall Tell Road |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $477,000 | $0 | $477,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-27 20:41:04 | Georgia | Jones Road | 2022-03-31
CSF- 231 | RC 137 | Koweta Trl | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Koweta Road to end |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $46,000 | $0 | $46,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-27 20:44:43 | Georgia | Koweta Trl | 2022-03-31
CSF- 232 | RC 139 | Mason Road | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Design | Deep base repair, milling, resurface and striping Roosevelt Highway to City Limits |  |  | Not Applicable | April, 2024 | August, 2024 | August, 2024 |  | Sales Tax | $230,000 | $0 | $230,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-02-27 21:06:50 | Georgia | Mason Road | 2022-03-31
CSF- 233 | RC 140 | Mcclure Lake Road | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Campbellton - Fairburn Road to end |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $52,000 | $0 | $52,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-27 21:10:34 | Georgia | Mcclure Road | 2022-03-31
CSF- 234 | RC 138 | Line Creek | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Campbellton - Fairburn Road to end |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $55,000 | $0 | $55,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-27 20:46:46 | Georgia | Line Creek | 2022-03-31
CSF- 235 | RC 141 | Milam Rd | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping City Limits to Fayette County Line |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $88,000 | $0 | $88,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-27 21:12:09 | Georgia | Milam Rd | 2022-03-31
CSF- 236 | RC 142 | Miles Rd | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Enon Road to Union Road |  |  | Not Applicable | April, 2024 | August, 2024 | August, 2024 |  | Sales Tax | $157,000 | $0 | $157,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-02-27 21:13:33 | Georgia | Miles Rd | 2022-03-31
CSF- 237 | RC 144 | Old Fairburn Road | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Buffington Road to Gwendoline Drive |  |  | Not Applicable | April, 2024 | August, 2024 | August, 2024 |  | Sales Tax | $58,000 | $0 | $58,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-02-27 21:18:04 | Georgia | Old Fairburn Road | 2022-03-31
CSF- 238 | RC 143 | Old Campbellton Rd SW | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Campbellton Road to Rocky Head Road |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $145,000 | $0 | $145,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-27 21:15:18 | Georgia | Old Campbellton Rd SW | 2022-03-31
CSF- 239 | RC 145 | Ono Rd | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Wilkerson Mill Road to Hobgood Road |  |  | Not Applicable | April, 2024 | August, 2024 | August, 2024 |  | Sales Tax | $418,000 | $0 | $418,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-02-27 21:19:46 | Georgia | Ono Rd | 2022-03-31
CSF- 24 | RS 380 | Putter's Village | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Birdie Lane and Wedge Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $40,227 | $24,390 | $15,837 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-02 14:17:39
CSF- 240 | RC 146 | Pittman Rd | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Stonewall Tell Road to Butner Road |  |  | Not Applicable | April, 2024 | August, 2024 | August, 2024 |  | Sales Tax | $345,000 | $0 | $345,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-02-27 21:21:49 | Georgia | Pittman Rd | 2022-03-31
CSF- 241 | RC 147 | Research Drive | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Cascade Road to Atlanta city limits |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $250,000 | $0 | $250,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-27 21:24:23 | Georgia | Research Drive | 2022-03-31
CSF- 242 | RC 148 | Short Rd | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Cedar Grove Road to South Fulton Parkway; Harbor Grove Road to Rivertown Road |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $372,000 | $0 | $372,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-27 21:30:48 | Georgia | Short Rd | 2022-03-31
CSF- 243 | RC 149 | Stacks Rd | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Design | Full Depth Pavement Reclamation and Drainage Repair Feldwood Road to 1,000 feet West of Mallory Road |  | Atlas | April, 2023 | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $306,000 | $0 | $306,000 |  | Green | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-27 21:33:32 | Georgia | Stacks Rd | 2022-03-31
CSF- 244 | RC 150 | Union Road | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Butner Road to Stonewall Tell Road |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $442,000 | $0 | $442,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-27 21:40:32 | Georgia | Union Road | 2022-03-31
CSF- 245 | RC 151 | Vandiver Road | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Union Road to Enon Road |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $117,000 | $0 | $117,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-27 21:41:57 | Georgia | Vandiver Road | 2022-03-31
CSF- 246 | RC 152 | Village Dr SW | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Fairburn Road to end |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $83,000 | $0 | $83,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-27 21:43:22 | Georgia | Village Dr SW | 2022-03-31
CSF- 247 | RC 154 | Westlake Parkway SW | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Camp Creek Parkway to end |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $820,000 | $0 | $820,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-27 21:45:23 | Georgia | Westlake PKWY SW | 2022-03-31
CSF- 248 | RC 155 | White City Rd | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Roosevelt Highway to city limits |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $156,000 | $0 | $156,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-27 21:46:52 | Georgia | White City Rd | 2022-03-31
CSF- 249 | RC 158 | Will Lee Road | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping Ben Hill Road to Welcome All Road |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $225,000 | $0 | $225,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-27 21:59:00 | Georgia | Will Lee Road | 2022-03-31
CSF- 25 | RS 381 | Ravenswood Drive | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The road (Ravenswood Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | July, 2021 |  |  | Sales Tax | $36,396 | $36,396 | $0 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 14:05:58
CSF- 250 | T 284 | White Mill Rd | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Construction | Pavement Reclamation | Atlanta Paving and Concrete Construction, Inc. | Atlas | August, 2022 | March, 2023 | April, 2023 | April, 2023 |  | Sales Tax | $1,650,000 | $18,120 | $1,631,880 | Yellow | Green | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-27 21:52:51 | Georgia | White Mill Rd | 2022-03-31
CSF- 251 | RC 157 | Wilkerson Mill Rd | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair, milling, resurface and striping within city limits - 2 segments |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $200,000 | $0 | $200,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-27 21:57:48 | Georgia | Wilkerson Mill Rd | 2022-03-31
CSF- 252 |  | Subdivision Resurfacing Toppings | Tier 2 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax | $0 | $0 | $0 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov |  | 2023-03-02 15:18:43 | Georgia | City of South Fulton | 2022-03-31
CSF- 253 | RST 218 | Oaks at Flat Shoals | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep Base Repair, Topping Layer Added Oak Bend Court Shoals Bend Court Shoals Oak Court |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $133,000 | $0 | $133,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-03-02 15:28:02 | Georgia | Oaks at Flat Shoals | 2022-03-31
CSF- 254 | RST 217 | Cedar Grove Village | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep Base Repair, Topping Layer Added Village Loop 1 Village Loop 2 Pikefarm Trail Splendida Court Ankara Court |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $204,000 | $0 | $204,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-03-02 15:26:17 | Georgia | Cedar Grove Village | 2022-03-31
CSF- 255 | RST 219 | Parkview Estates | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep Base Repair, Topping Layer Added Rosehall Place Millberry Road Thornbud Road Trimrose Court Bigsage Drive |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $324,000 | $0 | $324,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-03-02 15:30:01 | Georgia | Parkview Estates | 2022-03-31
CSF- 256 | RST 220 | Rose Crest | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep Base Repair, Topping Layer Added Rock Rose Lane |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $120,000 | $0 | $120,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-03-02 15:31:32 | Georgia | Rose Crest | 2022-03-31
CSF- 257 | RS 304 | Bentwood Village | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface East Village Court Haymarket Court West Village Court |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $104,000 | $0 | $104,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-03-02 16:01:06 | Georgia | Bentwood Village | 2022-03-31
CSF- 258 |  | Subdivisions Resurfacing | Tier 2 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax | $0 | $0 | $0 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov |  | 2023-03-02 15:32:02 | Georgia | City of South Fulton | 2022-03-31
CSF- 259 | RS 411 | Bethsaida Woods | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface East Village Court Haymarket Court West Village Court |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $104,000 | $0 | $104,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-03-02 19:14:22 | Georgia | Bethsaida Woods | 2022-03-31
CSF- 26 | RS 382 | Rebecca Lake | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Estate Lake Court, Estate lake drive, Rebecca Lake Way, and Rebecca LakeTrace) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | May, 2019 |  |  | Sales Tax | $59,383 | $95,431 | $-36,048 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 20:16:33
CSF- 260 | RS 412 | Cambridge Commons | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Abercorn Drive Belgrave Court Caxton Court Sheffield Court Draycott Court Epworth Court Amesbury Cove Kenton Court |  |  | Not Applicable | April, 2024 | August, 2024 | August, 2024 |  | Sales Tax | $484,000 | $0 | $484,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-03-02 19:02:56 | Georgia | Cambridge Commons | 2022-03-31
CSF- 261 | RS 413 | Cascade Glen | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Beechcrest Road Hickory Glen Lane Old Oak Court Chinkapin Circle |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $135,000 | $0 | $135,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-03-02 19:06:05 | Georgia | Cascade Glen | 2022-03-31
CSF- 262 | RS 415 | Cascade Manor | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Manor Hills Lane Majestic Oaks Way |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $99,000 | $0 | $99,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-03-02 19:08:28 | Georgia | Cascade Manor | 2022-03-31
CSF- 263 | RS 413 | Creekside | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Bigelow Court Stonecrop Drive Blazing Trail Creekside Cove Buckeye Place Chicory Cove Thistle Cove |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $320,000 | $0 | $320,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-03-02 19:12:07 | Georgia | Creekside | 2022-03-31
CSF- 264 | RS 418 | Heritage Park | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Creel Road from Old National Highway to Benidorm Court |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $112,000 | $0 | $112,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-28 20:06:27 | Georgia | Heritage Park | 2022-03-31
CSF- 265 | RS 417 | Fulton Industrial Area | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Design | Pavement Reclamation at 15 streets in FIB District |  | Atlas | April, 2023 | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $600,000 | $0 | $600,000 |  | Green | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-27 22:05:04 | Georgia | Fulton Industrial Area | 2022-03-31
CSF- 266 | RS 420 | Herron Creek | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Herron Drive Herron Trail Brooklake Herron Pass Herron Lane Herron Way Herron Way Herron Cove Herron Trace Herron Point Halcyon Drive Peacevalley Drive Peacevalley Court |  |  | Not Applicable | April, 2024 | August, 2024 | August, 2024 |  | Sales Tax | $663,000 | $0 | $663,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-02-28 20:11:41 | Georgia | Herron Creek | 2022-03-31
CSF- 267 | RS 419 | Herndon Woods | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Mahogany Drive Teak Lane |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $72,000 | $0 | $72,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-28 20:08:51 | Georgia | Herndon Woods | 2022-03-31
CSF- 268 | RS 422 | Jailette Estates | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Completed | Deep base repair as needed, milling and resurface Completed in 2021 under TSPLOST 1 -2020 | CW Mathews |  | Not Applicable | August, 2020 | April, 2021 | April, 2021 |  | Sales Tax | $125,000 | $125,000 | $0 | Green | Green | Inactive | jeff.mueller@cityofsouthfultonga.gov | 2021 | 2023-02-28 20:50:22 | Georgia | Jailette Estates | 2022-03-31
CSF- 269 | RS 421 | Highland Lake | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Highland Lake Drive Highland Lake Court Highland Hill Drive Highland Overlook Highland Lake View Highland Lake Trace |  |  | Not Applicable | April, 2024 | August, 2024 | August, 2024 |  | Sales Tax | $402,000 | $0 | $402,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-02-28 20:14:17 | Georgia | Highland Lake | 2022-03-31
CSF- 27 | RS 383 | Red Oak Woods | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The road (Marcus Nyah Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $42,143 | $35,366 | $6,777 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 20:17:16
CSF- 270 | RS 423 | Joshua Crossing | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Joshua Way |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $80,000 | $0 | $80,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-28 22:10:36 | Georgia | Joshua Crossing | 2022-03-31
CSF- 271 | RS 346 | Kimberly (units 3, 4a & 4b) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Adena Lane East and West Cainwood Drive Baxley Way Baxley Court West Forestside Court Forestside Court Cainwood Court East and West Woodburn Court Winkfield Place Winkfield Court Winkfield Point |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $400,000 | $0 | $400,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-28 21:16:11 | Georgia | Kimberly | 2022-03-31
CSF- 272 | RS 427 | Loch Lomond | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Loch Lomond Trail, New Hope Rd (north side) to End |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $67,000 | $0 | $67,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-28 21:27:50 | Georgia | Loch Lomond | 2022-03-31
CSF- 273 | RS 426 | Lakeside Manor | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Stonemeade Court |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $76,000 | $0 | $76,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-28 21:22:49 | Georgia | Lakeside Manor | 2022-03-31
CSF- 274 | RS 428 | Oakleaf Manor | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Oakleaf Pass Volion Parkway Battle Pass |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $163,000 | $0 | $163,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-28 21:37:34 | Georgia | Oakleaf Manor | 2022-03-31
CSF- 275 | RS 425 | Lakes and Village at Cedar Grove | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface The Lakes Drive |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $393,000 | $0 | $393,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-28 21:20:48 | Georgia | Lakes and Village at Cedar Grove | 2022-03-31
CSF- 276 | RS 429 | Parkside-Fulton County | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Willow Park Boulevard Willow Ash Drive Oak Park Terrace Oak Park Square Willow Park Trail |  |  | Not Applicable | April, 2024 | August, 2024 | August, 2024 |  | Sales Tax | $189,000 | $0 | $189,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-02-28 21:39:42 | Georgia | Parkside-Fulton County | 2022-03-31
CSF- 277 | RS 430 | Pittman Park | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Harrier Lane |  |  | Not Applicable | April, 2024 | August, 2024 | August, 2024 |  | Sales Tax | $86,000 | $0 | $86,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-02-28 21:41:12 | Georgia | Pittman Park | 2022-03-31
CSF- 278 | RS 432 | Shoals Creek | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Kayla Court Shoals Creek Drive |  |  | Not Applicable | August, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $136,000 | $0 | $136,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-02-28 21:51:00 | Georgia | Shoals Creek | 2022-03-31
CSF- 279 | RS 434 | Walden Park | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Baker Court Renaissance Circle Concord Loop Hayes Court Pickford Place Garland Circle Walden Boulevard Evergreen Trail Lawrence Place Tanner Way Holiday Lane |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $860,000 | $0 | $860,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-28 21:55:51 | Georgia | Walden Park | 2022-03-31
CSF- 28 | RS 384 | Robinson Woods Drive | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Old Bethsaida Way and Robinson Wood Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $68,961 | $92,695 | $-23,734 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 20:17:33
CSF- 280 | RS 431 | Retreat at Jones Mill | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Shamrock Drive |  |  | Not Applicable | April, 2024 | August, 2024 | August, 2024 |  | Sales Tax | $116,000 | $0 | $116,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-02-28 21:42:40 | Georgia | Retreat at Jones Mill | 2022-03-31
CSF- 281 | RS 433 | Three Lakes | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Three Lakes Drive Twin Lakes Drive Meadow Lake Road |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $114,000 | $0 | $114,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-28 21:53:39 | Georgia | Three Lakes | 2022-03-31
CSF- 282 | RS 435 | Wolf Creek Country (Excluding Current Toppings) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Wolf Club Drive Wolf Club Court Wolf Lake Court Wolf Den Lane Wolf Trail Wolf Lake Drive Wolf View Court |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $306,000 | $0 | $306,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-28 21:57:39 | Georgia | Wolf Creek Country | 2022-03-31
CSF- 283 | T 276 | Cochran Road over Deep Creek | Tier 1 | Bridges | TSPLOST2 | City of South Fulton | Land | The proposed project will replace the bridge carrying Cochran Road over Deep Creek. The project begins 280 ft. south of the existing bridge and ends 280 ft. north of the existing bridge. This project would replace the existing substandard bridge over Deep Creek with a new structure and new roadway approaches. The proposed mainline will consist of two 11Æ-0ö travel lane and curb and gutter in each direction. Sidewalks will be constructed in each direction for the full project length. A 2.0Æ buffer will be provided between the sidewalk and curb. |  | Long Engineering | December, 2022 | March, 2023 | February, 2024 |  |  | Sales Tax | $1,530,000 | $160,000 | $1,370,000 |  | Yellow | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-03-02 20:49:31 | Georgia | Cochran Road | 2022-03-31
CSF- 284 | RS 436 | Woodside Hills | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Woodside Drive Fern Valley Drive Fern Valley Court Green Hill Court Reynolds Road Red Berry Lane Zane Drive Faron Drive |  |  | Not Applicable | April, 2024 | August, 2024 | August, 2024 |  | Sales Tax | $337,000 | $0 | $337,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-02-28 21:59:44 | Georgia | Woodside Hills | 2022-03-31
CSF- 285 | B 505 | Derrick Rd over Deep Creek Tributary | Tier 1 | Bridges | TSPLOST2 | City of South Fulton | Planning | Bridge replacement to meet better rating capacity and alleviate congestion |  |  | March, 2025 | June, 2025 | March, 2026 | March, 2026 |  | Sales Tax | $2,280,000 | $0 | $2,280,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-03-02 20:52:16 | Georgia | Derrick Rd | 2022-03-31
CSF- 286 | T 270 | Demooney Road over Deep Creek | Tier 1 | Bridges | TSPLOST2 | City of South Fulton | Land | The project begins 1,000' southwest of the existing bridge and ends 980' northeast of the existing bridge. It will replace the existing substandard bridge with a new structure and new roadway approaches. The proposed typical section consists of 12' travel lanes with curb and gutter along with sidewalks in each direction within the project limits. |  | Long Engineering | April, 2023 | July, 2023 | December, 2024 | December, 2024 |  | Sales Tax | $3,090,000 | $260,000 | $2,830,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-03-02 20:48:47 | Georgia | Demooney Road | 2022-03-31
CSF- 287 | B 508 | Koweta Rd over Deep Creek | Tier 1 | Bridges | TSPLOST2 | City of South Fulton | Planning | Bridge replacement to meet better rating capacity |  |  | June, 2025 | June, 2026 | March, 2027 | March, 2027 |  | Sales Tax | $2,227,000 | $0 | $2,227,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2026 | 2023-03-02 21:00:49 | Georgia | Koweta Rd | 2022-03-31
CSF- 288 | T 271 | Fairburn Rd | Tier 1 | Bridges | TSPLOST2 | City of South Fulton | Bidding | The project is located on Fairburn Road, starting at Cascade Road and continuing to North Utoy Creek. The typical section includes 12' travel lanes, curb and gutter, a 10-foot multi-use path on the West side and a 6-foot wide sidewalk behind a 2-foot stamped concrete strip on the east side of Fairburn Road. Improvements also include bridge replacements at North and South Utoy Creek with bottomless culverts and turning lane improvements at the Fairburn Road/Cascade Road intersection. |  | Qk4 | November, 2022 | March, 2023 | September, 2024 | September, 2024 |  | Sales Tax | $3,372,000 | $37,000 | $3,335,000 |  | Yellow | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-03-02 20:58:17 | Georgia | Fairburn Rd | 2022-03-31
CSF- 289 | B 503 / T 288 | Stacks Rd over CSX RR | Tier 1 | Bridges | TSPLOST2 | City of South Fulton | Design | This project consists of replacement of bridge structure on Stacks Road over the CSX Railroad. |  | American Engineers, Inc. | December, 2023 | June, 2024 | December, 2024 | December, 2024 |  | Sales Tax | $2,712,000 | $48,000 | $2,664,000 |  | Green | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-03-02 21:04:01 | Georgia | Stacks Rd | 2022-03-31
CSF- 29 | RS 385 | Sable Chase S/D | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Carriage Chase Road, Devon Chase Road, Sable Chase Lane, Sable Glen Lane, Sable Glen Road, Sable Run Road, and Sable View Lane) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | July, 2021 |  |  | Sales Tax | $480,812 | $326,570 | $154,242 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2021-10-12 18:33:56
CSF- 290 | OSI 620 | Aldredge Road and Merk Road | Tier 1 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | Intersection improvements will include the addition of a circular roundabout to address congestion and reduce the severity of accidents at this intersection. Additional improvements include drainage, curb & gutter, streetlights, and 5' wide sidewalks. |  |  | November, 2025 | November, 2025 | March, 2027 | March, 2027 |  | Sales Tax | $1,550,000 | $0 | $1,550,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-03-02 19:22:10 | Georgia | Aldredge Road | 2022-03-31
CSF- 291 | OSI 622 | Bethlehem Rd and Cedar Grove Rd | Tier 1 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | The intersection is being analyzed for traffic improvements including a roundabout alternative. Additional improvements include curb & gutter, drainage, sidewalks, and streetlights. The proposed project will improve safety and relieve congestion. |  |  | September, 2026 | September, 2026 | December, 2027 | December, 2027 |  | Sales Tax | $1,110,000 | $0 | $1,110,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2026 | 2023-03-02 19:26:37 | Georgia | Bethlehem Rd | 2022-03-31
CSF- 292 | OSI 600 | Bethsaida Road and Creel / West Road | Tier 1 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | The intersection is being analyzed for traffic improvements including a roundabout alternative. Additional improvements include curb & gutter, drainage, sidewalks, and streetlights. The proposed project will improve safety and relieve congestion. |  |  | June, 2025 | September, 2025 | March, 2027 | March, 2027 |  | Sales Tax | $1,835,000 | $0 | $1,835,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov |  | 2023-03-02 19:30:27 | Georgia | Bethsaida Rd | 2022-03-31
CSF- 293 | OSI 623 | Butner Road and Aldredge Road | Tier 1 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | The intersection is being analyzed for traffic improvements including a roundabout alternative. Additional improvements include curb & gutter, drainage, sidewalks, and streetlights. The proposed project will improve safety and relieve congestion. |  |  | September, 2026 | September, 2026 | December, 2027 | December, 2027 |  | Sales Tax | $1,480,000 | $0 | $1,480,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2026 | 2023-03-02 19:33:03 | Georgia | Butner Road | 2022-03-31
CSF- 294 |  | Intersection Improvements | Tier 2 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax | $0 | $0 | $0 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov |  | 2023-03-02 19:19:03 | Georgia | City of South Fulton | 2022-03-31
CSF- 295 | OSI 628 | Old Fairburn Road and Thaxton Road | Tier 1 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | The intersection is being analyzed for traffic improvements including a roundabout alternative. Additional improvements include curb & gutter, drainage, sidewalks, and streetlights. The proposed project will improve safety and relieve congestion. |  |  | June, 2025 | June, 2025 | June, 2026 | June, 2026 |  | Sales Tax | $1,480,000 | $0 | $1,480,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2026 | 2023-03-02 19:36:03 | Georgia | Old Fairburn Road | 2022-03-31
CSF- 296 | OSI 629 | Ono Rd/Hobgood Rd and Rivertown Rd | Tier 1 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | The intersection is being analyzed for traffic improvements including a roundabout alternative. Additional improvements include curb & gutter, drainage, sidewalks, and streetlights. The proposed project will improve safety and relieve congestion. |  |  | September, 2024 | September, 2024 | December, 2025 | December, 2025 |  | Sales Tax | $2,238,000 | $0 | $2,238,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-03-02 19:38:55 | Georgia | Ono Rd/Hobgood Rd | 2022-03-31
CSF- 297 | OSI 801 | Cascade Road (New Hope to City of Atlanta) | Tier 1 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | Connected vehicles deployment phase 2: connected vehicle signal communication upgrades, including all signals on all roads, excluding those already upgraded or programmed for upgrade through CV1K initiative or through connected vehicles deployment phase 1 |  |  | October, 2026 | October, 2026 | June, 2027 | June, 2027 |  | Sales Tax | $2,450,000 | $0 | $2,450,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2027 | 2023-03-02 19:53:54 | Georgia | Cascade Road | 2022-03-31
CSF- 298 | P 902 | Bethsaida Road | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | City of South Fulton | Planning | Multi-Use Trail Old National Highway to Nunn Woods Way |  |  | October, 2024 | October, 2024 | October, 2025 | October, 2025 |  | Sales Tax | $3,600,000 | $0 | $3,600,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-03-02 21:21:48 | Georgia | Bethsaida Road | 2022-03-31
CSF- 299 |  | Intersection Control Evaluation (ICE) | Tier 3 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax | $0 | $0 | $0 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov |  | 2023-03-02 19:54:35 | Georgia | City of South Fulton | 2022-03-31
CSF- 3 | RC 102 | Cascade Road (Fulton Ind Blvd to Beechcrest Road SW) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The Cascade Road (Fulton Ind Blvd to Beechcrest Road SW) to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2018 |  |  | Sales Tax | $1,356,984 | $1,336,163 | $20,821 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 16:08:49
CSF- 30 | RS 386 | Sherbrook Forest | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Sherbrook Court and Sherbrook Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | July, 2021 |  |  | Sales Tax | $72,792 | $137,122 | $-64,330 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2021-10-12 19:02:15
CSF- 300 | T 271 | Fairburn Road | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | City of South Fulton | Planning | The project is located on Fairburn Road, starting at Cascade Road and continuing to North Utoy Creek. The typical section includes 12' travel lanes, curb and gutter, a 10-foot multi-use path on the West side and a 6-foot wide sidewalk behind a 2-foot stamped concrete strip on the east side of Fairburn Road. Improvements also include bridge replacements at North and South Utoy Creek with bottomless culverts and turning lane improvements at the Fairburn Road/Cascade Road intersection. Also included as part of CSF-349 |  | Qk4 | November, 2022 | March, 2023 | September, 2024 | September, 2024 |  | Sales Tax | $2,045,000 | $37,000 | $2,008,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-03-02 21:29:15 | Georgia | Fairburn Road | 2022-03-31
CSF- 301 | P 903 | Cascade Road | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | City of South Fulton | Planning | Multi-Use Trail City of Altanta Limits to Fulton Industrial Blvd |  |  | March, 2026 | March, 2026 | June, 2027 | June, 2027 |  | Sales Tax | $6,632,000 | $0 | $6,632,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2026 | 2023-03-02 21:24:02 | Georgia | Cascade Road | 2022-03-31
CSF- 302 | P 908 | Flat Shoals Road | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | City of South Fulton | Planning | Multi-Use Trail Old National Highway to Buffington Road |  |  | October, 2027 | October, 2027 | March, 2029 | March, 2029 |  | Sales Tax | $5,427,000 | $0 | $5,427,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2027 | 2023-03-02 21:33:31 | Georgia | Flat Shoals Road | 2022-03-31
CSF- 303 | P 910 | Jerome Road | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | City of South Fulton | Planning | Fill in sidewalk gaps within the existing sidewalk network. Old National Highway to Old Bill Cook Road |  |  | June, 2024 | June, 2024 | March, 2025 | March, 2025 |  | Sales Tax | $1,500,000 | $0 | $1,500,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-03-02 21:41:10 | Georgia | Jerome Road | 2022-03-31
CSF- 304 | P 914 | Union Road | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | City of South Fulton | Planning | Fill in sidewalk gaps within the existing sidewalk network. Campbellton Road to Vandiver Road |  |  | December, 2023 | December, 2024 | December, 2025 | December, 2025 |  | Sales Tax | $1,200,000 | $0 | $1,200,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-03-02 21:45:54 | Georgia | Union Road | 2022-03-31
CSF- 305 | P 911 | Merk Road | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | City of South Fulton | Planning | Multi-Use Trail Camp Creek Parkway to Aldredge Road |  |  | September, 2025 | September, 2025 | June, 2026 | June, 2026 |  | Sales Tax | $2,720,000 | $0 | $2,720,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2026 | 2023-03-02 21:43:07 | Georgia | Merk Road | 2022-03-31
CSF- 306 | P 909 | Fulton Industrial Area | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | City of South Fulton | Planning | Sidewalk Gaps Various Locations in Fulton Industrial Blvd District |  |  | April, 2024 | April, 2024 | November, 2024 | November, 2024 |  | Sales Tax | $1,000,000 | $0 | $1,000,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2024 | 2023-03-02 21:37:07 | Georgia | Fulton Industrial Area | 2022-03-31
CSF- 307 | P 906 | Welcome All Road | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | City of South Fulton | Planning | Multi-Use Trail Roosevelt Highway to Will Lee Road |  |  | August, 2024 | September, 2025 | September, 2026 | September, 2026 |  | Sales Tax | $2,940,000 | $0 | $2,940,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-03-02 21:50:01 | Georgia | Welcome All Road | 2022-03-31
CSF- 308 |  | Harris Rd | Tier 2 | Bridges | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Harris Rd | 2022-03-31
CSF- 309 |  | Bethsaida Road | Tier 2 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Bethsaida Road | 2022-03-31
CSF- 31 | RC 111 | Merk Road (Butner Rd to Union Rd) | Tier 2 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Construction | The Merk Road (Butner Rd to Union Rd) to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable |  | June, 2021 | November, 2021 |  |  | Sales Tax | $622,536 | $268,577 | $353,959 | Green | Gray | Active | roussan.francois@fultoncountyga.gov | 2021 | 2022-09-22 13:20:20
CSF- 310 |  | City Wide | Tier 1 | Quick Response Projects | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of South Fulton | 2022-03-31
CSF- 311 |  | Campbellton Road | Tier 2 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Campbellton Road | 2022-03-31
CSF- 312 |  | Cascade Palmetto Highway | Tier 2 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Cascade Palmetto Highway | 2022-03-31
CSF- 313 |  | Enon Road | Tier 2 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Enon Road | 2022-03-31
CSF- 314 |  | Intersection Improvements | Tier 2 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of South Fulton | 2022-03-31
CSF- 315 |  | Scarborough Road | Tier 2 | Pedestrian and Bike Improvements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Scarborough Road | 2022-03-31
CSF- 316 |  | South Fulton Parkway | Tier 2 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | South Fulton Parkway | 2022-03-31
CSF- 317 |  | Cascade Road | Tier 2 | Pedestrian and Bike Improvements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Cascade Road | 2022-03-31
CSF- 318 |  | Binford Road | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Binford Road | 2022-03-31
CSF- 319 |  | Easton Drive | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Easton Drive | 2022-03-31
CSF- 32 | RS 387 | Silverwood Estates | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Linden Garden and Silverdale Road) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $53,636 | $76,061 | $-22,425 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-02 14:21:22
CSF- 320 |  | City Wide | Tier 2 | Quick Response Projects | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of South Fulton | 2022-03-31
CSF- 321 |  | Elva Drive | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Elva Drive | 2022-03-31
CSF- 322 |  | Resurfacing of Corridors | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of South Fulton | 2022-03-31
CSF- 323 |  | Herndon Rd | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Herndon Rd | 2022-03-31
CSF- 324 |  | Hall Road | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Hall Road | 2022-03-31
CSF- 325 |  | Hillside Way | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Hillside Way | 2022-03-31
CSF- 326 |  | Hillside Road | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Hillside Road | 2022-03-31
CSF- 327 |  | Koweta Rd | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Koweta Rd | 2022-03-31
CSF- 328 |  | John Rivers Rd | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | John Rivers Rd | 2022-03-31
CSF- 329 |  | Washington Road | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Washington Road | 2022-03-31
CSF- 33 | RS 388 | Smoke Ridge | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Merry Wood Drive, Merry Wood Way, Merrywood Drive, Merrywood Way, Smoke Ridge Court, and Smoke Ridge Drive I) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | June, 2021 |  |  | Sales Tax | $250,942 | $235,268 | $15,674 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2021-10-12 18:35:00
CSF- 330 |  | Loch Lomond | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Loch Lomond | 2022-03-31
CSF- 331 |  | Subdivisions Resurfacing | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of South Fulton | 2022-03-31
CSF- 332 |  | Fulton Industrial Area | Tier 3 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Fulton Industrial Area | 2022-03-31
CSF- 333 |  | Creel Road | Tier 3 | Pedestrian and Bike Improvements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Creel Road | 2022-03-31
CSF- 334 |  | Intersection Improvements | Tier 3 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of South Fulton | 2022-03-31
CSF- 335 |  | Old Fairburn Road | Tier 3 | Pedestrian and Bike Improvements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Old Fairburn Road | 2022-03-31
CSF- 336 |  | Wallace Road | Tier 3 | Pedestrian and Bike Improvements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Wallace Road | 2022-03-31
CSF- 337 |  | City Wide | Tier 3 | Quick Response Projects | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of South Fulton | 2022-03-31
CSF- 338 | OSI 631 | Union / Thames | Tier 1 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | The intersection is being analyzed for traffic improvements including a roundabout alternative. Additional improvements include curb & gutter, drainage, sidewalks, and streetlights. The proposed project will improve safety and relieve congestion. |  |  | September, 2024 | September, 2024 | December, 2025 | December, 2025 |  | Sales Tax | $1,480,000 | $0 | $1,480,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-03-02 19:57:42 |  |  | 2022-05-13
CSF- 339 |  | Cascade Palmetto Hwy/Wilkerson Mill Rd | Tier 2 | Operation and Safety Improvements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax | $0 | $0 | $0 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov |  | 2023-03-02 19:50:56 | Georgia | Cascade Palmetto Hwy/Wilkerson Mill Rd | 2022-05-13
CSF- 34 | RS 389 | Southern Colony | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Construction | The road (Sulene Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $17,240 | $206,445 | $-189,205 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 14:10:00
CSF- 340 |  | Scarborough Rd (Brookwood Place to Welcome All Rd) | Tier 3 | Pedestrian and Bike Improvements | TSPLOST2 | City of South Fulton | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | GA | Scarborough Rd | 2022-06-08
CSF- 35 | RS 390 | Southern Pines Estates | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Greentree Lane and Greentree Trail) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $187,727 | $273,833 | $-86,106 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 20:20:53
CSF- 36 | RS 391 | Spring Valley | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Ethan Allen Court, Ethan Allen Drive, Green Mountain Trail, Spring Valley Boulevard, Spring Valley Circle, Spring Valley Pkwy, Spring Valley Trace, and Spring Valley Way) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $254,773 | $263,779 | $-9,006 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-02 14:22:13
CSF- 37 | RS 392 | Sunrise | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Dawn Drive II, Jeffery Drive, Morning Trail, Sun Rise Court, Sun Rise Trail, Sun Rise Trail II, Sun Rise Trail III, Sunrise Court, and Taver Terrace) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $206,883 | $191,581 | $15,302 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-02 14:22:41
CSF- 38 | RS 393 | Thaxton Pointe | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Glad Morning Court, Glad Morning Drive, Hawkins Crossing, and Lendy Lane) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $103,442 | $145,355 | $-41,913 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-02 14:23:10
CSF- 39 | RS 394 | Thaxton Reserve | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Quivas Court, Tiwanaku Drive, Umatilla Lane, and Wewatla Street) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | July, 2021 |  |  | Sales Tax | $344,805 | $259,988 | $84,817 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 14:10:26
CSF- 4 | RC 103 | Cedar Grove Road (Chattahoochee Hills City Limits to Rivertown Rd) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The Cedar Grove Road (Chattahoochee Hills City Limits to Rivertown Rd) to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | E R Snell | Not Applicable | Not Applicable | April, 2017 | April, 2017 | August, 2017 |  | Sales Tax | $1,114,748 | $1,179,801 | $-65,053 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 16:10:21
CSF- 40 | RS 395 | The Meadows | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Deerfield Court, Deerfield Lane, Deerfield Trail, Dunmoreland Terrace, Dunmorlenad Court, East Hampton Court, Jerome Road, Jolly Road, Long Meadow Lane, Northfield Boulevard, Northfield Court, Southwick Court, Springfield Court, Sturbridge Way, Swansea Court, The Meadows Way, Warfield Court, Westfield Trail, Westford Circle, Westford Court, Westhill Circle, and Weststead Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | August, 2019 |  |  | Sales Tax | $1,095,714 | $708,132 | $387,582 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 20:23:49
CSF- 41 | RS 396 | Thornton Woods | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Fox Hall Lane, Marlboro Circle, Thonbury Way, and Thornton Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | July, 2020 |  |  | Sales Tax | $189,643 | $199,825 | $-10,182 | Yellow | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 20:24:22
CSF- 42 | RC 112 | Jones Road (Campbellton Rd to Hall Rd) | Tier 2 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Planning | The Jones Road (Campbellton Rd to Hall Rd) to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $1,155,790 | $0 | $1,155,790 | Gray | Gray | Inactive | roussan.francois@fultoncountyga.gov |  | 2021-05-03 16:21:54
CSF- 43 | RS 397 | Tacoma Forest | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Cherokee Circle, Navaho Circle, Shoshonee Trail, Tocomc Trail, Towanda Circle, and Towanda Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2021 |  |  | Sales Tax | $235,617 | $297,559 | $-61,942 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 14:11:09
CSF- 44 | RS 398 | Versailles | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Marceau Way, Martinique Court, Monaco Run, and Saint Marteen Court) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $99,610 | $279,088 | $-179,478 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-02 14:11:38
CSF- 45 | RS 399 | Village Green | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (North Star Trail and Windhaven Trail) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | March, 2020 |  |  | Sales Tax | $76,623 | $78,900 | $-2,277 | Yellow | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 20:27:25
CSF- 46 | RS 401 | Wexwood Glen | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The road (Kerry Drive) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable |  | July, 2021 |  |  | Sales Tax | $40,227 | $284,054 | $-243,827 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2021-10-12 18:39:09
CSF- 47 | RS 402 | Will Lee Pines | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Fradon Court and Welcome All Terrace) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | November, 2018 |  |  | Sales Tax | $93,864 | $87,148 | $6,716 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 20:28:49
CSF- 48 | RS 403 | Wolf Creek Forest | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The road (Wolf Creek Circle) within the sbdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | November, 2019 |  |  | Sales Tax | $53,636 | $35,151 | $18,485 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 20:29:17
CSF- 49 | RS 404 | Woodland Estates | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Commonwood Place, Keels Lane, Smoke Ridge Drive II, Springtree Court, Squirrel Way, and Woody Path Lane) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | May, 2019 |  |  | Sales Tax | $210,714 | $129,044 | $81,670 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 20:29:35
CSF- 5 | RC 104 | Creel Road (Old National Hwy to West Rd) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The Creel Road (Old National Hwy to West Rd) to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable | March, 2019 | August, 2019 |  |  | Sales Tax | $295,100 | $283,472 | $11,628 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 16:11:47
CSF- 50 | RS 405 | Woodward Estates | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Amethist Court, Garnett Way, Mica Trace, Old Rocky Road, Rockway Road, Rocky Court, Topaz Trail, Turquoise Trail, and Woodward Road) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM | Not Applicable | Not Applicable |  | June, 2019 |  |  | Sales Tax | $469,318 | $294,440 | $174,878 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 20:29:52
CSF- 51 | B 500 | Butner Road over Camp Creek | Tier 1 | Bridges | TSPLOST | City of South Fulton | Design | The proposed Butner Road over Camp Creek includes improvements to the bridge that will extend to the Camp Creek Parkway edge of pavement on the south leg of the intersection. A new bridge is proposed to replace the existing near the Butner Road/Camp Creek Parkway intersection. The proposed bridge will be wide enough to accommodate two traffic lanes of 24-ft wide, 30'' curb and gutter and 12-ft wide pedestrian sidewalk on the west side to tie into a proposed multi-use trail off the bridge and 6-ft wide sidewalk on the east side. A turning lane will be designed off the bridge to finish free flow and stacking length up to the intersection with Camp Creek Parkway. |  | William-Russell & Johnson | December, 2022 | April, 2020 | September, 2024 |  |  | Sales Tax | $1,600,000 | $61,911 | $1,538,089 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2023-03-05 00:19:21
CSF- 52 | RST 200 | Camp Creek Village (SFR), (LL 73 Dist 14FF) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The primary work is to resurface the final asphalt topping layer. The roads (Zultana and zoya) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. Milling of the existing asphalt surface is not expected to be required for these roadways. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $44,140 | $49,491 | $-5,351 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 20:30:27
CSF- 53 | B 501 | Enon Road over Camp Creek Tributary (Timber Bridge) | Tier 1 | Bridges | TSPLOST | City of South Fulton | Design | The proposed project will replace the existing culvert located on Enon Road between Enon Mill Drive and Enon Pines Drive. The deteriorated timber culvert will be removed and replaced with a structure to carry two 12-foot travel lanes and 8-foot shoulders, which include 6-foot sidewalks. |  | AEI | February, 2022 | December, 2022 | February, 2024 |  |  | Sales Tax | $600,000 | $87,454 | $512,546 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-05 00:22:05
CSF- 54 | B 502 | Bethsaida over Morning Creek | Tier 2 | Bridges | TSPLOST | City of South Fulton | Planning | Bridge replacement to be analyzed for a better rating capacity and alleviate congestion. | [7 empty] | Sales Tax | $1,500,000 | $0 | $1,500,000 | Gray | Gray | Active | roussan.francois@fultoncountyga.gov |  | 2023-03-05 00:23:02
CSF- 55 | OSI 601 | Butner Road @ Camp Creek Parkway | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | The proposed Butner Road project is a capacity project that begins at the intersection of Camp Creek Parkway and extends approximately 1,000 feet to the north along Butner Road. It consists of widening the existing Butner Road by adding left and right-turn lanes, providing a nature trail at-grade crossing and updating the intersection signalization and guardrails, as a safety measure, on the east side of Butner Road to Merk Road. The travel lanes will be minimum 11 foot-wide with 2-foot stamped concrete and 12-foot trail on the east side. This project also includes signal upgrade and installation of new decorative mast arms. |  | American Engineers, Inc | December, 2022 | August, 2020 | January, 2025 |  |  | Sales Tax | $3,174,000 | $16,250 | $3,157,750 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2023-03-05 00:26:37
CSF- 56 | OSI 602 | Butner Road @ Union Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | Intersection improvements will include the use of an oval roundabout or circular roundabout. A traffic report concluded that a roundabout is the best alternative to handle the traffic congestion at this intersection. Additional improvements include drainage, curb & gutter, street lights, and sidewalks. |  | American Engineers, Inc | December, 2022 | December, 2019 | August, 2024 |  | https://performance.fultoncountyga.gov/stories/s/v555-6sca | Sales Tax | $1,986,000 | $241,500 | $1,744,500 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2023-03-05 00:28:01
CSF- 57 | OSI 603 | Butner Road @ Pittman Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | The proposed project will improve traffic safety by realigning the approach of PIttman Road to eliminate an extreme angle of incidence at the intersection. Additional improvements include curb & gutter, drainage, sidewalks, and streetlights |  | AEI | May, 2023 | December, 2020 | December, 2024 |  |  | Sales Tax | $1,412,000 | $73,234 | $1,338,766 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-05 00:30:11
CSF- 58 | OSI 604 | Campbellton Road @ Stonewall Tell Road (Project Design on Hold) | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Construction | Intersection will be analyzed for traffic improvements including a roundabout alternative. Curb & Gutter, drainage, sidewalks, and street lights will be part of the proposed improvements. The intersection improvements will provide geometric and congestion relief. | CMC, INC | American Engineers, Inc | December, 2022 | April, 2020 | March, 2024 |  |  | Sales Tax | $1,422,000 | $172,932 | $1,249,068 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2023-03-05 00:40:45
CSF- 59 | OSI 605 | Campbellton-Fairburn Road @ Jones Road (Project Design on Hold) | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | Geometric and capacity improvements to include traditional or roundabouts |  | American Engineers, Inc | August, 2018 |  | August, 2019 |  |  | Sales Tax | $1,464,000 | $0 | $1,464,000 | Green | Green | Active | roussan.francois@fultoncountyga.gov |  | 2021-05-03 22:55:24
CSF- 6 | RC 105 | Enon Road (Stonewall Tell Rd to Atlanta City limits) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The Enon Road (Stonewall Tell Rd to Atlanta City limits)to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable | March, 2019 | August, 2019 |  |  | Sales Tax | $921,496 | $752,801 | $168,695 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2018 | 2021-05-03 16:12:54
CSF- 60 | OSI 606 | Cascade-Palmetto Highway @ West Stubbs Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Completed | The project and plans reflect the installation of a new signal at the intersection of Cascade Palmetto Highway and West Stubbs Road. In addition, it includes the installation of curb & gutter, a solar powered advanced signal warning sign, ADA ramps, and signing & marking. The existing non-signalized intersection already includes the necessary turn lanes and right of way. |  | Not Applicable | Not Applicable | May, 2018 | November, 2018 |  |  | Sales Tax | $1,554,000 | $272,757 | $1,281,243 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 22:46:16
CSF- 61 | OSI 607 | Demooney Road @ West Stubbs Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | Intersection improvements will include the addition of a circular roundabout to address congestion and reduce the severity of accidents at this intersection. Additional improvements include drainage, curb & gutter, streetlights, and 5' wide sidewalks. |  | AEI | May, 2023 | December, 2020 | November, 2024 |  |  | Sales Tax | $1,422,000 | $108,809 | $1,313,191 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-05 00:38:41
CSF- 62 | OSI 608 | Enon Road @ Stonewall Tell Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | .Intersection will be analyzed for traffic improvements including a roundabout alternative. Curb & Gutter, drainage, sidewalks, and street lights will be part of the proposed improvements. The intersection improvements will provide geometric and congestion relief. |  | AEI | May, 2023 | December, 2020 | October, 2024 |  |  | Sales Tax | $1,674,000 | $104,310 | $1,569,690 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-05 00:40:33
CSF- 63 | RST 201 | Chestnut Ridge @ Cedar Grove | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Appaloose Cove and Sorrel Drive) within the subdivision is to resurface the final asphalt topping layer. The roads within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. Milling of the existing asphalt surface is not expected to be required for these roadways. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $41,187 | $39,476 | $1,711 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 20:30:42
CSF- 64 | OSI 609 | Feldwood Road @ Morning Creek Drive | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Completed | Intersection will be analyzed for traffic improvements including a roundabout alternative. Curb & Gutter, drainage, sidewalks, and street lights will be part of the proposed improvements. The intersection improvements will provide geometric and congestion relief. |  | AEI | December, 2022 |  | January, 2023 |  |  | Sales Tax | $952,800 | $79,878 | $872,922 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-05 00:42:06
CSF- 65 | OSI 610 | Feldwood Road @ Bench Mark Drive | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Completed | Intersection will be analyzed for traffic improvements including a roundabout alternative. Curb & Gutter, drainage, sidewalks, and street lights will be part of the proposed improvements. The intersection improvements will provide geometric and congestion relief. |  | American Engineers, Inc | December, 2022 | December, 2020 | December, 2022 |  |  | Sales Tax | $775,200 | $35,000 | $740,200 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2023-03-05 00:45:19
CSF- 66 | OSI 613 | Old Fairburn Road @ Union Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | Improvements will include the addition of a circular roundabout to address congestion and reduce the severity of accidents at this intersection. Additional improvements include drainage, curb & gutter, streetlights, and 5' wide sidewalks. Due to the proximity, this project will be delivered as a single construction project along with OSI 615 Stonewall Tell Road @ Union Road. |  | American Engineers, Inc | March, 2023 | December, 2020 | July, 2025 |  |  | Sales Tax | $1,464,000 | $38,399 | $1,425,601 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2023-03-05 00:46:59
CSF- 67 | OSI 614 | Rivertown Road @ Cedar Grove Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Bidding | Improvements will include the addition of a circular roundabout to address congestion and reduce the severity of accidents at this intersection. Additional improvements include drainage, curb & gutter, streetlights, and 5' wide sidewalks. |  | American Engineers, Inc | February, 2023 | July, 2024 | March, 2023 |  | https://performance.fultoncountyga.gov/stories/s/f85b-5vnc | Sales Tax | $1,310,000 | $98,319 | $1,211,681 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2023-03-05 00:49:10
CSF- 68 | OSI 615 | Stonewall Tell Road @ Union Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | Improvements will include the addition of a circular roundabout to address congestion and reduce the severity of accidents at this intersection. Additional improvements include drainage, curb & gutter, streetlights, and 5Æ wide sidewalks. Due to the proximity, this project will be delivered as a single construction project along with OSI 613 Old Fairburn Road at Union Road. |  | American Engineers, Inc | March, 2023 | December, 2020 | July, 2025 |  | https://performance.fultoncountyga.gov/stories/s/itui-hn3h | Sales Tax | $1,488,000 | $32,049 | $1,455,951 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2023-03-06 12:28:39
CSF- 69 | OSI 616 | Stonewall Tell Road @ Jones Road/Pittman Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | The intersection will be analyzed for traffic improvements including a roundabout alternative. Additional improvements include curb & gutter, drainage, sidewalks, and streetlights. The intersection improvements will improve safety and relieve congestion. |  | AEI | March, 2023 | December, 2020 | October, 2024 |  |  | Sales Tax | $1,600,000 | $87,890 | $1,512,110 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2021 | 2023-03-06 12:30:16
CSF- 7 | RC 106 | New Hope Road (Boat Rock to Cascade Rd) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The New Hope Road (Boat Rock to Cascade Rd) to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | December, 2017 |  | Sales Tax | $414,358 | $453,951 | $-39,593 | Yellow | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 16:14:02
CSF- 70 | OSI 617 | Welcome All Road @ Jailette Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | The intersection will be analyzed for traffic improvements including a roundabout alternative. Curb & Gutter, drainage, sidewalks, and street lights will be part of the proposed improvements. The intersection improvements will address safety improvements, congestion mitigation, and geometric design standards. |  | ATLAS | March, 2023 | May, 2021 | April, 2024 |  |  | Sales Tax | $1,070,400 | $142,000,108,847 | $-141,999,038,447 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2023-03-06 12:32:33
CSF- 71 | OSI 618 | Welcome All Road @ Scarboro Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | The intersection will be analyzed for traffic improvements including a roundabout alternative. Curb & Gutter, drainage, sidewalks, and street lights will be part of the proposed improvements. The intersection improvements will address safety improvements, congestion mitigation, and geometric design standards. |  | AEI | May, 2023 | May, 2021 | December, 2024 |  |  | Sales Tax | $1,556,400 | $84,643 | $1,471,757 | Green | Green | Active | roussan.francois@fultoncountyga.gov |  | 2023-03-06 12:37:09
CSF- 72 | RST 202 | Falls @ Camp Creek | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The primary work is to resurface the final asphalt topping layer. The road Casa Blanca Lane) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. Milling of the existing asphalt surface is not expected to be required for these roadways. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $50,297 | $62,067 | $-11,770 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 20:30:59
CSF- 73 | OSI 619 | West Stubbs Road @ Butner Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Bidding | Intersection will be analyzed for traffic improvements including a roundabout alternative. Curb & Gutter, drainage, sidewalks, and street lights will be part of the proposed improvements. The intersection improvements will provide geometric and congestion relief. |  |  |  | July, 2021 |  |  |  | Sales Tax | $1,722,000 | $150,000 | $1,572,000 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2021-10-19 13:23:07
CSF- 74 | OSI 620 | Aldredge Road @Merk Road | Tier 2 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | Intersection will be analyzed for traffic improvements including a roundabout alternative. Curb & Gutter, drainage, sidewalks, and street lights will be part of the proposed improvements. The intersection improvements will provide geometric and congestion relief. |  |  |  | July, 2021 |  |  |  | Sales Tax | $984,000 | $0 | $984,000 | Gray | Gray | Active
CSF- 75 | OSI 621 | Bethsaida Road @ Old National Hwy. | Tier 2 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | Intersection will be analyzed for traffic improvements including a roundabout alternative. Curb & Gutter, drainage, sidewalks, and street lights will be part of the proposed improvements. The intersection improvements will provide geometric and congestion relief. |  |  |  | July, 2021 |  |  |  | Sales Tax | $1,788,000 | $0 | $1,788,000 | Gray | Gray | Active
CSF- 76 | OSI 622 | Butner Road @ Aldredge Road | Tier 2 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | Intersection will be analyzed for traffic improvements including a roundabout alternative. Curb & Gutter, drainage, sidewalks, and street lights will be part of the proposed improvements. The intersection improvements will provide geometric and congestion relief. |  |  |  | July, 2021 |  |  |  | Sales Tax | $1,434,000 | $0 | $1,434,000 | Gray | Gray | Active
CSF- 77 | OSI 624 | Washington Road @ Roosevelt Highway | Tier 2 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | Intersection will be analyzed for traffic improvements including a roundabout alternative. Curb & Gutter, drainage, sidewalks, and street lights will be part of the proposed improvements. The intersection improvements will provide geometric and congestion relief. |  |  |  | July, 2021 |  |  |  | Sales Tax | $2,449,200 | $0 | $2,449,200 | Gray | Gray | Active
CSF- 78 | OSI 625 | Welcome All Road @ Will Lee Road | Tier 2 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | Intersection will be analyzed for traffic improvements including a roundabout alternative. Curb & Gutter, drainage, sidewalks, and street lights will be part of the proposed improvements. The intersection improvements will provide geometric and congestion relief. |  |  | July, 2021 |  |  |  |  | Sales Tax | $1,669,200 | $0 | $1,669,200 | Gray | Gray | Active
CSF- 79 | SU 700 | Flat Shoals Rd at Old National Hwy | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | Traffic signal upgrades will include new mast arm poles, new cabinets, detection, signal heads, back plates, pedestrian signals, and pavement markings at the intersections. The work will include fiber communication along Flat Shoals Road from Mallory Road to Old National Highway. |  | Jacobs | March, 2023 | September, 2020 | July, 2024 |  |  | Sales Tax | $250,000 | $0 | $250,000 | Green | Green | Active | roussan.francois@fultoncountyga.gov |  | 2023-03-06 12:54:47
CSF- 8 | RC 107 | Old Bill Cook Road (Buffington Rd to Old National Hwy) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The Old Bill Cook Road (Buffington Rd to Old National Hwy) to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. |  | Not Applicable | Not Applicable | March, 2020 | August, 2020 |  |  | Sales Tax | $438,189 | $458,162 | $-19,973 | Yellow | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 16:14:51
CSF- 80 | SU 701 | Flat Shoals Rd at Hemperly Rd | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | The overall objective of this project is the redesign and reconstruction of eleven (11) traffic signals along the Flat Shoals Road corridor to complement the proposed Advanced Traffic Management System (ATMS) along the corridor. Closed Circuit TV (CCTV) cameras will be installed as well as fiber optic drop cables to the cameras and existing traffic signals. Traffic signals will be timed to maintain coordinated traffic flow through the synchronized intersections. The progression of vehicles along the major roadway will be given priority even when the characteristics of the roadway traffic flow and control changes. |  |  |  | July, 2019 |  |  |  | Sales Tax | $250,000 | $0 | $250,000 | Green | Green | Active
CSF- 81 | SU 702 | Flat Shoals Rd at Kimberly Mill Road | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | The overall objective of this project is the redesign and reconstruction of eleven (11) traffic signals along the Flat Shoals Road corridor to complement the proposed Advanced Traffic Management System (ATMS) along the corridor. Closed Circuit TV (CCTV) cameras will be installed as well as fiber optic drop cables to the cameras and existing traffic signals. Traffic signals will be timed to maintain coordinated traffic flow through the synchronized intersections. The progression of vehicles along the major roadway will be given priority even when the characteristics of the roadway traffic flow and control changes. |  |  |  | July, 2019 |  |  |  | Sales Tax | $250,000 | $0 | $250,000 | Green | Green | Active
CSF- 82 | RST 218 | Forrest Creek | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The primary work is to resurface the final asphalt topping layer. The roads (Amberland Sq, Bluemist Cove, Graywind Trl, and Jadetree La) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. Milling of the existing asphalt surface is not expected to be required for these roadways. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $86,578 | $101,379 | $-14,801 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 20:14:31
CSF- 83 | SU 703 | Flat Shoals Rd at Red Oak Rd | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | The overall objective of this project is the redesign and reconstruction of eleven (11) traffic signals along the Flat Shoals Road corridor to complement the proposed Advanced Traffic Management System (ATMS) along the corridor. Closed Circuit TV (CCTV) cameras will be installed as well as fiber optic drop cables to the cameras and existing traffic signals. Traffic signals will be timed to maintain coordinated traffic flow through the synchronized intersections. The progression of vehicles along the major roadway will be given priority even when the characteristics of the roadway traffic flow and control changes. | Not Applicable | Not Applicable |  | July, 2019 |  |  |  | Sales Tax | $250,000 | $0 | $250,000 | Green | Green | Active
CSF- 84 | SU 704 | Flat Shoals Rd at Hidden Brook Dr | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | The overall objective of this project is the redesign and reconstruction of eleven (11) traffic signals along the Flat Shoals Road corridor to complement the proposed Advanced Traffic Management System (ATMS) along the corridor. Closed Circuit TV (CCTV) cameras will be installed as well as fiber optic drop cables to the cameras and existing traffic signals. Traffic signals will be timed to maintain coordinated traffic flow through the synchronized intersections. The progression of vehicles along the major roadway will be given priority even when the characteristics of the roadway traffic flow and control changes. |  |  |  | July, 2019 |  |  |  | Sales Tax | $250,000 | $0 | $250,000 | Green | Green | Active
CSF- 85 | SU 705 | Flat Shoals Rd at Connel Rd | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | The overall objective of this project is the redesign and reconstruction of eleven (11) traffic signals along the Flat Shoals Road corridor to complement the proposed Advanced Traffic Management System (ATMS) along the corridor. Closed Circuit TV (CCTV) cameras will be installed as well as fiber optic drop cables to the cameras and existing traffic signals. Traffic signals will be timed to maintain coordinated traffic flow through the synchronized intersections. The progression of vehicles along the major roadway will be given priority even when the characteristics of the roadway traffic flow and control changes. |  |  |  | July, 2019 |  |  |  | Sales Tax | $250,000 | $0 | $250,000 | Green | Green | Active
CSF- 86 | SU 706 | Flat Shoals Rd at Buffington Rd | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | The overall objective of this project is the redesign and reconstruction of eleven (11) traffic signals along the Flat Shoals Road corridor to complement the proposed Advanced Traffic Management System (ATMS) along the corridor. Closed Circuit TV (CCTV) cameras will be installed as well as fiber optic drop cables to the cameras and existing traffic signals. Traffic signals will be timed to maintain coordinated traffic flow through the synchronized intersections. The progression of vehicles along the major roadway will be given priority even when the characteristics of the roadway traffic flow and control changes. |  |  |  | July, 2019 |  |  |  | Sales Tax | $250,000 | $0 | $250,000 | Green | Green | Active
CSF- 87 | SU 707 | Flat Shoals Rd at I -85 North | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | The overall objective of this project is the redesign and reconstruction of eleven (11) traffic signals along the flat Shoals Road corridor to complement the proposed ATMS along the corridor. CCTV cameras will be installed as well as fiber optic drop cables to the cameras and existing traffic signals. Traffic signals will be timed to maintain coordinated traffic flow progression through the synchronized intersections. The progression of vehicles along the major roadway will be given priority even when the characteristics of the roadway traffic flow and control changes. |  |  |  | July, 2019 |  |  |  | Sales Tax | $250,000 | $0 | $250,000 | Green | Green | Active
CSF- 88 | SU 708 | Flat Shoals Rd at I -85 South | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | The overall objective of this project is the redesign and reconstruction of eleven (11) traffic signals along the Flat Shoals Road corridor to complement the proposed Advanced Traffic Management System (ATMS) along the corridor. Closed Circuit TV (CCTV) cameras will be installed as well as fiber optic drop cables to the cameras and existing traffic signals. Traffic signals will be timed to maintain coordinated traffic flow through the synchronized intersections. The progression of vehicles along the major roadway will be given priority even when the characteristics of the roadway traffic flow and control changes. |  |  |  | July, 2019 |  |  |  | Sales Tax | $250,000 | $0 | $250,000 | Green | Green | Active
CSF- 89 | SU 709 | Flat Shoals Rd at Feldwood Rd | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | The overall objective of this project is the redesign and reconstruction of eleven (11) traffic signals along the Flat Shoals Road corridor to complement the proposed Advanced Traffic Management System (ATMS) along the corridor. Closed Circuit TV (CCTV) cameras will be installed as well as fiber optic drop cables to the cameras and existing traffic signals. Traffic signals will be timed to maintain coordinated traffic flow through the synchronized intersections. The progression of vehicles along the major roadway will be given priority even when the characteristics of the roadway traffic flow and control changes. |  |  |  | July, 2019 |  |  |  | Sales Tax | $250,000 | $0 | $250,000 | Green | Green | Active
CSF- 9 | RC 108 | Old Fairburn Road (Union Rd to Camp Creek Pkwy) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The Old Fairburn Road (Union Rd to Camp Creek Pkwy) to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | December, 2017 |  | Sales Tax | $606,253 | $642,227 | $-35,974 | Yellow | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 16:15:50
CSF- 90 | SU 710 | Flat Shoals Rd at Mallory Rd | Tier 1 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | The overall objective of this project is the redesign and reconstruction of eleven (11) traffic signals along the Flat Shoals Road corridor to complement the proposed Advanced Traffic Management System (ATMS) along the corridor. Closed Circuit TV (CCTV) cameras will be installed as well as fiber optic drop cables to the cameras and existing traffic signals. Traffic signals will be timed to maintain coordinated traffic flow through the synchronized intersections. The progression of vehicles along the major roadway will be given priority even when the characteristics of the roadway traffic flow and control changes. |  |  |  | July, 2019 |  |  |  | Sales Tax | $250,000 | $0 | $250,000 | Green | Green | Active
CSF- 91 | ATMS 800 | Flat Shoals Road | Tier 2 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Design | The overall objective of this project is the redesign and reconstruction of eleven (11) traffic signals along the Flat Shoals Road corridor to complement the proposed Advanced Traffic Management System (ATMS) along the corridor. Closed Circuit TV (CCTV) cameras will be installed as well as fiber optic drop cables to the cameras and existing traffic signals. Traffic signals will be timed to maintain coordinated traffic flow through the synchronized intersections. The progression of vehicles along the major roadway will be given priority even when the characteristics of the roadway traffic flow and control changes. |  |  | December, 2021 | July, 2021 | March, 2023 |  |  | Sales Tax | $1,000,000 | $326,837 | $673,163 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2020 | 2021-05-03 23:10:11
CSF- 92 | PBI 900 | Danforth Road (Rehoboth Circle to Cascade Road) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | City of South Fulton | Construction | The project scope includes the installation of 5 foot-wide concrete ADA (Americans with Disabilities Act) compliant sidewalks, concrete curb and gutter, a 2- foot stamped concrete, drainage and pedestrian lighting on both sides of Danforth Road from Rehoboth Circle to Cascade Road. The approximate length of the project is 0.8 mile. | CMC, INC | AEI | September, 2022 | February, 2022 | December, 2023 |  |  | Sales Tax | $2,250,000 | $90,653 | $2,159,347 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2023-03-06 12:44:33
CSF- 93 | PBI 901 | Enon Road (Lynarbor Lane to Sanford J. Jones) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | City of South Fulton | Design | Proposed project includes sidewalk facilities along both sides of Enon Road from just north of Lynarbor Lane and extends to Sanford J. Jones Boulevard for a distance of approximately 1.5 miles. Project features include adding 5-6 foot sidewalks along the west side, 8-ft. sidewalks along east side from Lynarbor Lane to Sanford J. Jones Boulevard. Drainage improvements, curb and gutter, and 2-foot stamped concrete is also included. |  | AAEI | March, 2023 | September, 2020 | June, 2024 |  |  | Sales Tax | $2,000,000 | $43,650 | $1,956,350 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2023-03-06 12:46:48
CSF- 94 | RST 203 | Falls @ Cascade Palms Phase 2 | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The roads (Palmview Court, Smithers Way, Talkeetna Court, Muskeg Court, and Cutbank Court) within the subdivision is to resurface the final asphalt topping layer. The roads within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. The subject subdivison was topped through an earlier contract outside TSPLOST funding. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $86,578 | $103,523 | $-16,945 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 20:31:37
CSF- 95 | OSI 600 | Bethsaida Road at Creel Road | Tier 2 | Operation and Safety Improvements | TSPLOST | City of South Fulton | Planning | Intersection will include either a roundabout or conventional improvements. A conventional improvement includes additional turn lanes and sometimes, if warranted, a signal. Whichever alternative is concluded, sidewalks, street lights, curb & gutter, and drainage will be included. |  |  |  | July, 2021 |  |  |  | Sales Tax | $1,353,600 | $0 | $1,353,600 | Gray | Gray | Active
CSF- 96 | RST 204 | Foxfire PH2, (LL 124/133 Dist 13) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The primary work is to resurface the final asphalt topping layer. The roads (Grey Fox Way and Polar Fox Ct) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. Milling of the existing asphalt surface is not expected to be required for these roadways. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $57,555 | $113,654 | $-56,099 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 20:31:52
CSF- 97 | RST 205 | Herron Creek PH2, (LL 99 Dist 14FF, LL 175 Dist 9C) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The primary work is to resurface the final asphalt topping layer. The roads (Halcyon Dr, Herron Trl, Herron La, Herron Pass, Herron Point, and Herron Trace) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. Milling of the existing asphalt surface is not expected to be required for these roadways. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $68,057 | $90,131 | $-22,074 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 20:32:08
CSF- 98 | RST 206 | Lake Royale U3, (LL 188 Dist 13) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The primary work is to resurface the final asphalt topping layer. The roads (Lake Rorale Drive and Lake Royale Pl)) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. Milling of the existing asphalt surface is not expected to be required for these roadways. | E R Snell | Not Applicable | Not Applicable |  | November, 2017 | Not Applicable |  | Sales Tax | $43,845 | $32,373 | $11,472 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 20:32:26
CSF- 99 | RST 207 | Le Jardin Multiple Phases | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The primary work is to resurface the final asphalt topping layer. The roads (Artistry Way, Botanica Way, Butchart Pl, Concerto Ct, Le Jardin Blvd, Les Fleurs La, Matisse Lane, Queen Ann Cage Ct, and Tapestry Club Dr) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. Milling of the existing asphalt surface is not expected to be required for these roadways. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $250,000 | $245,590 | $4,410 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 20:32:41
CSS- 10 | TS106 | Northside Dr. at Riverview Dr.-Old Powers Ferry Rd. | Tier 1 | Operation and Safety Improvements | TSPLOST | Sandy Springs | Completed | Realignment of the intersection and a possible roundabout with sidewalk improvements. | Vertical Earth | HNTB | May, 2021 | September, 2018 | August, 2024 | March, 2024 | http://spr.gs/riverview | Sales Tax | $4,402,748 | $3,660,367 | $742,381 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2024 | 2025-02-28 09:05:10
CSS- 11 | TS105 | Roswell Road at Grogans Ferry Road | Tier 1 | Operation and Safety Improvements | TSPLOST | Sandy Springs | Completed | Realignment of the intersection and installation of traffic signal. Access management on Roswell Road. | Ohmshiv | Columbia Engnieering | July, 2020 | February, 2018 | April, 2023 | March, 2023 | https://www.sandyspringsga.gov/roswell-roadgrogans-ferry-road-improvements | Sales Tax | $4,800,000 | $4,765,529 | $34,471 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2023 | 2024-03-29 14:31:48
CSS- 12 | TS108 | Roswell Road at Dalrymple Road | Tier 1 | Operation and Safety Improvements | TSPLOST | Sandy Springs | Completed | Extend EB left-turn storage and increase radii on NW and SW quadrants | Vertical Earth | KCI | May, 2021 | October, 2018 | December, 2024 | November, 2024 |  | Sales Tax | $2,840,000 | $2,400,529 | $439,471 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2024 | 2025-12-11 08:49:00
CSS- 13 | TS114 | Mount Vernon Hwy at Heards Ferry Road (Phase 2) | Tier 1 | Operation and Safety Improvements | TSPLOST | Sandy Springs | Completed | Construction of dedicated NB left-turn lane |  |  |  | May, 2020 |  |  |  | Sales Tax | $0 | $0 | $0 | Green | Green | Inactive | ajohnson@sandyspringsga.gov | 2021 | 2022-05-26 17:57:42
CSS- 14 | TS113 | Lake Forest Drive at Mount Paran Road | Tier 1 | Operation and Safety Improvements | TSPLOST | Sandy Springs | Completed | Add NB and SB dedicated right-turn lanes | [7 empty] | Sales Tax | $0 | $0 | $0 | Green | Green | Inactive | ajohnson@sandyspringsga.gov | 2022 | 2022-05-26 17:57:21
CSS- 15 | TS104 | Roswell Road at Trowbridge Road (Concept) | Tier 1 | Operation and Safety Improvements | TSPLOST | Sandy Springs | Completed | Design and construct EB and WB turn lane extensions and SB right turn lane | [7 empty] | Sales Tax | $0 | $0 | $0 | Green | Green | Inactive | ajohnson@sandyspringsga.gov | 2021 | 2022-05-26 17:48:15
CSS- 16 | TS131 | Peachtree Dunwoody Multi-Use Path | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Land | The project consists of a multi-use path from Hammond Drive to Abernathy Road in conjunction with PCID. |  | Kimley Horn | October, 2026 | January, 2024 | April, 2028 | April, 2028 |  | Sales Tax | $3,050,000 | $465,721 | $2,584,279 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2028 | 2026-03-06 15:48:32
CSS- 17 | TS136 | Central Parkway Sidewalk Gap Fill | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Provided a 600 ft. sidewalk gap fill in Sandy Springs and Dunwoody along Central Parkway in the Perimeter district | GDP | PCID/Dunwoody | February, 2018 | March, 2018 | March, 2018 | March, 2018 |  | Sales Tax | $15,899 | $15,899 | $0 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2018 | 2021-05-04 19:12:29
CSS- 18 | TS191 | Mt Vernon Road and Johnson Ferry Road Intersection Improvements | Tier 1 | Congestion Relief | TSPLOST | Sandy Springs | Construction | Operation and Safety improvements near the intersection of Mt. Vernon Hwy and Johnson Ferry Road. | Vertical Earth | Jacobs | December, 2022 | May, 2017 | May, 2026 | April, 2026 | http://spr.gs/jfmv | Sales Tax | $27,300,000 | $19,596,575 | $7,703,425 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2026 | 2026-03-06 15:49:07
CSS- 19 | TS192 | Mt. Vernon Multi Use Path | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Construction | Multi-modal transportation options are being considered in this key link between City Springs and the Sandy Springs MARTA Station | Excellere | KCI | December, 2022 | July, 2017 | April, 2026 | April, 2026 | http://spr.gs/mvc | Sales Tax | $18,075,160 | $14,383,687 | $3,691,473 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2026 | 2026-03-06 15:49:30
CSS- 20 | TS193 | Hammond Drive - Phase 1 Efficiency Improvements | Tier 1 | Congestion Relief | TSPLOST | Sandy Springs | Completed | The project limits are Hammond Drive from Roswell Road (State Route 9) to Glenridge Drive. The scope of work includes developing concepts for the widening of Hammond Drive with associated operational improvements to intersections along the corridor. The goals of this project are to improve safety, mobility, and improve pedestrian/bicycle access. |  | Gresham Smith | July, 2022 | September, 2018 |  |  | http://spr.gs/hdc | Sales Tax | $12,504,162 | $12,504,162 | $0 | Green | Green | Active | ajohnson@sandyspringsga.gov |  | 2023-12-14 15:56:19
CSS- 21 | TS201 | SR 400 Trail System | Tier 2 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Looking into multiple segments of adding a multi-use path between the Cities of Atlanta and Roswell along/near SR400. |  | Heath & Lineback | April, 2021 | August, 2017 | May, 2024 | May, 2024 | http://spr.gs/400 | Sales Tax | $0 | $0 | $0 | Gray | Gray | Inactive | ajohnson@sandyspringsga.gov | 2024 | 2022-05-26 18:30:47
CSS- 22 | TS161 | Johnson Ferry Road - Harleston Rd. to Glenridge Drive | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Installation of 6' sidewalk on the south side of Johnson Ferry Road from the existing sidewalk on Glenridge Drive to the existing sidewalk on Johnson Ferry Road-just west of Kayron Drive. Pedestrian lights will also be installed. | Triscapes | CALYX | April, 2019 | May, 2017 | January, 2020 | December, 2019 |  | Sales Tax | $415,275 | $415,275 | $0 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2020 | 2022-07-29 17:57:16
CSS- 23 | TS137 | Johnson Ferry Road - Glenridge Connector to existing sidewalk at Wells Fargo site | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Connect the sidepath system on south side of Johnson Ferry Road from existing sidewalk onto Glenridge Drive | Proterra Development | AEI | May, 2019 | May, 2017 | October, 2020 | September, 2020 |  | Sales Tax | $472,581 | $472,581 | $0 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2020 | 2022-08-16 13:17:02
CSS- 24 | TS164 | Windsor Pkwy - Peachtree Dunwoody Rd. to City Limit | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Connect the sidewalk system on south side of Windsor Pkwy from existing sidewalk to the City Limit | Astra Grading | Michael Baker | November, 2019 | May, 2017 | November, 2020 | November, 2020 | http://spr.gs/26 | Sales Tax | $1,204,969 | $1,204,969 | $0 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2020 | 2022-07-29 17:59:11
CSS- 25 | TS165 | Northwood Drive - Kingsport to Roswell Road | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Connect the sidewalk system on south side of Northwood Drive from Kingsport Dr. to existing sidewalk | Proterra Development | AEI | May, 2018 | July, 2018 | February, 2019 | December, 2018 |  | Sales Tax | $268,968 | $268,968 | $0 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2019 | 2022-05-26 18:05:34
CSS- 26 | TS166 | Spalding Drive - Spalding Lake Ct. to Holcomb Bridge | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | The City included adding multi-use paths along Spalding Drive as part of the T-SPLOST project. As part of the agreement with Gwinnett County, improvements will include a multi-use path along the south side of Spalding Drive, from Winters Chapel Road to River Exchange Drive, and a sidewalk on the north side of Spalding Drive from Winters Chapel Road to River Exchange Drive. The sidewalks will connect to the existing sidewalks on Holcomb Bridge Road and will provide enhanced connectivity to Crooked Creek Park and the surrounding neighborhoods. | CMES | Atkins | December, 2019 | October, 2017 | May, 2023 | May, 2023 | http://spr.gs/spalding | Sales Tax | $1,963,352 | $1,882,608 | $80,744 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2023 | 2023-12-14 15:54:36
CSS- 27 | TS167 | Brandon Mill Road - Marsh Creek to Lost Forest Dr. - Design | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Connect the sidewalk system on east side of Brandon Mill Road from existing sidewalk to Lost Forest Dr | CMES | Atkins | March, 2019 | October, 2017 | March, 2022 | March, 2022 |  | Sales Tax | $1,950,728 | $1,725,047 | $225,681 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2022 | 2024-10-18 16:02:43
CSS- 28 | TS168 | Dalrymple Road - existing sidewalk at Princeton Sq (@Princeton Way) to Duncourtney Dr. | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Connect the sidewalk system on north side of Dalrymple Road from Princeton Way to Duncourtney Dr. May need mid-block crossing at Duncourtney Dr to the existing sidewalk on south side | Construction 57 | KCI | September, 2021 | February, 2020 | April, 2023 | March, 2023 |  | Sales Tax | $759,155 | $426,265 | $332,890 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2023 | 2023-04-27 13:47:17
CSS- 29 | TS169 | Dunwoody Club Dr. - Spalding to exsiting walk at Fenimore Circle | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Connect the sidewalk system on east side of Dunwoody Club Drive from existing sidewalk to Spalding Dr | CMES | Calyx | July, 2020 | March, 2019 | May, 2022 | May, 2022 |  | Sales Tax | $1,165,000 | $1,036,283 | $128,717 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2022 | 2023-01-27 22:08:43
CSS- 3 | TS115 | Mt. Vernon at Long Island | Tier 1 | Operation and Safety Improvements | TSPLOST | Sandy Springs | Completed | Add left turn on Long Island | Excellere | Michael Baker | July, 2017 | August, 2017 | October, 2017 | September, 2017 |  | Sales Tax | $91,937 | $91,937 | $0 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2018 | 2021-05-04 19:12:07
CSS- 30 | TS170 | Interstate North Pkwy - Chattahoochee River to Northside Drive | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Sidepath system on north side of Interstate Pkwy from the park to Northside Drive | CMES | Atkins | October, 2020 | March, 2019 | November, 2022 | November, 2022 |  | Sales Tax | $2,646,272 | $2,436,362 | $209,910 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2022 | 2023-01-27 22:10:38
CSS- 31 | TS171 | Roberts Drive (Ex. Walk S of Northridge Rd to Ex. Walk at Davis Academy) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Connect the sidewalk system on east side of Roberts Drive from Northridge to Davis Academy | SD&C | Calyx | July, 2020 | February, 2019 | January, 2022 | July, 2021 |  | Sales Tax | $446,377 | $446,377 | $0 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2021 | 2022-07-29 18:04:05
CSS- 32 | TS172 | Brandon Mill Road - Lost Forest Dr. to Brandon Ridge Dr. | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Connect the sidewalk system on east side of Brandon Mill Road from Lost Forest Drive to Brandon Ridge Dr |  | NV5 | October, 2021 | December, 2019 | May, 2025 | May, 2025 |  | Sales Tax | $466,403 | $474,840 | $-8,437 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2025 | 2024-10-18 16:02:27
CSS- 33 | TS173 | Dalrymple Road -605 Dalrymple Road (near Roswell Rd) to Duncourney Dr. | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Connect the sidewalk system on south side of Dalrymple Road to Duncourtney Dr. | [7 empty] | Sales Tax | $0 | $0 | $0 | Green | Green | Inactive | ajohnson@sandyspringsga.gov |  | 2022-05-26 18:24:28
CSS- 34 | TS174 | Riverside Drive - Johnson Ferry to Brandon Mill | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Connect the sidewalk system from south of I-285 to Mt Vernon Hwy. Curb and gutter will be required in some areas. | [7 empty] | Sales Tax | $0 | $0 | $0 | Green | Green | Inactive | ajohnson@sandyspringsga.gov |  | 2021-05-03 20:28:00
CSS- 35 | TS132 | Ashton Woods Last Mile Connection (Concept) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Looking for a concept to connect the Ashton Woods development to Glenlake Drive. |  | KCI | February, 2019 | September, 2018 |  |  |  | Sales Tax | $0 | $0 | $0 | Green | Green | Inactive | ajohnson@sandyspringsga.gov |  | 2022-05-26 18:01:27
CSS- 36 | S2104 | Boylston Drive Sidepath & Realignment | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Sandy Springs | Construction | Intersection and streetscape improvements from Hammond Drive to Hilldebrand Drive. | Excellere | NV5 | November, 2024 | October, 2019 | March, 2025 | March, 2025 |  | Sales Tax | $0 | $0 | $0 | Green | Green | Inactive | ajohnson@sandyspringsga.gov | 2025 | 2025-12-11 08:32:32 | Georgia | Boylston Drive | 2022-03-31
CSS- 37 | S2103 | Johnson Ferry Rd at Peachtree Dunwoody Rd Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Sandy Springs | Concept | Intersection improvement at Johnson Ferry Road and Peachtree Dunwoody Road |  | KCI |  | February, 2023 |  |  |  | Sales Tax | $3,000,000 | $47,378 | $2,952,622 | Green |  | Active | ajohnson@sandyspringsga.gov |  | 2025-06-18 16:13:32 | Georgia | Johnson Ferry Rd | 2022-03-31
CSS- 38 | S2105 | Roswell Road North Boulevard Project | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Sandy Springs | Design | Streetscape, access management and intersection improvements on Roswell Road from Dunwoody Place to the Chattahoochee River |  | Heath & Lineback | July, 2028 | July, 2024 | March, 2030 | March, 2030 |  | Sales Tax | $8,800,000 | $202,822 | $8,597,178 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2030 | 2026-03-06 15:35:20 | Georgia | Roswell Road | 2022-03-31
CSS- 39 | S2101 | Intelligent Transportation System Ring A | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Sandy Springs | Bidding | Intelligent Transportation System Ring A |  | Kimley Horn | April, 2024 | May, 2023 | January, 2027 | January, 2027 |  | Sales Tax | $1,500,000 | $812,997 | $687,003 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2027 | 2026-03-06 15:38:03 | Georgia | 5559 Glenridge Drive, Sandy Springs, GA 30342 | 2022-03-31
CSS- 4 | TS103 | Spalding Drive at Dalrymple Road-Trowbridge | Tier 1 | Operation and Safety Improvements | TSPLOST | Sandy Springs | Completed | NB and SB left-turn lanes; WB left-turn and right-turn lanes. Upgraded signal operation. | CMES | KCI | October, 2019 | April, 2017 | May, 2021 | May, 2021 |  | Sales Tax | $2,422,873 | $2,422,873 | $0 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2021 | 2022-07-29 17:47:49
CSS- 40 | S2121 | SR 400 Multi-Use Trail | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Construction | Project will provide an extension of the existing trail with a 12Æ multi-use trail along the east side of SR400 from Loridans Drive to north of the Glenridge Connector. This is the construction match funding for 1.8 miles in Sandy Springs. | FS Scarborough | Heath & Lineback | June, 2023 | August, 2017 | January, 2028 | January, 2028 |  | Sales Tax | $4,000,000 | $2,035,437 | $1,964,563 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2028 | 2026-03-06 15:35:39 | Georgia | SR 400 | 2022-03-31
CSS- 41 | S2122 | Glenridge Dr., Hammond to south of Wellington Trace | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Land | Multi-Use Trail on Glenridge Drive from Wellington Place to Hammond Drive |  | Holt | November, 2025 | April, 2024 | August, 2027 | August, 2027 |  | Sales Tax | $2,500,000 | $371,771 | $2,128,229 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2027 | 2026-03-06 15:36:11 | Georgia | Glenridge Dr | 2022-03-31
CSS- 42 | S2185-2 | Lake Forrest Sidewalk Phase 2 | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Land | Sidewalk project on Lake Forrest Drive from City Limit to Long Island Drive |  | Kimley Horn | January, 2026 | January, 2023 | March, 2027 | March, 2027 |  | Sales Tax | $2,140,000 | $248,968 | $1,891,032 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2027 | 2025-12-11 08:43:12 | Georgia | Lake Forrest | 2022-03-31
CSS- 43 | S2182 | Holcomb Bridge (River Exchange to Spalding) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Planning | Holcomb Bridge (River Exchange to Spalding) | [7 empty] | Sales Tax | $0 | $0 | $0 | Green |  | Active | ajohnson@sandyspringsga.gov |  | 2024-05-20 14:53:53 | Georgia | 7840 Holcomb Bridge Rd, Sandy Springs, GA | 2022-03-31
CSS- 44 | S2193 | Hammond Drive Widening | Tier 1 | Congestion Relief | TSPLOST2 | Sandy Springs | Land | Project provides multi-modal opportunities within the approximately 0.75 mile corridor between Boylston Drive and Glenridge Drive including increased vehicular capacity, roundabouts, transit/shuttle provisions, multi-use trails, sidewalks, wide median, and other attributes. |  | Gresham Smith | August, 2025 | June, 2022 | June, 2029 | June, 2029 |  | Sales Tax | $35,000,000 | $11,874,378 | $23,125,622 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2029 | 2026-03-06 15:48:01 | Georgia | Hammond Drive | 2022-03-31
CSS- 45 | S2221 | Roberts Drive Sidepath, Roswell Rd to Dunwoody Pl | Tier 2 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Planning | Multi-Use Trail on Roberts Drive from Dunwoody Place to Island Ford Parkway, continuing onto Roswell Road. | [7 empty] | Sales Tax | $9,855,000 | $0 | $9,855,000 | Green |  | Active | ajohnson@sandyspringsga.gov |  | 2022-11-18 22:13:35 | Georgia | Roberts Drive | 2022-03-31
CSS- 46 | S2132 | Riverside Road Bridge Over Chattahoochee Tributary | Tier 1 | Bridges | TSPLOST2 | Sandy Springs | Design | Riverside Road Bridge Over Chattahoochee Tributary |  | Heath & Lineback | May, 2026 | May, 2023 | May, 2028 | May, 2028 |  | Sales Tax | $2,400,000 | $372,212 | $2,027,788 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2026 | 2026-03-06 15:39:29 | Georgia | 6545 Riverside Drive, Sandy Springs | 2022-03-31
CSS- 47 | S2123 | Design for Tier 2 Sidepath / Walk Design | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Concept | Design for Tier 2 Multi-Use Trail Design | [7 empty] | Sales Tax | $930,000 | $244,040 | $685,960 | Green | Green | Active | ajohnson@sandyspringsga.gov |  | 2025-12-11 08:34:57 | Georgia | City of Sandy Springs | 2022-03-31
CSS- 48 | S2222 | Johnson Ferry Rd. Sidepath, Glenridge Dr. to Peachtree Dunwoody Rd | Tier 2 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Planning | Multi-Use Trail on Johnson Ferry Road from Glenridge Drive to Peachtree Dunwoody Road | [7 empty] | Sales Tax | $3,607,380 | $0 | $3,607,380 | Green |  | Active | ajohnson@sandyspringsga.gov |  | 2022-11-18 22:13:58 | Georgia | Johnson Ferry Rd | 2022-03-31
CSS- 49 | S2321 | Powers Ferry Sidepath, City Limits to Dupree | Tier 3 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Planning | Multi-Use Path on Powers Ferry Road from City Limit to Dupree Drive | [7 empty] | Sales Tax | $3,607,380 | $0 | $3,607,380 | Green |  | Active | ajohnson@sandyspringsga.gov |  | 2022-11-18 22:14:29 | Georgia | Powers Ferry | 2022-03-31
CSS- 5 | TS107 | SCOOT Upgrade | Tier 1 | Operation and Safety Improvements | TSPLOST | Sandy Springs | Completed | Adaptive signal upgrade for 16 intersections. | RJ Haynie | WSP | May, 2019 | July, 2018 | June, 2021 | June, 2021 |  | Sales Tax | $1,484,961 | $1,484,961 | $0 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2021 | 2022-07-29 17:51:46
CSS- 50 | S2341 | Roadway Maintenance and Paving | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | Sandy Springs | Planning | Roadway Maintenance and Paving | [7 empty] | Sales Tax | $9,000,000 | $0 | $9,000,000 | Green |  | Active | ajohnson@sandyspringsga.gov |  | 2022-11-22 15:21:08 | Georgia | City of Sandy Springs | 2022-03-31
CSS- 51 | S2102 | Intelligent Transportation System Fire Station 3 | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Sandy Springs | Completed | Intelligent Transportation System Fire Station 3 | Lumen8 | Atlas | March, 2025 | May, 2024 | March, 2026 | March, 2026 |  | Sales Tax | $650,000 | $202,077 | $447,923 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2026 | 2026-03-06 15:33:19 |  | 6025 Raider Dr, Sandy Springs, GA 30328
CSS- 52 | S2131 | Mt Vernon Bridge Enhancement | Tier 1 | Bridges | TSPLOST2 | Sandy Springs | Completed | Bridge Enhancement Payment to GDOT for the Mount Vernon Highway Bridge over I-285 | Archer Western | Heath & Lineback |  | September, 2022 | March, 2026 | March, 2026 |  | Sales Tax | $3,203,000 | $3,203,000 | $0 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2026 | 2026-03-06 15:37:23 |  | 425 Mt Vernon Highway, Sandy Springs
CSS- 53 | S2188-1 | Allen Road at Sandy Springs Circle | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Gap Fill Sidewalks | Blount Construction | NV5 |  | January, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $55,000 | $19,125 | $35,875 | Green |  | Active | ajohnson@sandyspringsga.gov | 2023 | 2024-03-29 14:22:20 |  | 1 Allen Rd NE, Sandy Springs, GA 30328
CSS- 54 | S2175 | Trowbridge Road Sidewalk (Spalding Trail to Trowbridge Lake Drive) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Trowbridge Road Sidewalk (Spalding Trail to Trowbridge Lake Drive) | Blount Construction | NV5 | October, 2024 | December, 2022 | April, 2024 | April, 2024 |  | Sales Tax | $95,000 | $50,985 | $44,015 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2024 | 2024-07-22 13:47:37 |  | 7445 Trowbridge Rd, Sandy Springs, GA 30328
CSS- 55 | S2167 | Mt. Vernon Highway Sidewalk (Glen Errol Road to Ex. SW at 500 Mt. Vernon Highway) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Mt. Vernon Highway Sidewalk (Glen Errol Road to Ex. SW at 500 Mt. Vernon Highway) | Sol Construction | NV5 | November, 2023 | December, 2022 | March, 2024 | March, 2024 |  | Sales Tax | $370,000 | $169,046 | $200,954 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2024 | 2024-07-22 13:46:00 |  | 550 Mount Vernon Hwy, Atlanta, GA 30327
CSS- 56 | S2161 | Windsor Parkway Sidewalk - Gap Fills | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Land | Windsor Parkway Sidewalk - Gap Fills |  | NV5 | May, 2025 | January, 2023 | May, 2027 | May, 2027 |  | Sales Tax | $925,000 | $208,767 | $716,233 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2027 | 2026-03-06 15:40:42 |  | 575 Windsor Pkwy, Atlanta, GA 30342
CSS- 57 | S2165 | Riverside Sidewalk (South of 285 to Mt Vernon Highway) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Land | Riverside Sidewalk (South of 285 to Mt Vernon Highway) |  | NV5 | April, 2025 | January, 2023 | January, 2028 | January, 2028 |  | Sales Tax | $885,000 | $158,103 | $726,897 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2028 | 2026-03-06 15:42:44 |  | 5768 Riverside Dr, Atlanta, GA 30327
CSS- 58 | S2170 | Mt. Vernon Highway Sidewalk (Ex. SW at DeClaire Court to Long Island Drive) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Mt. Vernon Highway Sidewalk (Ex. SW at DeClaire Court to Long Island Drive) | Lagniappe | Kimley Horn | July, 2024 | January, 2023 | June, 2024 | June, 2024 |  | Sales Tax | $215,000 | $139,602 | $75,398 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2024 | 2025-07-17 14:22:20 |  | 5970 Long Island Dr, Sandy Springs, GA 30328
CSS- 59 | S2172 | Glenridge Drive Sidewalk (Canopy Drive to Glenridge Close Court) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Design | Glenridge Drive Sidewalk (Canopy Drive to Glenridge Close Court) |  | Heath & Lineback | August, 2024 | December, 2022 | March, 2025 | March, 2025 |  | Sales Tax | $225,000 | $70,560 | $154,440 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2025 | 2024-03-29 10:51:54 |  | 6449 Glenridge Dr, Sandy Springs, GA 30328
CSS- 6 | TS116 | Dunwoody Club Drive at Jett Ferry Road (Concept) | Tier 1 | Operation and Safety Improvements | TSPLOST | Sandy Springs | Completed | Construction of a new traffic signal (or roundabout) with dedicated turn lanes |  | Calyx | April, 2019 | May, 2017 |  |  |  | Sales Tax | $0 | $0 | $0 | Green | Green | Inactive | ajohnson@sandyspringsga.gov |  | 2022-05-26 17:59:34
CSS- 60 | S2177 | Powers Ferry Road (New Northside Drive to 6201 Powers Ferry Road) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Powers Ferry Road (New Northside Drive to 6201 Powers Ferry Road) | Vertical Earth | NV5 | September, 2023 | December, 2022 | February, 2025 | December, 2024 |  | Sales Tax | $385,000 | $278,960 | $106,040 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2025 | 2025-06-18 16:23:24 |  | 6201 Powers Ferry Rd NW, Sandy Springs, GA 30339
CSS- 61 | S2179 | Spalding Drive (Nesbit Ferry to Spalding Lake Court) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Spalding Drive (Nesbit Ferry to Spalding Lake Court) | Zaveri | Heath & Lineback | November, 2024 | December, 2022 | April, 2025 | March, 2025 |  | Sales Tax | $550,000 | $325,489 | $224,511 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2025 | 2025-07-17 14:23:02 |  | 5040 Spalding Dr, Sandy Springs, GA 30350
CSS- 62 | S2168 | Hilderbrand Police gym to Roswell Road (both sides) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Hilderbrand Police gym to Roswell Road (both sides) | Zaveri | NV5 | February, 2025 | December, 2022 | August, 2025 | July, 2025 |  | Sales Tax | $520,000 | $442,270 | $77,730 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2025 | 2025-12-11 08:39:33 |  | 218 Hilderbrand Dr, Atlanta, GA 30328
CSS- 63 | S2163 | Northland Drive (Landmark Drive to Ex. SW at Northland Ridge Trail) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Northland Drive (Landmark Drive to Ex. SW at Northland Ridge Trail) | Construction 57 | Heath & Lineback | April, 2024 | December, 2022 | November, 2024 | October, 2024 |  | Sales Tax | $195,000 | $176,156 | $18,844 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2024 | 2025-06-18 16:19:56 |  | 4906 Northland Dr, Atlanta, GA 30342
CSS- 64 | S2164 | Evergreen Drive Sidewalk (Ex SW at Greenwood Close to PDR) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Evergreen Drive Sidewalk (Ex SW at Greenwood Close to PDR) | Sol Construction | Heath & Lineback | January, 2025 | December, 2022 | December, 2025 | November, 2025 |  | Sales Tax | $355,000 | $261,698 | $93,302 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2025 | 2026-03-06 15:41:06 |  | 3503 Evergreen Dr NE, Atlanta, GA 30319
CSS- 65 | S2186 | Mt. Paran Road and Powers Ferry Road (Rebel Trail to Carol Lane) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Bidding | Mt. Paran Road and Powers Ferry Road (Rebel Trail to Carol Lane) |  | Kimley Horn | December, 2025 | January, 2023 | February, 2027 | February, 2027 |  | Sales Tax | $2,400,000 | $272,558 | $2,127,442 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2027 | 2026-03-06 15:46:32 |  | 385 Mt Paran Rd NW, Atlanta, GA 30327
CSS- 66 | S2183 | Lake Forrest Drive (Mt. Paran Road to Long Island Drive) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Design | Lake Forrest Drive (Mt. Paran Road to Long Island Drive) |  | Kimley Horn |  | January, 2023 |  |  |  | Sales Tax | $790,000 | $0 | $790,000 | Green |  | Inactive | ajohnson@sandyspringsga.gov |  | 2024-07-22 13:48:25 |  | 5060 Lake Forrest Dr NW, Sandy Springs, GA 30342
CSS- 67 | S2184 | Jett Ferry Road/Spalding Drive (Jett Ferry Court to Dunvegan Close) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Construction | Jett Ferry Road/Spalding Drive (Jett Ferry Court to Dunvegan Close) | Sol Construction | Kimley Horn | June, 2026 | December, 2021 | September, 2026 | September, 2026 |  | Sales Tax | $700,000 | $148,431 | $551,569 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2026 | 2026-03-06 15:44:03 |  | 3245 Spalding Dr, Sandy Springs, GA 30350
CSS- 68 | S2171 | Dalrymple Road (Duncourtney to Glencourtney Drive to 605 Dalrymple Road) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Planning | Dalrymple Road (Duncourtney to Glencourtney Drive to 605 Dalrymple Road) | [7 empty] | Sales Tax | $0 | $0 | $0 | Green |  | Active | ajohnson@sandyspringsga.gov |  | 2024-05-20 14:50:43 |  | 471 Dalrymple Rd, Sandy Springs, GA 30328
CSS- 69 | S2174 | Long Island Drive @ 5910 Gap Fill | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Planning | Long Island Drive @ 5910 Gap Fill | [7 empty] | Sales Tax | $0 | $0 | $0 | Green |  | Active | ajohnson@sandyspringsga.gov |  | 2024-05-20 14:51:28 |  | 5910 Long Island Dr, Sandy Springs, GA 30328
CSS- 7 | TS109 | Peachtree-Dunwoody Road at Windsor Parkway | Tier 1 | Operation and Safety Improvements | TSPLOST | Sandy Springs | Completed | Add and extend SB left-turn lane and WB right-turn lane |  | Clark Patterson Lee | February, 2021 | August, 2018 | September, 2021 | August, 2021 |  | Sales Tax | $0 | $0 | $0 | Green | Green | Inactive | ajohnson@sandyspringsga.gov | 2021 | 2022-05-26 17:54:22
CSS- 70 | S2169 | Carpenter Drive @ 345 Carpenter Dr | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Planning | Carpenter Drive @ 345 Carpenter Dr |  |  |  | December, 2022 |  |  |  | Sales Tax | $0 | $0 | $0 | Green |  | Active | ajohnson@sandyspringsga.gov |  | 2024-05-20 14:49:38 |  | 345 Carpenter Dr NE,Sandy Springs, GA 30328
CSS- 71 | S2188-2 | South Johnson Ferry Road at Brookhaven City Limit | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | This project will add a sidewalk and sidewalk ramp at the northeast corner of the intersection and a sidewalk extension with ramp on along the south side of Allen Road that will connect to the existing crosswalk across Allen Road. | Blount Construction | NV5 |  | January, 2023 | November, 2023 | November, 2023 |  | Sales Tax | $65,000 | $254,017 | $-189,017 |  |  | Active | ajohnson@sandyspringsga.gov | 2023 | 2026-03-06 15:44:54 |  | 1531 Johnson Ferry Rd NE, Sandy Springs, GA 30319
CSS- 72 | S2188-3 | Glenridge Drive at Messina Way | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | This sidewalk will provide a connection between the existing sidewalk at Spalding Trace to Messina Way | Blount Construction | NV5 |  | January, 2023 | March, 2024 | March, 2024 |  | Sales Tax | $65,000 | $19,225 | $45,775 | Green |  | Active | ajohnson@sandyspringsga.gov | 2024 | 2024-03-29 14:20:18 |  | 7001 Glenridge Dr, Sandy Springs, GA 30328
CSS- 73 | S2188-4 | River Exchange Drive Sidewalk | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | The project will add 10'-wide sidepath along the west side of River Exchange Dr. from Spalding Dr. North to the entrance of Crooked Creek Park. The project will also provide 6'-wide sidewalk from the entrance of Crooked Creek Park north to tie into existing sidewalk. | Sol Construction | NV5 | September, 2023 | January, 2023 | July, 2024 | June, 2024 | Sandy Springs | Sales Tax | $165,000 | $150,324 | $14,676 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2024 | 2024-06-21 15:10:43 | Georgia | 3101 River Exchange Dr, Sandy Springs
CSS- 74 | S2188-5 | Windsor Parkway, YMCA to Peachtree Dunwoody Road | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | The project will add 525 LF of sidewalk to the north side of Windsor Parkway from the intersection of Peachtree Dunwoody Road to the YMCA entrance |  | NV5 | September, 2023 | January, 2023 | July, 2024 | June, 2024 |  | Sales Tax | $205,000 | $133,136 | $71,864 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2024 | 2024-06-21 15:11:12 | Georgia | 940 Windsor Pkwy, Sandy Springs, GA 30342
CSS- 75 | S2187 | Brandon Mill Road - Lost Forest Dr. to Brandon Ridge Dr. | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Construction of a sidewalk system on east side of Brandon Mill Road from Lost Forest Drive to Brandon Ridge Dr | Backbone | NV5 | October, 2021 | December, 2019 | December, 2025 | December, 2025 |  | Sales Tax | $1,890,000 | $1,673,016 | $216,984 |  |  | Active | ajohnson@sandyspringsga.gov | 2025 | 2026-03-06 15:47:16
CSS- 76 | S2185-1 | Lake Forrest Sidewalk Phase 1 | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Lake Forest Sidewalk from south of Pine Lake Drive to Mt Paran Road | Excellere | Kimley Horn | March, 2025 | January, 2023 | December, 2025 | December, 2025 |  | Sales Tax | $272,700 | $269,918 | $2,782 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2025 | 2026-03-06 15:44:29
CSS- 8 | TS110 | Mount Paran Road at Powers Ferry Road | Tier 1 | Operation and Safety Improvements | TSPLOST | Sandy Springs | Completed | Roundabout Design |  | Arcadis | December, 2019 | June, 2017 |  |  |  | Sales Tax | $346,739 | $346,739 | $0 | Green | Green | Inactive | ajohnson@sandyspringsga.gov |  | 2022-07-29 17:53:15
CSS- 9 | TS111 | Spalding Drive at Pitts Road | Tier 1 | Operation and Safety Improvements | TSPLOST | Sandy Springs | Completed | Construction of NB and EB dedicated left turn lanes. | Vertical Earth | Kimley-Horn and Associates | December, 2021 | October, 2017 | March, 2025 | January, 2025 |  | Sales Tax | $4,318,179 | $4,400,534 | $-82,355 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2025 | 2025-12-11 08:48:35
EP- 10 | EP-178 | Headland Drive Sidewalks | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | East Point | Completed | Construction Complete. Pedestrian/Bike Improvements Projects in City of East Point - Headland Drive (City of Atlanta to Kimmeridge Drive). Combined With EP-179 | Autaco Development | Foresite Group | March, 2021 | December, 2021 | May, 2024 | May, 2024 |  | Sales Tax | $291,439,120 | $291,439,120 | $0 | Red | Green | Active | chall@eastpointcity.org | 2018 | 2024-11-07 14:44:12 | Georgai | Headland Dr and Delowe Dr | 2024-06-11
EP- 11 | EP-179 | Headland and Delowe Intersection | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | East Point | Completed | Pedestrian/Bike/Landscape/Streetscape Projects in City of East Point - Delowe Drive (Washington Rd to SR 166) The last phase of the project included in the Delowe Drive / Headland Drive Intersection Upgrade. |  | Foresite Group | March, 2021 | January, 2022 | December, 2021 | November, 2021 |  | Sales Tax | $1,122,644 | $825,000 | $297,644 | Green | Green | Active | chall@eastpointcity.org | 2021 | 2024-11-07 14:45:56
EP- 12 | EP-180 | EP PATH Master Trail System | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | East Point | Completed | Pedestrian/Bike Projects in City of East Point - Master Trail System | Lewallen |  | August, 2018 | February, 2019 | July, 2020 | June, 2020 |  | Sales Tax | $2,949,652 | $2,949,652 | $0 | Green | Green | Active | chall@eastpointcity.org | 2018 | 2021-10-13 15:15:06
EP- 13 | EP-181 | Ale Circle Realignment | Tier 1 | Operation and Safety Improvements | TSPLOST | East Point | Construction | This is a combined projects: EP-181, EP-182 and EP-326 EP-181 $200,000 EP- 182 $550,000 EP-326 $1,100,000 Total project cost $1,850,000 | Construction 57 | Lowe Engineers | June, 2021 | August, 2021 | January, 2025 | December, 2024 |  | Sales Tax | $2,000,000 | $200,000 | $1,800,000 | Red | Yellow | Active | chall@eastpointcity.org | 2019 | 2024-11-07 14:48:16
EP- 14 | EP-182 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | East Point | Land | Operations and Safety in City of East Point - Ale Circle at Washington Road Intersection Improvements This project is a combined solicitation EP-181, EP182 and EP-326 Project total 1,850,000 EP-181 $200,000 EP-182 $550,000 EP 326 $1,100,000 | [7 empty] | Sales Tax | $550,000 | $100,000 | $450,000 | Green | Red | Active | JREEVES@EASTPOINTCITY.ORG | 2019 | 2021-02-01 23:59:28
EP- 15 | EP-183 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | East Point | Completed | Sidewalks |  |  | August, 2021 | October, 2021 | August, 2022 | April, 2022 |  | Sales Tax | $712,500 | $17,750 | $694,750 | Green | Green | Active | chall@eastpointcity.org | 2020 | 2024-11-07 14:49:00
EP- 16 | EP-184 | Quick Response Projects | Tier 1 | Quick Response | TSPLOST | East Point | Planning | Quick Response Projects in City of East Point | [7 empty] | Sales Tax | $873,355 | $0 | $873,355 | Gray | Gray | Active | guest |  | 2021-05-05 00:42:20
EP- 17 | EP-201 | Maintenance and Safety Enhancements | Tier 2 | Maintenance and Safety Enhancements | TSPLOST | East Point | Planning | Maintenance and Safety Enhancements in City of East Point -Resurfacing | [7 empty] | Sales Tax | $4,408,500 | $0 | $4,408,500 | Gray | Gray | Active | JREEVES@EASTPOINTCITY.ORG |  | 2021-02-01 23:41:15
EP- 18 | EP-214 | Pedestrian/Bike Projects | Tier 2 | Pedestrian and Bike Improvements | TSPLOST | East Point | Planning | Pedestrian/Bike/Landscape Projects in City of East Point - Dobbs Way (Washington Rd to Ben Hill Rd) | [7 empty] | Sales Tax | $210,000 | $0 | $210,000 | Gray | Gray | Active | JREEVES@EASTPOINTCITY.ORG |  | 2021-02-01 23:39:53
EP- 19 | EP-215 | Pedestrian/Bike Projects | Tier 2 | Pedestrian and Bike Improvements | TSPLOST | East Point | Land | Pedestrian/Bike Projects in City of East Point - Redwine Road (City of Atlanta to North Commerce Drive) This is a combined project EP-215 and EP-325 EP-215 $218,000 EP- 325 $350,000 Total project cost $568,000 |  |  | February, 2020 | August, 2021 | April, 2022 | December, 2021 |  | Sales Tax | $218,000 | $22,132 | $195,868 | Green | Yellow | Active | JREEVES@EASTPOINTCITY.ORG | 2020 | 2021-02-01 23:51:26
EP- 2 | EP-159 | Desert Drive Resurfacing and Sidewalk | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | East Point | Completed | Road resurfacing and new sidewalk installation. Desert Drive between Camp Creek Pkwy and Washington Road. | Mullins Brothers, Inc |  | July, 2018 | May, 2018 | July, 2018 | June, 2019 | http://www.eastpointcity.org | Sales Tax | $500,000 | $414,077 | $85,923 | Green | Green | Active | guest | 2018 | 2021-05-05 00:22:37
EP- 20 | EP-216 | Ben Hill Rd (South) Sidewalks and Traffic Calming | Tier 1 | Operation and Safety Improvements | TSPLOST | East Point | Construction | Ben Hill Road (Will Lee Road to Unincorporated Fulton County) Traffic Calming and sidewalks | Sol Construction, LLC | Southeastern Engineers | June, 2021 | October, 2021 | February, 2022 | February, 2022 | www.eastpointcity.org | Sales Tax | $712,500 | $441,074 | $271,426 | Green | Green | Active | guest | 2021 | 2021-10-11 22:23:41
EP- 21 | EP-303 | Maintenance and Safety Enhancements | Tier 3 | Maintenance and Safety Enhancements | TSPLOST | East Point | Planning | Maintenance and Safety Enhancements in City of East Point - Resurfacing | [7 empty] | Sales Tax | $3,375,976 | $0 | $3,375,976 | Gray | Gray | Active | JREEVES@EASTPOINTCITY.ORG |  | 2021-02-01 23:48:26
EP- 22 | EP-324 | Operations and Safety | Tier 3 | Operation and Safety Improvements | TSPLOST | East Point | Design | Operations and Safety in City of East Point - Janice Drive at Washington Road Intersection Improvements |  | Atkins | March, 2021 | December, 2021 | April, 2022 | February, 2022 |  | Sales Tax | $250,000 | $0 | $250,000 | Green | Green | Active | guest | 2021 | 2021-05-05 00:44:19
EP- 23 | EP-325 | Operations and Safety | Tier 3 | Operation and Safety Improvements | TSPLOST | East Point | Land | Operations and Safety in City of East Point - North Commerce Drive at Redwine Road Intersection Improvements Construction. This is a combined project EP-215 and EP-325 EP-215 $218,000 EP- 325 $350,000 Total project cost $568,000 |  |  | April, 2021 | October, 2021 | February, 2022 | January, 2022 |  | Sales Tax | $350,000 | $50,000 | $300,000 | Green | Red | Active | JREEVES@EASTPOINTCITY.ORG | 2019 | 2021-02-02 00:00:09
EP- 24 | EP-326 | Operations and Safety | Tier 3 | Operation and Safety Improvements | TSPLOST | East Point | Concept | Operations and Safety in City of East Point - North Desert Drive Extension to Ale Circle - Intersection Improvements This is a combined projects: EP-181, EP-182 and EP-326 EP-181 $200,000 EP- 182 $550,000 EP-326 $1,100,000 Total project cost $1,850,000 |  |  | February, 2020 | February, 2019 | April, 2022 | December, 2021 |  | Sales Tax | $1,100,000 | $25,000 | $1,075,000 | Gray | Gray | Active | guest | 2019 | 2021-05-05 00:47:26
EP- 25 | EP-112 | Bobby Brown | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | East Point | Completed | Road resurfacing safety enhancement |  |  |  | July, 2017 | September, 2017 | September, 2017 |  | Sales Tax | $320,000 | $320,000 | $0 | Green | Green | Active | guest | 2017 | 2021-05-05 00:45:58
EP- 26 | EP-122 | Norman Berry Drive | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | East Point | Completed | Road resurfacing and safety | Baldwin Paving |  | August, 2019 | August, 2017 | August, 2017 | September, 2017 |  | TSPLOST | $200,000 | $200,000 | $0 | Green | Green | Active | guest | 2017 | 2021-05-05 00:47:05
EP- 27 | EP-130 | Willingham Drive | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | East Point | Completed | Roadway resurfacing and Safety | Mullins Brother's Paving |  | April, 2017 | September, 2017 | September, 2017 | December, 2019 |  | TSPLOST | $651,000 | $651,000 | $0 | Green | Green | Active | guest | 2017 | 2021-05-05 00:48:38
EP- 28 | EP-131 | Arrowood Drive | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | East Point | Completed | Road resurfacing and safety | Mullins Brothers |  | April, 2018 |  | August, 2018 | August, 2018 |  | TSPLOST | $417,000 | $417,000 | $0 | Green | Green | Active | guest | 2018 | 2021-05-05 00:49:21
EP- 29 | EP-149 | Tyewood Lane | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | East Point | Completed | Road resurfacing and safety | Mullin's Brother's Paving |  |  | August, 2018 | August, 2018 | August, 2018 |  | Sales Tax | $58,000 | $58,000 | $0 | Green | Green | Active | guest | 2018 | 2021-05-05 00:50:49
EP- 3 | EP-123 | Oakleigh Drive Improvements | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | East Point | Completed | This project within an industrial warehouse district, consisting of road resurfacing and new sidewalk installation. | BRTU Construction |  |  | May, 2018 | August, 2018 | July, 2018 | http://www.eastpointcity.org | Sales Tax | $1,300,000 | $1,300,000 | $0 | Green | Green | Active | guest | 2018 | 2021-05-05 00:22:20
EP- 30 | EP-150 | Waleska Way | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | East Point | Completed | Road resurfacing and safety | Mullins Brothers Paving |  | April, 2018 | August, 2018 | August, 2018 |  |  | Sales Tax | $121,400 | $121,400 | $0 | Green | Green | Active | guest | 2018 | 2021-05-05 00:51:17
EP- 31 |  | Resurfacing | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of East Point | 2022-03-31
EP- 32 |  | East Point Path #2 | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of East Point | 2022-03-31
EP- 33 |  | City Wide | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of East Point | 2022-03-31
EP- 34 |  | City Wide | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of East Point | 2022-03-31
EP- 35 |  | Sylvan Rd Sidewalk (Cleveland Ave to City Limits - Hapeville) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Sylvan Rd | 2022-03-31
EP- 36 |  | Sylvan Rd Sidewalk (Winburn Rd to City Limits - Atlanta) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Sylvan Rd | 2022-03-31
EP- 37 |  | Dodson Dr (Earl Godfrey Cir to Hogan Rd) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Dodson Dr | 2022-03-31
EP- 38 |  | N. Commerce Dr Sidewalk (Shelby Ln to Redwine Rd) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | N. Commerce Dr | 2022-03-31
EP- 39 |  | Dodson Dr Connector (Washington Rd to Stone Rd) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Dodson Dr | 2022-03-31
EP- 4 | EP-004 | Ale Circle Realignment and Desert Drive N Extension | Tier 1 | Operation and Safety Improvements | TSPLOST | East Point | Land | The project is in "Land Acquisition and Environmental Permitting" and the purpose of this project is to reduce traffic and safety issue at the intersection of Washington Road & Camp Creek Pkwy. |  | Lowe Engineers | June, 2018 | January, 2022 | November, 2022 | November, 2022 | http://www.eastpointcity.org | Sales Tax | $1,850,000 | $176,000 | $1,674,000 | Green | Red | Active | guest | 2018 | 2021-10-11 22:05:54
EP- 40 |  | City Wide ITS Enhancements | Tier 1 | Operation and Safety Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of East Point | 2022-03-31
EP- 41 |  | Headland Terrace Bike and Pedestrian Improvements | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Headland Terrace | 2022-03-31
EP- 42 |  | Welcome All Rd Intersection Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of East Point | 2022-03-31
EP- 43 |  | Janice Dr Intersection Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Janice Dr | 2022-03-31
EP- 44 |  | Resurfacing | Tier 2 | Maintenance and Safety Enhancements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of East Point | 2022-03-31
EP- 45 |  | N. Commerce Dr @ Centre Pkwy Intersection Improvement | Tier 1 | Operation and Safety Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | N. Commerce Dr | 2022-03-31
EP- 46 |  | Washington Rd @ Taylor Intersection Improvement | Tier 1 | Operation and Safety Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Washington Rd | 2022-03-31
EP- 47 |  | North Desert Drive Extension - Phase II | Tier 2 | Operation and Safety Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | North Desert Drive | 2022-03-31
EP- 48 |  | Resurfacing | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of East Point | 2022-03-31
EP- 49 |  | EP PATH - Phase 3 | Tier 3 | Pedestrian and Bike Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of East Point | 2022-03-31
EP- 5 | EP-177 | Washington Road Sidewalk | Tier 1 | Pedestrian Improvements | TSPLOST | East Point | Construction | The Project was bid Out for Construction. The lowest apparent bidder was DAF Concrete. Project is for new installation of sidewalk along the Washington Road corridor from I-285 to Delowe Drive. | DAF Concrete, LLC | Moreland Altobelli (ATLAS) | June, 2018 | June, 2021 | June, 2022 | June, 2022 | http://www.eastpointcity.org | Sales Tax | $1,993,420 | $322,000 | $1,671,420 | Green | Green | Active | Cadell Hall | 2021 | 2021-10-11 22:09:50
EP- 50 |  | N. Desert Dr Sidewalk (Camp Creek Pkwy to Redwine Rd) | Tier 3 | Pedestrian and Bike Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | North Desert Drive | 2022-03-31
EP- 51 |  | City Wide | Tier 3 | Operation and Safety Improvements | TSPLOST2 | East Point | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of East Point | 2022-03-31
EP- 6 | EP-325 | N Commerce Dr @ Redwine Rd improvements | Tier 1 | Operation and Safety Improvements | TSPLOST | East Point | Land | The project is in "Land Acquisition". The propose of the project is intersection safety and improvements, Engineering Design and Land Acquisition. |  | Moreland Altobelli (ATLAS) | June, 2020 | January, 2022 | December, 2022 | December, 2022 | http://www.eastpointcity.org | Sales Tax | $350,000 | $63,225 | $286,775 | Green | Red | Active | guest | 2021 | 2021-10-11 22:21:13
EP- 7 | EP-176 | Ben HIll Sidewalk | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | East Point | Design | The plan is to design new sidewalk installation and road enhancement with Intersection improvements. |  | Prime Engineering | April, 2021 | October, 2021 | February, 2022 | December, 2021 | http://www.eastpointcity.org | Sales Tax | $1,160,000 | $274,467 | $885,533 | Green | Green | Active | guest | 2020 | 2021-08-17 20:30:14
EP- 8 | EP-006 | Dodson Drive Resurfacing | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | East Point | Completed | The project is in design for roadway resurfacing. The projects listed below were grouped together for solicitation: EP-152 $190,000; EP-133 $419,667; EP-132 $26,000; EP-136 $189,000; EP-153 $174,500; EP-154 $52,800; EP-155 $248,000 EP-156 $311,500 EP-157 $84,500 EP-135 $32,000 EP-137 $120,000 EP-138 $405,000 EP-144 $65,000 EP-147 $442,700 EP-160 $341,500 EP-162 $41,500 EP-168 $82,500 EP-148 $116,000 EP-173 $51,000 EP-175 $296,000 EP-140 $300,000 EP-151 $280,000 EP-304 $385,000 EP-103 $336,667 EP-106 $393,333 | Mullin's Brothers Paving | Griffin & Davis Consulting | June, 2018 | February, 2020 | November, 2020 | December, 2020 | http://www.eastpointcity.org | Sales Tax | $5,384,167 | $5,384,167 | $0 | Green | Green | Active | guest | 2020 | 2021-10-11 22:24:39
EP- 9 | EP-101 | Bonnybrooke Way Resurfacing | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | East Point | Completed | Maintenance and Safety Enhancements in City of East Point -Resurfacing. Bonnybrooke Way (see EP - 006) | Mullin's Brothers Paving | Griffin & Davis Consulting | January, 2020 | April, 2020 | November, 2020 | November, 2020 |  | Sales Tax | $103,000 | $10,300 | $92,700 | Green | Green | Active | guest | 2020 | 2021-08-17 20:28:26
FA- 10 |  | E. Broad Street & E. Malone Street Pedestrian Improvements Project | Tier 2 | Pedestrian and Bike Improvements | TSPLOST | Fairburn | Completed | Pedestrian Improvements on E. Broad Street & E. Malone Street near Landmark Christain School. | BOSS Concrete | Design-Build | April, 2018 | August, 2018 | November, 2018 | October, 2018 |  | Sales Tax | $32,354 | $32,354 | $0 | Green | Green | Active | anthony.belcher@fairburn.com | 2018 | 2025-08-01 07:44:59 | GA | E. Broad St.
FA- 11 | 18-011 | Renaissance Parkway Extension Project | Tier 3 | Congestion Relief | TSPLOST | Fairburn | Completed | Renaissance Parkway Roadway Extension Roadway project designed to provide congestiion relief to SR 74/Senoia Road. | AMCON Construction | Harris-Gray, LLC | August, 2018 | March, 2019 | December, 2019 | November, 2019 |  | Sales Tax | $87,611 | $87,611 | $0 | Green | Green | Active | lthompson@fairburn.com | 2019 | 2021-09-08 19:24:28
FA- 12 | 19-002 | Roadway Improvements on Various City Roads Project | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fairburn | Completed | City-Wide Resurfacing, 2019 Roadway Improvements on Various City Roads Project | Shepco Paving, Inc. | In-House | June, 2023 | August, 2019 | December, 2019 | December, 2019 |  | Sales Tax | $544,894 | $463,461 | $81,433 | Green | Green | Active | lthompson@fairburn.com | 2019 | 2020-12-17 13:31:23
FA- 13 | 20-004 | Howell Avenue Extension Roadway Project | Tier 1 | Roadway Projects | TSPLOST | Fairburn | Completed | T-SPLOST Roadway Project designed to provide connectivity between Bohannon Road and SR74/Senoia Road, an alternative route for motorists (trucks), and to open up parcels for future development. | Strack Incorporated | Southeastern Engineering. Inc. | May, 2020 | July, 2020 | July, 2021 | June, 2021 |  | Sales Tax | $4,543,122 | $1,872,795 | $2,670,327 | Green | Green | Active | lthompson@fairburn.com | 2020 | 2021-09-08 19:59:14
FA- 14 | 20-002 | Roadway Improvements on Various City Roads Project | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fairburn | Completed | 2020 City-Wide Resurfacing, Roadway Improvements Project | C.W.Matthews | In-House | March, 2020 | July, 2020 | December, 2020 | November, 2020 |  | Sales Tax | $1,157,670 | $694,620 | $463,050 | Green | Green | Active | lthompson@fairburn.com | 2020 | 2020-12-17 20:18:13
FA- 15 | 25-004 | Park Road Extension Project | Tier 1 | Roadway Projects | TSPLOST | Fairburn | Bidding | Extension of Park Road to provide a secondary entrance/exit into Clarence Duncan Park. |  | Southeastern Engineering, Inc. | April, 2025 |  |  |  |  | Sales Tax | $722,685 | $0 | $722,685 | Gray | Gray | Active | anthony.belcher@fairburn.com | 2024 | 2025-08-01 15:10:45 | GA
FA- 16 | 21-001 | Oakley Industrial Boulevard Full-Depth Reclamation Project Phase II | Tier 1 | Roadway Projects | TSPLOST | Fairburn | Completed | The work consists of full depth reclamation, asphalt paving and striping on Oakley Industrial Boulevard Road from the deceleration lane of the Solstice Apartment Complex to SR 74 as the base bid. In addition, (Add Alternate #1) Oakley Industrial Boulevard (from SR 74 to SR 92), (Add Alternate #2) Oakley Industrial Boulevard (from SR 92 to Fayetteville Road), (Add Alternate #4) Oakley Industrial Boulevard (from just west of Bohannon Road to Creekwood Road). | C.W.Matthews | Moreland Altobelli Associates, LLC | December, 2020 | July, 2021 | March, 2022 | October, 2021 |  | Sales Tax | $2,609,883 | $1,191,210 | $1,418,673 | Green | Green | Active | lthompson@fairburn.com | 2021 | 2023-03-08 15:55:42
FA- 17 | 23-003 | Rivertown Connector Project | Tier 1 | Roadway Projects | TSPLOST | Fairburn | Bidding | City of Fairburn Roadway Project design to provide connectivity between Rivertown Road and Virlyn B. Smith Road. |  | SOUTHEASTERN ENGINEERING INC. | April, 2025 | May, 2025 | August, 2025 | July, 2025 |  | Sales Tax | $937,240 | $0 | $937,240 | Gray | Gray | Active | anthony.belcher@fairburn.com | 2020 | 2025-05-01 11:30:19
FA- 18 |  | SR 14/Senoia Road Traffic Signal Project | Tier 1 | Quick Response | TSPLOST | Fairburn | Planning | Operation and Safety Improvements in City of Fairburn - To Be Determined |  | Southeastern Engineering. Inc. | [5 empty] | Sales Tax | $200,000 | $0 | $200,000 | Gray | Gray | Active | lthompson@fairburn.com | 2020 | 2020-12-17 20:37:37
FA- 19 | 20-005 | Bohannon Road Sidewalk Project | Tier 2 | Pedestrian and Bike Improvements | TSPLOST | Fairburn | Completed | Pedestrian Improvements project designed to provide workers in the area a safe route to and from work. | The Corbett Group | Moreland Altobelli Associates, LLC | April, 2020 | July, 2020 | December, 2020 | November, 2020 |  | Sales Tax | $234,488 | $23,862 | $210,626 | Green |  | Active | lthompson@fairburn.com | 2020 | 2021-09-08 19:41:40
FA- 20 |  | Quiet Zone R/R Crossings Project | Tier 2 | Operation and Safety Improvements | TSPLOST | Fairburn | Planning | Quiet Zone Railroad Crossings Project | [7 empty] | Sales Tax | $750,000 | $0 | $750,000 | Gray | Gray | Active | lthompson@fairburn.com | 2020
FA- 21 | 20-001 | Pedestrian Improvements on Various City Roads | Tier 2 | Pedestrian and Bike Improvements | TSPLOST | Fairburn | Completed | 2020 TSPLOST Pedestrian Improvements, Pedestrian Improvements on Various City Roads | Construction 57 | In-House | February, 2020 | May, 2020 | July, 2020 | June, 2020 |  | Sales Tax | $182,250 | $181,586 | $664 | Green | Green | Active | lthompson@fairburn.com | 2020 | 2020-12-17 20:45:08
FA- 22 | 21-004 | Roadway Improvements on Various City Roads Project | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fairburn | Completed | 2021 City-Wide Resurfacing | Blount Construction Company, Inc. | In-House | May, 2021 | September, 2021 | March, 2022 | December, 2021 |  | Sales Tax | $1,649,113 | $1,061,356 | $587,757 | Green | Green | Active | lthompson@fairburn.com | 2021 | 2023-03-08 16:13:32
FA- 23 |  | 2022 Roadway Improvement on Various City Roads Project | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fairburn | Completed | 2022 City-Wide Resurfacing Project. | Magnum Paving, LLC | In-House | February, 2022 | June, 2022 | October, 2022 | September, 2022 |  | Sales Tax | $1,802,279 | $1,525,031 | $277,248 | Green | Green | Active | lthompson@fairburn.com | 2022 | 2023-03-08 16:31:05
FA- 24 |  | Quick Response Project | Tier 3 | Quick Response | TSPLOST | Fairburn | Planning | Quick Response Project | [7 empty] | Sales Tax | $41,417 | $0 | $41,417 | Gray | Gray | Active | lthompson@fairburn.com
FA- 25 | 20-003 | Dodd Street Pedestrian Improvements | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fairburn | Completed | Streetscape project on Dodd Street in the Lightning Neighborhood. The work includes the removal of existing header curb, installation of new header curb, installation of new sidewalk, replacement of existing sidewalk as required, installation of new ADA handicap ramps, the replacement of existing handicap ramps as required, and the installation of concrete sidewalk-header curb-retaining wall combination as required. The scope of the Add Alternate includes milling, asphalt paving, the installation of traffic-print textured paving crosswalks, manhole adjustments and associated tasks. *It is important to note that TSPLOST dollars were spent on the Add-Alternate only. | The Corbett Group | In-House | April, 2020 | June, 2020 | December, 2020 | November, 2020 |  | Sales Tax | $409,659 | $31,449 | $378,210 | Green | Green | Active | lthompson@fairburn.com | 2020 | 2021-09-09 11:53:10
FA- 26 |  | Milo Fisher, Bay Street & Grant Street Pedestrian Improvements | Tier 2 | Pedestrian and Bike Improvements | TSPLOST | Fairburn | Completed | Extend sidewalk on Milo Fisher to the intersection of Clayton Street, extend sidewalk on Bay Street to the intersection of Malone Street, install sidewalk on Grant street from Milo Fisher Street to Chestnut Street. | BOSS Concrete Construction, LLC |  | March, 2021 | April, 2021 | June, 2021 | May, 2021 |  | Sales Tax | $25,000 | $19,977 | $5,023 | Green | Green | Active | lthompson@fairburn.com | 2021 | 2021-09-09 11:55:01
FA- 27 | 25-004 | City Wide Road Resurfacing | Tier 1 | Roadway Projects | TSPLOST2 | Fairburn | Construction | The City of Fairburn will accept sealed bids from qualified Contractors for furnishing all labor, equipment, and materials necessary to complete 4.1 mi of Roadway Improvements ON VARIOUS CITY ROADS Contract #25-004. The work includes milling, temporary traffic control, asphalt paving, manhole adjustments and associated tasks. The scope of Add Alternate #1 consists of the paving of the VETERANS OF FOREIGN WARS (VFW) parking lot located at 1699 Park Rd. Fairburn, GA 30213. All work must be completed within one hundred and twenty (120) calendar days of the Notice to Proceed (NTP). | TRIPLE R CONSTRUCTION | In-house | June, 2025 | July, 2025 | November, 2025 | October, 2025 | Fairburn | Sales Tax | $1,688,078 | $0 | $1,688,078 | Green | Green | Active | anthony.belcher@fairburn.com | 2025 | 2025-08-01 13:45:39 | Georgia | City of Fairburn | 2022-03-31
FA- 28 | 23-002 | SOUTHEAST BROAD STREET PEDESTRIAN IMPROVEMENTS PROJECT | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Fairburn | Completed | SOUTHEAST BROAD STREET PEDESTRIAN IMPROVEMENTS PROJECT #23-002. The work includes the removal of existing curb & gutter, sidewalk and driveway aprons as required, installation of new curb & gutter, installation of new sidewalk, replacement of existing sidewalk as required, installation of new driveway aprons, and the installation of new ADA handicap ramps. The contract will also include preparation of sub-grade, saw-cutting and demolition of existing asphalt and concrete, as well as clean up and backfilling. | The Corbet Group | Atlas Technical Consultants |  |  |  |  | Fairburn | Sales Tax | $678,277 | $610,405 | $67,872 | Green | Green | Inactive | anthony.belcher@fairburn.com | 2023 | 2025-07-31 14:01:15 | Georgia |  | 2022-03-31
FA- 29 |  | Pedestrian and Bike Improvements (Phase 1) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Fairburn | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Fairburn | 2022-03-31
FA- 3 | 17-005 | Roadway Improvements on Various City Roads Project | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fairburn | Completed | City-Wide Resurfacing. The project includes milling, temporary traffic control, asphalt paving, thermoplastic striping, manhole adjustments and associated tasks. Our strategy was to use 2017-2018 TSPLOST funds to focus our resurfacing efforts on the heart of the City (downtown) and extend future efforts to its extremities. In doing so, the implementation of the Downtown LCI Project, would have a more meaningful impact on the revitalization of FairburnÆs Historic Downtown. | E.R. Snell Contractor, Inc. | In-House | June, 2017 | November, 2017 | December, 2018 | October, 2018 |  | Sales Tax | $1,200,000 | $968,367 | $231,633 | Green | Green | Active | lthompson@fairburn.com | 2017
FA- 30 | 25-011 | Oakley Industrial Boulevard Left Turn Lane Project | Tier 1 | Roadway Projects | TSPLOST2 | Fairburn | Bidding | The widening of 0.299 mi of a left turn lane for Oakley Industrial Boulevard at entrance of the SC Johnson's distribution enter. | PIEDMONT PAVING | Atlas Technical Consultants | July, 2025 | August, 2025 | January, 2026 | December, 2025 | Fairburn | Sales Tax | $1,315,248 | $0 | $1,315,248 | Green | Green | Active | anthony.belcher@fairburn.com | 2025 | 2025-08-01 14:35:20 | Georgia | Oakley Industrial Boulevard | 2022-03-31
FA- 31 | 24-009 | McLarin Road/E. Broad Street (Bohannon Road to Gullat Road) Full-Depth Reclamation | Tier 1 | Roadway Projects | TSPLOST2 | Fairburn | Completed | Full-Depth Reclamation of McLarin Road along with asphalt paving, the installation of thermoplastic striping and raised pavement markers (RPMs), and manhole and water valve adjustments. From Bohannon Rd. to Gullatt Road. | BLOUNT CONSTRUCTION | SOUTHEASTERN ENGINEERING INC. | [5 empty] | Sales Tax | $100,000 | $100,000 | $0 | Green |  | Active | lthompson@fairburn.com | 2024 | 2025-06-24 11:13:11 | Georgia | McLarin Road | 2022-03-31
FA- 32 | 24-009 | Gullatt Road Full-Depth Reclamation | Tier 1 | Roadway Projects | TSPLOST2 | Fairburn | Completed | "Full-Depth Reclamation of Gullatt Road from McLarin Road East to just west of Cleckler Road. The project also included asphalt paving, the installation of thermoplastic striping and raised pavement markers (RPMs), and manhole and water valve adjustments. The approved T-SPLOST Project List allocates $$674,612.00 of Roadway Projects funding to the Full-Depth Reclamation of Gullatt Road. Total Project cost 2,658,412.08 | BLOUNT CONSTRUCTION | SOUTHEASTERN ENGINEERING INC. | April, 2024 | July, 2024 | November, 2024 | October, 2024 |  | Sales Tax | $337,306 | $674,612 | $-337,306 | Green | Green | Active | anthony.belcher@fairburn.com | 2024 | 2025-08-04 16:36:16 | Georgia | Gullatt Road | 2022-03-31
FA- 33 |  | Quiet Zone R/R Crossings | Tier 2 | Operation and Safety Improvements | TSPLOST2 | Fairburn | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Fairburn | 2022-03-31
FA- 34 | 23-002 | Pedestrian and Bike Improvements (Phase 2) | Tier 2 | Pedestrian and Bike Improvements | TSPLOST2 | Fairburn | Completed | SOUTHEAST BROAD STREET PEDESTRIAN IMPROVEMENTS PROJECT #23-002. The work includes the removal of existing curb & gutter, sidewalk and driveway aprons as required, installation of new curb & gutter, installation of new sidewalk, replacement of existing sidewalk as required, installation of new driveway aprons, and the installation of new ADA handicap ramps. The contract will also include preparation of sub-grade, saw-cutting and demolition of existing asphalt and concrete, as well as clean up and backfilling. | The Corbet Group | Moreland Altobelli | November, 2022 | January, 2023 | May, 2023 | April, 2023 |  | Sales Tax | $678,277 | $678,277 | $0 | Green | Green | Inactive | anthony.belcher@fairburn.com | 2023 | 2025-07-02 16:33:59 | Georgia | City of Fairburn | 2022-03-31
FA- 35 |  | City Wide | Tier 3 | Congestion Relief | TSPLOST2 | Fairburn | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Fairburn | 2022-03-31
FA- 36 |  | City Wide | Tier 3 | Operation and Safety Improvements | TSPLOST2 | Fairburn | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Fairburn | 2022-03-31
FA- 37 |  | Dodd Street Roundabout | Tier 3 | Roadway Project | TSPLOST2 | Fairburn | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Dodd Street | 2022-03-31
FA- 38 |  | Pedestrian and Bike Improvements (Phase 3) | Tier 3 | Pedestrian and Bike Improvements | TSPLOST2 | Fairburn | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Fairburn | 2022-03-31
FA- 39 |  | Oakley Industrial Boulevard Extension (Design Only) | Tier 1 | Roadway Projects | TSPLOST2 | Fairburn | Concept | The extension of Oakley Industrial Boulevard, from Creekwood Road to Gullatt Road. |  |  | June, 2025 | August, 2025 | November, 2025 | October, 2025 |  | Sales Tax | $0 | $0 | $0 | Green | Green | Active | anthony.belcher@fairburn.com |  | 2025-08-01 14:57:15 | Georgia | Oakley Industrial Boulevard | 2022-03-31
FA- 4 | 17-004 | Pedestrian Improvements on Various City Roads Project | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Fairburn | Completed | The project includes grading complete, temporary traffic control, installation of sidewalk, driveway reconstruction, installation of handicap ramps, curb & gutter installation, header curb installation and associated tasks. The is the first TSPLOST Pedestrian and Bike Improvements Project. The objective was to install new sidewalk and handicap ramps at various locations throughout the City that were currently not served with pedestrian facilities. The project also proposed connection to existing pedestrian facilities in the area. The project's purpose was to improve safety by providing a safe means for pedestrian to walk downtown to access various services and amenities. The project also provided pedestrians a safe means by which access to the newly renovated Clarence Duncan Memorial Park. | TOPLE Construction & Engineering | In-House | July, 2017 | November, 2017 | November, 2018 | November, 2018 |  | Sales Tax | $439,288 | $193,565 | $245,723 | Green | Green | Active | lthompson@fairburn.com | 2017
FA- 40 | 25-003 | MULLIS STREET PEDESTRIAN IMPROVEMENTS PROJECT | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Fairburn | Construction | The installation of a 5-foot concrete sidewalk with a 2-foot beauty strip along Mullis Street, from West Campbellton Street to Dodd Street, and from Dodd Street to Strickland Street. The project also entails the installation of pedestrian improvements on a section of Dodd Street, from Mullis Street to W. Broad Street. The work includes the removal of existing curb & gutter and header curb, and the installation of new header curb and sidewalk. This contract will also include preparation of sub-grade, saw-cutting and demolition of existing asphalt as well as clean up and backfilling. The scope of Add Alternate #1 consists of the installation of pedestrian lighting | CONSTRUCTION 57 INC. | POND ENGINEERING | March, 2025 | May, 2025 | July, 2025 | June, 2025 |  | Sales Tax | $570,201 | $570,201 | $0 | Green | Green | Active | anthony.belcher@fairburn.com | 2025 | 2025-05-06 10:21:42 | GA |  | 2025-05-06
FA- 41 | 24-009 | Cleckler Rd Full-Depth Reclamation Project | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | Fairburn | Bidding | Full-Depth Reclamation of Cleckler Road along with asphalt paving, the installation of thermoplastic striping and raised pavement markers (RPMs), and manhole and water valve adjustments. | BLOUNT CONSTRUCTION | SOUTHEASTERN ENGINEERING INC. | May, 2024 | July, 2024 | November, 2024 | October, 2024 |  | Sales Tax | $209,041 | $0 | $209,041 | Green | Green | Active | anthony.belcher@fairburn.com | 2024 | 2025-08-04 16:18:35 | GA | Cleckler Rd. | 2025-05-06
FA- 42 | 25-011 | Oakley Industrial Boulevard Left Turn Lane Project | Tier 1 | Roadway Projects | TSPLOST2 | Fairburn | Bidding | This project consists of a total of 0.299 miles of Widening on Oakley Industrial Boulevard at the entrance of SC Johnson's distribution center. | PIEDMONT PAVING | Atlas Technical Consultants | May, 2025 | July, 2025 | November, 2025 | October, 2025 | Fairburn | Sales Tax | $330,000 | $0 | $330,000 | Gray | Gray | Active | anthony.belcher@fairburn.com | 2025 | 2025-08-01 14:37:15 | Georgia | 314 NW Broad St | 2025-06-16
FA- 43 |  | BROOKS DR. EXTENSION | Tier 1 | Roadway Projects | TSPLOST2 | Fairburn | Design | Extension of 0.2 mi of Brooks Dr. |  |  | January, 2024 |  |  |  |  | Sales Tax | $100,000 | $0 | $100,000 | Green |  | Active | anthony.belcher@fairburn.com | 2025 | 2025-08-03 19:06:57 |  |  | 2025-07-31
FA- 5 | 18-002 | Oakley Industrial Boulevard Full-Depth Reclamation (FDR) Project | Tier 1 | Roadway Projects | TSPLOST | Fairburn | Completed | Full-Depth Reclamation of Oakley Industrial Boulevard, from Bohannon Road to just west of SR 74/ Senoia Road. The project also included asphalt paving, the installation of thermoplastic striping and raised pavement markers (RPMs), and manhole and water valve adjustments. The approved T-SPLOST Project List allocates $897,309 of Roadway Projects funding to the Full-Depth Reclamation of Oakley Industrial Boulevard (OIB). Since we only did approximately half of the entire project, only $448,654.50 of TSPLOST Funds were allocated to the project.. | C.W.Matthews Contracting Co., Inc. | Moreland Altobelli Associates, LLC | May, 2018 | July, 2018 | February, 2019 | January, 2019 |  | Sales Tax | $629,879 | $411,049 | $218,830 | Green | Green | Active | lthompson@fairburn.com | 2018 | 2021-09-08 19:22:03
FA- 6 | 18-002 | McLarin Road Full-Depth Reclamation Project | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fairburn | Completed | Full-Depth Reclamation of McLarin Road along with asphalt paving, the installation of thermoplastic striping and raised pavement markers (RPMs), and manhole and water valve adjustments. | C.W.Matthews Contracting Co., Inc. | Moreland Altobelli Associates, LLC | May, 2018 | July, 2018 | February, 2019 | January, 2019 |  | Sales Tax | $524,177 | $330,790 | $193,387 | Green | Green | Active | lthompson@fairburn.com | 2018
FA- 7 | 18-002 | Terminus Drive Full-Depth Reclamation Project | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fairburn | Completed | Full-Depth Reclamation of Terminus Drive along with asphalt paving, the installation of thermoplastic striping and raised pavement markers (RPMs), and the adjustment of manholes and water valves. | C.W.Matthews Contracting Co., Inc. | Moreland Altobelli Associates, LLC | May, 2018 | July, 2018 | February, 2019 | January, 2019 |  | Sales Tax | $622,226 | $341,612 | $280,614 | Green | Green | Active | lthompson@fairburn.com | 2018
FA- 8 | 18-006 | Roadway Improvements on Various City Roads Project | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fairburn | Completed | City-Wide Resurfacing. The project includes milling, temporary traffic control, asphalt paving, thermoplastic striping, manhole adjustments and associated tasks. City-Wide Resurfacing. This yearÆs project we again focused our resurfacing efforts on the heart of the City (downtown) in preparation for the implementation of Downtown LCI Project and extend future efforts to its extremities. In addition to areas in close proximity to downtown, this yearÆs project list also contains other priorities and cooperative efforts identified by Staff. The Invitation for Bid (IFB#18-006, Roadway Improvements on Various City Roads) was advertised on May 16th. The bid opening was bid opening date was June 15th, 2018 at 3:00 pm at which time the four (4) bids were opened and read aloud. After completion of the bid evaluation, it was determined that Baldwin Paving Company, Inc. was the lowest responsive and responsible bidder with a bid price of $2,289,810.12. | Baving Paving, Inc. | In-House | July, 2018 | October, 2018 | October, 2019 | April, 2019 |  | Sales Tax | $2,165,861 | $1,717,810 | $448,051 | Green | Yellow | Active | lthompson@fairburn.com | 2018 | 2020-12-17 13:26:23
FA- 9 |  | Senoia Road Pedestrian Improvements Project | Tier 2 | Pedestrian and Bike Improvements | TSPLOST | Fairburn | Completed | Pedestrian Improvements on Senoia Road near Harvest Rain Church. | LB Concrete & Construction, LLC | Design-Build | May, 2017 | September, 2017 | December, 2017 | November, 2017 |  | Sales Tax | $21,843 | $21,843 | $0 | Green | Green | Active | lthompson@fairburn.com | 2018 | 2021-09-09 11:48:06
FIB- 11 | UFC-101 | Maintenance and Safety Enhancements | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fulton Industrial Blvd. | Completed | 2017 Resurfacing of West Park Drive within the Fulton Industrial District | CW Matthews | N/A |  |  | December, 2018 |  |  | Sales Tax | $482,272 | $482,272 | $0 | Green | Green | Active | steve.williams@fultoncountyga.gov | 2017 | 2022-10-04 00:24:49
FIB- 12 | UFC-102 | Maintenance and Safety Enhancements | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fulton Industrial Blvd. | Planning | Maintenance and Safety Enhancements - Subdivision Toppings in Unincorporated Fulton | [7 empty] | Sales Tax | $1,625,475 | $0 | $1,625,475 | Gray | Gray | Inactive | mike.rowicki@fultoncountyga.gov
FIB- 13 | UFC-103 | Maintenance and Safety Enhancements | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fulton Industrial Blvd. | Planning | Maintenance and Safety Enhancements - Subdivision Resurfacing in Unincorporated Fulton | [7 empty] | Sales Tax | $23,021,489 | $0 | $23,021,489 | Gray | Gray | Inactive | mike.rowicki@fultoncountyga.gov
FIB- 14 | UFC-126 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | Fulton Industrial Blvd. | Planning | Operations and Safety Improvements in Unincorporated Fulton, Signal Upgrades | [7 empty] | Sales Tax | $2,750,000 | $0 | $2,750,000 | Gray | Gray | Inactive | mike.rowicki@fultoncountyga.gov
FIB- 15 | UFC-129 | Fulton County Airport | Tier 1 | Fulton County Airport Improvements | TSPLOST | Fulton Industrial Blvd. | Planning | Matching funds for captial improvements at the Fulton County Airport, | [7 empty] | Sales Tax | $1,000,000 | $0 | $1,000,000 | Gray | Gray | Inactive | mike.rowicki@fultoncountyga.gov
FIB- 16 | UFC-130 | Fulton County Airport | Tier 1 | Fulton County Airport Improvements | TSPLOST | Fulton Industrial Blvd. | Planning | Fulton County Airport Improvements in Unincorporated Fulton - Aviation Circle Paving | [7 empty] | Sales Tax | $189,500 | $0 | $189,500 | Gray | Gray | Inactive | mike.rowicki@fultoncountyga.gov
FIB- 17 | UFC-131 | Quick Response Projects | Tier 1 | Quick Response | TSPLOST | Fulton Industrial Blvd. | Planning | Quick Response Projects in Unincorporated Fulton | [7 empty] | Sales Tax | $1,648,045 | $0 | $1,648,045 | Gray | Gray | Inactive | mike.rowicki@fultoncountyga.gov
FIB- 18 | UFC-201 | Maintenance and Safety Enhancements | Tier 2 | Maintenance and Safety Enhancements | TSPLOST | Fulton Industrial Blvd. | Planning | Maintenance and Safety Enhancements in Unincorporated Fulton - Resurfacing of Corridors | [7 empty] | Sales Tax | $1,778,326 | $0 | $1,778,326 | Gray | Gray | Inactive | mike.rowicki@fultoncountyga.gov
FIB- 19 | UFC-210 | Quick Response Projects | Tier 2 | Quick Response | TSPLOST | Fulton Industrial Blvd. | Planning | Quick Response Projects in Unincorporated Fulton | [7 empty] | Sales Tax | $290,831 | $0 | $290,831 | Gray | Gray | Inactive | mike.rowicki@fultoncountyga.gov
FIB- 20 | UFC-301 | Maintenance and Safety Enhancements | Tier 3 | Maintenance and Safety Enhancements | TSPLOST | Fulton Industrial Blvd. | Planning | Maintenance and Safety Enhancements in Unincorporated Fulton, Subdivision Resurfacing | [7 empty] | Sales Tax | $124,513 | $0 | $124,513 | Gray | Gray | Inactive | mike.rowicki@fultoncountyga.gov
FIB- 21 | UFC-308 | Quick Response Projects | Tier 3 | Quick Response | TSPLOST | Fulton Industrial Blvd. | Planning | Quick Response Projects in Unincorporated Fulton | [7 empty] | Sales Tax | $346,755 | $0 | $346,755 | Gray | Gray | Inactive | mike.rowicki@fultoncountyga.gov
FIB- 22 | RSF 369 | Park Plateau off Park Resurfacing | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fulton Industrial Blvd. | Completed | Wendell Drive and Wendell Court will be resurfaced in 2019. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. Project was completed in November 2019. | CW Matthews | N/A | Not Applicable | August, 2019 | November, 2019 | November, 2019 |  | Sales Tax | $26,818 | $26,818 | $0 | Green | Green | Active | cordell.rhymer@fultoncountyga.gov | 2019
FIB- 23 | RS 400 | West Park SD | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fulton Industrial Blvd. | Bidding | The roads (Boulder Ridge Drive, Gwantley Drive, NorthWest Park Drive, Rock Field Court, South West Park Drive, West Park Drive, Westfield Drive, and Westpark Place) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CWM |  |  |  | November, 2018 |  |  | Sales Tax | $482,727 | $186,421 | $296,306 | Gray | Gray | Inactive | cordell.rhymer@fultoncountyga.gov | 2018
FIB- 24 | OSI 611 | Fulton Industrial Boulevard- Streetscapes and pedestrian upgrades from Frederick Dr. to MLK Jr. Dr inc. I-20 Interchange Ramps | Tier 1 | Operation and Safety Improvements | TSPLOST | Fulton Industrial Blvd. | Completed | A joint project with the Boulevard CID to provide landsscaping and hardscaping improvements around the I-20 interchange ramps with Fulton Industrial Boulevard. | PCID | PCID |  |  | November, 2018 | July, 2018 |  | Sales Tax | $1,000,000 | $999,969 | $31 | Green | Green | Active | steve.williams@fultoncountyga.gov | 2018
FIB- 25 | OSI 612 | Fulton Industrial Boulevard @ Cascade Road | Tier 1 | Operation and Safety Improvements | TSPLOST | Fulton Industrial Blvd. | Design | Intersection will be analyzed for traffic improvements including a roundabout alternative. Curb & Gutter, drainage, sidewalks, and street lights will be part of the proposed improvements. The intersection improvements will provide geometric and congestion relief. | TBD | Kimley-Horn | December, 2020 | July, 2019 | December, 2023 | October, 2023 |  | Sales Tax | $1,000,000 | $100,000 | $900,000 | Green | Green | Active | cordell.rhymer@fultoncountyga.gov | 2019
FIB- 26 | OSI 623 | Fulton Industrial Boulevard-Sidewalks corridor-wide | Tier 2 | Operation and Safety Improvements | TSPLOST | Fulton Industrial Blvd. | Planning | Design and construction of sidewalk improvements along Fulton Industrial Boulevard at the highest priority locations | TBD | TBD | August, 2023 | May, 2023 | December, 2023 | November, 2023 |  | Sales Tax | $500,000 | $0 | $500,000 | Gray | Gray | Active | cordell.rhymer@fultoncountyga.gov | 2023
FIB- 27 | FFA 1001 | Charlie Brown Airport Matching Funds | Tier 1 | Fulton County Airport Improvements | TSPLOST | Fulton Industrial Blvd. | Planning | Matching Funds for federal and state grant programs for capital improvements at the Fulton County Airport | TBD | Michael Baker International | May, 2020 | May, 2020 | October, 2023 | July, 2023 |  | Sales Tax | $1,000,000 | $0 | $1,000,000 | Green | Green | Active | cordell.rhymer@fultoncountyga.gov | 2020
FIB- 28 | FFA 1002 | Aviation Circle Paving | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fulton Industrial Blvd. | Completed | Aviation Circle Paving from Fulton Industrial Boulevard to the Airport Terminal Project was completed in November 2019. | CW Matthews | N/A | Not Applicable | October, 2019 | December, 2019 | November, 2019 |  | Sales Tax | $189,500 | $189,500 | $0 | Green | Green | Active | cordell.rhymer@fultoncountyga.gov | 2019
HA- 10 |  | Sidewalk, Curb & Gutter Repairs | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Hapeville | Bidding | City wide replacement of dilapidated sidewalks on selected streets & N. Central Section Replacement |  |  | September, 2022 | November, 2025 | April, 2026 | March, 2026 |  | Sales Tax | $1,200,000 | $0 | $1,200,000 | Gray | Green | Active | lsudduth@hapeville.org |  | 2025-09-22 12:17:26 | Georgia | City of Hapeville | 2022-03-31
HA- 11 |  | Traffic Signal and Signage Improvement Project | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Hapeville | Completed | Installation of new traffic signal heads and new School Zone Flashers | Sunbelt |  | July, 2022 | September, 2022 | September, 2026 | January, 2026 |  | Sales Tax | $60,200 | $106,106 | $-45,906 | Red | Green | Active | lsudduth@hapeville.org |  | 2025-09-22 11:56:16 | Georgia | N. Fulton and King Arnold Intersection | 2022-03-31
HA- 2 |  | Dogwood Drive Streetscape | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Hapeville | Concept | New sidewalks, curb & gutter, drainage, paving and bicycle lanes. | Tri Scapes Inc. | Keck & Wood | April, 2017 | April, 2017 | August, 2018 | August, 2018 |  | Sales Tax | $1,900,000 | $923,901 | $976,099 | Green | Green | Active | lsudduth@hapeville.org | 2018 | 2021-11-09 21:45:25
HA- 3 |  | Silent Crossings | Tier 1 | Operation and Safety Improvements | TSPLOST | Hapeville | Completed | Install silent crossings at five railroad crossings in Hapeville | NS | NS | August, 2019 | December, 2020 | June, 2021 | June, 2021 |  | Sales Tax | $1,600,000 | $1,321,754 | $278,246 | Green | Green | Active | lsudduth@hapeville.org | 2018 | 2021-11-09 21:48:31
HA- 4 | HA-103 | Loop Road Improvement Project | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Hapeville | Concept | Maintenance & Safety in City of Hapeville - Paving & Drainage Loop Road Project | Excellere | HGOR | April, 2017 | September, 2018 | December, 2019 | December, 2019 |  | Sales Tax | $500,000 | $477,740 | $22,260 | Green | Green | Active | lsudduth@hapeville.org | 2019 | 2025-09-22 12:16:21
HA- 5 | HA-201 | Rail Facilities Project | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Hapeville | Concept | Maintenance & Safety in City of Hapeville - Paving & Drainage | Astra | Keck & Wood |  | June, 2018 | October, 2019 | October, 2019 |  | Sales Tax | $300,000 | $252,927 | $47,073 | Gray | Gray | Active | lsudduth@hapeville.org | 2019 | 2021-11-09 21:47:16
HA- 6 | HA-108 | Hapeville Paving Project | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Hapeville | Bidding | Paving of roads | TBD | Keck & Wood | August, 2021 | January, 2022 | April, 2022 | March, 2022 |  | Sales Tax | $600,000 | $1,360,567 | $-760,567 |  | Gray | Active | lsudduth@hapeville.org | 2021 | 2021-11-09 21:59:59
HA- 7 |  | Paving & Drainage | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | Hapeville | Construction | City Wide Paving of selected streets | Vertical Earth Paving |  | December, 2023 | April, 2024 | October, 2026 | October, 2026 |  | Sales Tax | $1,000,000 | $252,802 | $747,198 | Green | Green | Active | lsudduth@hapeville.org |  | 2025-09-22 12:15:11 | Georgia | City of Hapeville | 2022-03-31
HA- 8 |  | King Arnold Pedestrian Improvement Project Phase 1 | Tier 2 | Pedestrian and Bike Improvements | TSPLOST2 | Hapeville | Design | King Arnold Streetscape- Completed S. Central Streetscape (sidewalks) | Sol Construction |  | April, 2023 | August, 2026 | January, 2027 | December, 2026 |  | Sales Tax | $892,976 | $553,442 | $339,534 | Gray | Gray | Active | lsudduth@hapeville.org | 2023 | 2025-09-22 12:10:25 | Georgia | King Arnold | 2022-03-31
HA- 9 |  | I-85 Soundwall | Tier 1 | Roadway Projects | TSPLOST2 | Hapeville | Planning | Sound wall on I-85 corridor. |  |  | January, 2025 | May, 2025 | December, 2025 | November, 2025 |  | Sales Tax | $3,600,000 | $0 | $3,600,000 | Gray | Gray | Inactive | lsudduth@hapeville.org |  | 2025-09-22 12:15:46 | Georgia | City of Hapeville | 2022-03-31
JCR- 10 | JCR-012 | New Location Road in Tech Park | Tier 1 | Operation and Safety Improvements | TSPLOST | Johns Creek | Planning | This project will construct a new 2-lane roadway to connect Bell Road to Johns Creek Parkway. This project may include improvements such as sidewalks, trails and, landscaping. | CMES INC. | Kimley Horn | September, 2019 | October, 2019 | August, 2020 | September, 2020 | https://www.johnscreekga.gov/residents/public-works/tsplost/bell-and-boles-rd-corridor-operational-and-safety | Sales Tax | $1,994,786 | $1,994,786 | $0 | Green | Green | Inactive | kevin.albi@johnscreekga.gov | 2020 | 2024-07-09 14:16:04 | Georgia | City of Johns Creek
JCR- 11 | JCR-013 | State Bridge Widening (Kimball Bridge to Medlock Bridge) | Tier 2 | Operation and Safety Improvements | TSPLOST | Johns Creek | Planning | This project will widen State Bridge Road from 4 to 6 lanes between Kimball Bridge and Medlock Bridge and may include improvements such as sidewalks, trails and landscaping. | Vertical Earth | WSP USA INC. | June, 2020 | September, 2020 | July, 2021 | June, 2021 | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Medlock-Bridge-Rd-at-State-Bridge-Rd | Sales Tax | $2,205,757 | $2,205,757 | $0 | Green | Green | Inactive | kevin.albi@johnscreekga.gov | 2021 | 2024-07-08 14:49:25 | Georgia | City of Johns Creek
JCR- 12 | JCR-025 | Bridge Improvements | Tier 2 | Bridges | TSPLOST | Johns Creek | Planning | This project may include maintenance work and widening to accommodate pedestrians and bicycles. | [6 empty] | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Bridge-Improvements | Sales Tax | $2,000,000 | $0 | $2,000,000 | Gray | Gray | Active | guest |  | 2021-05-05 12:43:21
JCR- 13 | JCR-006 | Old Alabama Road Capacity (Nesbit Ferry to Old Alabama Connector) | Tier 2 | Operation and Safety Improvements | TSPLOST | Johns Creek | Planning | This project will widen Old Alabama Road from Nesbit Ferry Road to Old Alabama Connector and may include improvements such as sidewalks, trails and landscaping. | TBD | TBD |  |  |  |  | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Old-Alabama-Widening-from-Nesbit-Ferry-to-Old-Alab | Sales Tax | $300,000 | $0 | $300,000 | Gray | Gray | Active | kevin.albi@johnscreekga.gov |  | 2024-07-09 14:28:25 | Georgia | City of Johns Creek
JCR- 14 | JCR-019 | Barnwell Road Corridor Improvements | Tier 3 | Operation and Safety Improvements | TSPLOST | Johns Creek | Design | This project will include improvements along Barnwell Road which may include trails, sidewalks, bike lanes, turn lanes, roundabouts and landscaping. This overall project will be constructed as several smaller projects. | Williams Contracting | Michael Baker |  |  | November, 2022 | October, 2022 | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Barnwell-Road-Corridor-Improvements | Sales Tax | $2,046,245 | $2,046,245 | $0 | Green | Green | Active | kevin.albi@johnscreekga.gov |  | 2024-07-09 14:59:52 | Georgia | City of Johns Creek
JCR- 15 | JCR-010 | Nesbit Ferry Corridor Improvements | Tier 3 | Operation and Safety Improvements | TSPLOST | Johns Creek | Planning | This project will widen Nesbit Ferry Road north of Scott Road and provide a center turn lane south of Scott Road. This project may include improvements such as turn lanes, sidewalks and landscaping. | [6 empty] | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Nesbit-Ferry-Rd-Corridor-Improvements | Sales Tax | $500,000 | $0 | $500,000 | Gray | Gray | Active | kevin.albi@johnscreekga.gov |  | 2024-07-09 15:08:49 | Georgia | City of Johns Creek
JCR- 16 | JCR-018 | Bridge Replacement | Tier 3 | Bridges | TSPLOST | Johns Creek | Planning | This project will replace two (2) bridges within the City. These may be located on Old Alabama Road over Johns Creek and Johns Creek Tributary. | CMES INC. | Michael Baker |  |  |  |  | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Bridge-Replacements | Sales Tax | $2,500,000 | $2,035,791 | $464,209 | Gray | Gray | Inactive | kevin.albi@johnscreekga.gov | 2020 | 2024-07-10 15:27:02 | Georgia | City of Johns Creek
JCR- 17 | JCR-017 | Sidewalk and Trail Enhancements | Tier 3 | Pedestrian and Bike Improvements | TSPLOST | Johns Creek | Planning | This project may consist of improvements including sidewalks, trails, pedestrian, bridges as per the City's Sidewalk Program. | Summit Construction | NV5 | July, 2020 | January, 2021 | November, 2021 | October, 2021 |  | Sales Tax | $1,129,318 | $1,129,318 | $0 | Green | Green | Inactive | kevin.albi@johnscreekga.gov | 2021 | 2024-07-11 11:40:03 | Georgia | City of Johns Creek | 2024-07-11
JCR- 18 | JCR-024 | Transportation Alternatives | Tier 3 | Operation and Safety Improvements | TSPLOST | Johns Creek | Planning | Multimodal alternatives |  | CHA | June, 2023 | August, 2023 |  |  |  | Sales Tax | $800,000 | $0 | $800,000 | Green | Green | Active | kevin.albi@johnscreekga.gov |  | 2024-07-11 11:45:19 | Georgia | City of Johns Creek | 2024-07-11
JCR- 19 | JCR-011 | Findley Road Extension to Lakefield Drive | Tier 3 | Operation and Safety Improvements | TSPLOST | Johns Creek | Planning | This project will extend the 2-lane Findley Road across Medlock Bridge and Lakefield Drive to Johns Creek Parkway. This project may include improvements such as sidewalks, trails, and landscaping. | [6 empty] | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Findley-Road-Extension-to-Lakefield-Drive | Sales Tax | $500,000 | $0 | $500,000 | Gray | Gray | Active | kevin.albi@johnscreekga.gov |  | 2024-07-11 11:49:15 | Georgia | City of Johns Creek | 2024-07-11
JCR- 2 | JCR-001 | Medlock Bridge Capacity Project (Chattahoochee River to McGinnis Ferry) | Tier 1 | Congestion Relief | TSPLOST | Johns Creek | Land | This project will improve intersections along the Medlock Bridge Road corridor and improve or add pedestrian facilities. | [6 empty] | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Medlock-Bridge-Road-Capacity-Project | Sales Tax | $2,500,000 | $42,336 | $2,457,664 | Green | Gray | Active | kevin.albi@johnscreekga.gov |  | 2024-07-11 11:56:44 | Georgia | City of Johns Creek | 2024-07-11
JCR- 20 | JCR-021 | Old Alabama Road Widening (Jones Bridge Road to Buice Road) | Tier 3 | Operation and Safety Improvements | TSPLOST | Johns Creek | Planning | This project will widen Old Alabama Road from 2 to 4 lanes between Jones Bridge and Buice and may include improvements such as sidewalks, trails, and landscaping. |  | Foresite Group |  |  |  |  | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Old-Alabama-Widening-from-Jones-Bridge-to-Buice-Rd | Sales Tax | $1,500,000 | $0 | $1,500,000 | Gray | Gray | Active | kevin.albi@johnscreekga.gov |  | 2024-07-11 12:14:44 | Georgia | City of Johns Creek | 2024-07-11
JCR- 21 | JCR-015 | Resurfacing Program | Tier 3 | Maintenance and Safety Enhancements | TSPLOST | Johns Creek | Planning | This project will resurface roadways throughout the City. | [6 empty] | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Resurfacing-Program | Sales Tax | $1,000,000 | $0 | $1,000,000 | Gray | Gray | Active | guest |  | 2021-05-05 12:46:59
JCR- 22 | JCR-022 | Medlock Bridge Transit Related Signal Enhancements | Tier 3 | Operation and Safety Improvements | TSPLOST | Johns Creek | Planning | This project will upgrade software and signal equipment along SR 141 to allow buses to obtain a green light as they enter a signalized intersection. | [6 empty] | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Medlock-Bridge-Rd-Transit-Related-Enhancements | Sales Tax | $500,000 | $0 | $500,000 | Gray | Gray | Active | guest |  | 2021-05-05 12:52:33
JCR- 23 | JCR-016 | Connected Vehicle Infrastructure | Tier 3 | Operation and Safety Improvements | TSPLOST | Johns Creek | Planning | This project would install infrastructure for connected vehicles. | [6 empty] | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Connected-Vehicle-Infrastructure | Sales Tax | $500,000 | $0 | $500,000 | Gray | Gray | Active | guest |  | 2021-05-05 12:52:43
JCR- 24 | JCR-008 | Bell / Boles Corridor Operational & Safety Improvements - Bell Road at McGinnis Ferry Road | Tier 1 | Operation and Safety Improvements | TSPLOST | Johns Creek | Completed | This project will add storage space in the right turn lane from Bell Road onto McGinnis Ferry Road. It will also add a lane on McGinnis Ferry Road for a short distance across the intersection for additional capacity. | CMES, Inc. | Kimley Horn and Associates | September, 2019 | October, 2019 | August, 2020 | September, 2020 | https://www.johnscreekga.gov/residents/public-works/tsplost/bell-and-boles-rd-corridor-operational-and-safety | Sales Tax | $1,994,786 | $1,994,786 | $0 | Green | Green | Inactive | chris.haggard@johnscreekga.gov | 2020 | 2022-08-22 15:05:35
JCR- 25 | JCR-020 | Medlock Bridge Road at State Bridge Improvements - Phase 1 | Tier 1 | Operation and Safety Improvements | TSPLOST | Johns Creek | Completed | This project will make improvements to the intersection of Medlock Bridge and State Bridge Road. Proposed improvements are adding a third southbound lane on SR 141/Medlock Bridge Road and a third eastbound and westbound lane on State Bridge Road. This will be accomplished using a combination of widening and restriping to minimize impacts. | Vertical Earth | WSP | June, 2020 | September, 2020 | July, 2021 | June, 2021 | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Medlock-Bridge-Rd-at-State-Bridge-Rd | Sales Tax | $2,205,757 | $2,205,757 | $0 | Green | Green | Inactive | chris.haggard@johnscreekga.gov | 2021 | 2022-08-22 15:03:34
JCR- 26 | JCR-004 | McGinnis Ferry Road Widening from Union Hill Rd to Sargent Rd - Phase 1 | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Johns Creek | Land | This regional capacity enhancement project includes widening of McGinnis Ferry Road from 2-lanes to 4-lanes. This portion of the project is jointly funded by Forsyth County and Johns Creek. McGinnis Ferry Road is a major east/ west corridor connecting I-85 with GA 400. The project limits are from Sargent Road to Seven Oaks Parkway/Brassfield Drive to Douglas Road -- This project is no longer active on its own and the McGinnis Ferry Road corridor will be completed under one project. | [6 empty] | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/McGinnis-Ferry-Road-Widening | Sales Tax | $0 | $0 | $0 |  |  | Active | chris.haggard@johnscreekga.gov |  | 2022-08-22 14:54:20
JCR- 27 | JCR-008 | Bell / Boles Corridor Operational & Safety Improvements - Bell Road at Medlock Bridge Road | Tier 1 | Operation and Safety Improvements | TSPLOST | Johns Creek | Completed | This project will add a left turn lane at the intersection as well as separate the a thru/right combined lane into separate lanes. Other turn lane improvements as well as sidewalk and signal upgrades are planned for this project. | CMES Inc. | DPE | December, 2019 | May, 2020 | March, 2021 | March, 2021 | https://www.johnscreekga.gov/residents/public-works/tsplost/bell-and-boles-rd-corridor-operational-and-safety | Sales Tax | $1,313,973 | $1,313,973 | $0 | Green | Green | Inactive | chris.haggard@johnscreekga.gov | 2021 | 2022-08-22 15:03:02
JCR- 28 | JCR-008 | Bell / Boles Corridor Operational & Safety Improvements - Bell Road at Rogers Circle (South) | Tier 1 | Operation and Safety Improvements | TSPLOST | Johns Creek | Completed | Project will introduce a roundabout at the intersection of Bell Road and Rogers Circle as well as a trail along Rogers Circle. | Ohmshiv | KCI | September, 2020 | December, 2020 | October, 2021 | September, 2021 | https://www.johnscreekga.gov/residents/public-works/tsplost/bell-and-boles-rd-corridor-operational-and-safety | Sales Tax | $2,026,935 | $2,026,935 | $0 | Green | Green | Inactive | chris.haggard@johnscreekga.gov | 2021 | 2022-08-22 15:01:11
JCR- 29 | JCR-008 | Bell / Boles Corridor Operational & Safety Improvements - Bell Road at Cauley Creek Park | Tier 1 | Operation and Safety Improvements | TSPLOST | Johns Creek | Completed | This project plans to proactively prepare for additional volume along Bell Road and from the future Cauley Creek Park by adding a roundabout at the intersection of Bell Road and Cauley Creek Park/Old Homestead Trail. | Summit Construction | NV5 | July, 2020 | January, 2021 | November, 2021 | October, 2021 | https://www.johnscreekga.gov/residents/public-works/tsplost/bell-and-boles-rd-corridor-operational-and-safety | Sales Tax | $1,129,318 | $1,129,318 | $0 | Green | Green | Inactive | chris.haggard@johnscreekga.gov | 2021 | 2022-08-22 15:06:40
JCR- 3 | JCR-014 | State Bridge Road Widening (Medlock Bridge to Chattahoochee River) | Tier 1 | Congestion Relief | TSPLOST | Johns Creek | Completed | This project will widen State Bridge Road from 4 to 6 lanes between Medlock Bridge and the Chattahoochee River and may include improvements such as sidewalks, trails and landscaping. | CMES, Inc. | Michael Baker | August, 2019 | November, 2019 | December, 2020 | December, 2020 | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/State-Bridge-Road-Widening | Sales Tax | $2,500,000 | $2,035,791 | $464,209 | Green | Green | Inactive | chris.haggard@johnscreekga.gov | 2020 | 2022-08-22 15:05:07
JCR- 30 | JCR-008 | Bell / Boles Corridor Operational & Safety Improvements - Bell Road Bridge over Cauley Creek Tributary | Tier 1 | Operation and Safety Improvements | TSPLOST | Johns Creek | Construction | This project will reconstruct a bridge identified by GDOT in a BFI. | Williams Contracting | Michael Baker |  |  | November, 2022 | October, 2022 | https://www.johnscreekga.gov/residents/public-works/tsplost/bell-and-boles-rd-corridor-operational-and-safety | Sales Tax | $2,046,245 | $2,046,245 | $0 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-08-22 15:08:53
JCR- 31 | TS0211 | Old Alabama Bridge over Chattahoochee Tributary | Tier 1 | Bridges | TSPLOST2 | Johns Creek | Concept | Replace existing substandard bridge on Old Alabama Road over Chattahoochee Tributary just West of Autrey Mill Nature Preserve entrance. |  | Michael Baker | [5 empty] | Sales Tax | $3,250,000 | $118,193 | $3,131,807 |  |  | Active | chris.haggard@johnscreekga.gov |  | 2022-10-05 12:49:26 | Georgia | City of Johns Creek | 2022-03-31
JCR- 32 | TS0221 | Nesbit Ferry Road Improvements | Tier 1 | Congestion Relief | TSPLOST2 | Johns Creek | Planning | Operational and safety improvements along Nesbit Ferry Road between SR 140/Holcomb Bridge Road and Old Alabama Road. | [7 empty] | Sales Tax | $7,500,000 | $0 | $7,500,000 |  |  | Active | chris.haggard@johnscreekga.gov |  | 2022-10-05 12:53:48 | Georgia | City of Johns Creek | 2022-03-31
JCR- 33 | TS0231 | Town Center - Creekside Park Trail Landscaping | Tier 1 | Landscape and Streetscape | TSPLOST2 | Johns Creek | Concept | Landscaping along Creekside Park Trail within Johns Creek Town Center redevelopment. |  | Forsite Group | [5 empty] | Sales Tax | $1,500,000 | $0 | $1,500,000 |  |  | Active | chris.haggard@johnscreekga.gov |  | 2022-10-19 12:50:44 | Georgia | City of Johns Creek | 2022-03-31
JCR- 34 | TS0241 | Barnwell at Niblick Intersection Improvement | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Johns Creek | Design | Operational improvement at the intersection of Barnwell Road at Niblick Drive. |  | Thomas and Hutton | September, 2023 | November, 2023 |  |  |  | Sales Tax | $2,350,000 | $11,500 | $2,338,500 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-10-05 13:10:07 | Georgia | City of Johns Creek | 2022-03-31
JCR- 35 | TS0251 | Old Alabama Road (Autrey Mill to Spruill Road) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Johns Creek | Design | Sidewalk/Trail connectivity from Autrey Mill Nature Preserve to Spruill Road on the North side of Old Alabama. |  | CHA | June, 2023 | August, 2023 |  |  |  | Sales Tax | $800,000 | $0 | $800,000 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-10-05 13:21:41 | Georgia | City of Johns Creek | 2022-03-31
JCR- 36 |  | City Wide | Tier 2 | Bridges | TSPLOST2 | Johns Creek | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Johns Creek | 2022-03-31
JCR- 37 |  | City Wide | Tier 2 | Congestion Relief | TSPLOST2 | Johns Creek | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Johns Creek | 2022-03-31
JCR- 38 |  | City Wide Operation and Safety | Tier 2 | Operation and Safety Improvements | TSPLOST2 | Johns Creek | Planning | Overall Operations and Safety | [7 empty] | Sales Tax | $2,000,000 | $500,000 | $1,500,000 |  |  | Active | chris.haggard@johnscreekga.gov |  | 2024-06-18 15:29:46 | Georgia | 2635 Peachtree Pkwy, Suwanee, GA 30024 | 2022-03-31
JCR- 39 |  | City Wide | Tier 2 | Pedestrian and Bike Improvements | TSPLOST2 | Johns Creek | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Johns Creek | 2022-03-31
JCR- 4 | JCR-020 | Medlock Bridge at State Bridge Improvements - Phase 2 | Tier 1 | Operation and Safety Improvements | TSPLOST | Johns Creek | Concept | This project will make improvements to the intersection of Medlock Bridge and State Bridge Road. The proposed improvements will be a hybrid solution of both continuous flow intersections and thru-U intersections (median u-turns). |  |  | August, 2023 |  |  |  | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Medlock-Bridge-Rd-at-State-Bridge-Rd | Sales Tax | $5,794,243 | $85,500 | $5,708,743 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-01-11 15:13:34
JCR- 40 |  | City Wide | Tier 3 | Pedestrian and Bike Improvements | TSPLOST2 | Johns Creek | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Johns Creek | 2022-03-31
JCR- 41 | TS0212 | Old Alabama Bridge over Johns Creek | Tier 1 | Bridges | TSPLOST2 | Johns Creek | Concept | Replace existing substandard bridge on Old Alabama Road over Johns Creek just East of Spruill Road. |  | Kimley-Horn | [5 empty] | Sales Tax | $3,250,000 | $110,943 | $3,139,057 |  |  | Active | chris.haggard@johnscreekga.gov |  | 2022-10-05 12:49:26 | Georgia | City of Johns Creek | 2022-03-31
JCR- 42 | TS0222 | Abbotts Bridge Road (Parsons to Medlock Bridge) | Tier 1 | Congestion Relief | TSPLOST2 | Johns Creek | Land | This regional capacity enhancement project includes widening of SR 120/ Abbotts Bridge Road from 2-lanes to 4-lanes. The project is jointly funded by GDOT and Johns Creek. Abbotts Bridge Road is a major east/ west corridor connecting I-85 with GA 400. The project limits are from Parsons Road to SR 141/ Medlock Bridge Road. |  | CHA | June, 2023 | October, 2023 |  |  |  | Sales Tax | $4,000,000 | $0 | $4,000,000 |  |  | Active | chris.haggard@johnscreekga.gov |  | 2022-10-05 12:59:16 | Georgia | City of Johns Creek | 2022-03-31
JCR- 43 | TS0232 | Town Center - Main Street (Lakefield Drive) | Tier 1 | Landscape and Streetscape | TSPLOST2 | Johns Creek | Concept | Landscaping along Main Street/Lakefield Drive within Johns Creek Town Center redevelopment. |  | Accura Engineering | [5 empty] | Sales Tax | $1,500,000 | $0 | $1,500,000 |  |  | Active | chris.haggard@johnscreekga.gov |  | 2022-10-19 12:54:16 | Georgia | City of Johns Creek | 2022-03-31
JCR- 44 | TS0242 | Sargent Road at Ashwick Place Intersection Improvement | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Johns Creek | Design | Operational improvement at the intersection of Sargent Road at Ashwick Place. |  | Lowe Engineers | March, 2024 | May, 2024 |  |  |  | Sales Tax | $2,500,000 | $0 | $2,500,000 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-10-05 13:10:07 | Georgia | City of Johns Creek | 2022-03-31
JCR- 45 | TS0243 | Town Center - Lakefield Drive at Johns Creek Parkway | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Johns Creek | Concept | Operational improvement at the intersection of Lakefield Drive at Johns Creek Parkway (North). |  | Accura Engineering | September, 2024 | November, 2024 |  |  |  | Sales Tax | $3,500,000 | $0 | $3,500,000 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-10-19 12:53:48 | Georgia | City of Johns Creek | 2022-03-31
JCR- 46 | TS0244 | Intelligent Transportation Systems Fiber Connectivity | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Johns Creek | Design | Fiber connectivity on Bell Road and Old Alabama Road. Communication upgrades citywide. |  | Atkins | December, 2022 | February, 2023 |  |  |  | Sales Tax | $1,000,000 | $0 | $1,000,000 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-10-05 13:10:07 | Georgia | City of Johns Creek | 2022-03-31
JCR- 47 | TS0252 | Town Center - Creekside North Pond Trail | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Johns Creek | Concept | Pedestrian Trail connectivity within Town Center redevelopment area. |  | Foresite | December, 2023 | February, 2024 |  |  |  | Sales Tax | $2,000,000 | $0 | $2,000,000 |  |  | Active | chris.haggard@johnscreekga.gov |  | 2022-10-05 13:21:41 | Georgia | City of Johns Creek | 2022-03-31
JCR- 48 | TS0253 | Rogers Bridge Road (Bell Road to Amberleigh Way) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Johns Creek | Concept | Sidewalk/Trail connectivity along Rogers Bridge Road from Bell Road to Amberleigh Way on the North side of Rogers Bridge Road. |  | KCI | December, 2023 | February, 2024 |  |  |  | Sales Tax | $2,200,000 | $41,300 | $2,158,700 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-10-05 13:21:41 | Georgia | City of Johns Creek | 2022-03-31
JCR- 49 | TS0254 | Barnwell Road (Rivermont Parkway to North Peak Drive) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Johns Creek | Concept | Trail connectivity from Rivermont Parkway to North Peak Drive on the West side of Barnwell Road. |  | Thomas and Hutton | June, 2024 | August, 2024 |  |  |  | Sales Tax | $3,400,000 | $0 | $3,400,000 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-10-05 13:21:41 | Georgia | City of Johns Creek | 2022-03-31
JCR- 5 | JCR-002 | Jones Bridge Widening (McGinnis Ferry to Douglas) | Tier 1 | Congestion Relief | TSPLOST | Johns Creek | Design | This project will widen Jones Bridge Road from 2 to 4 lanes between Douglas Road to McGinnis Ferry Road and may include improvements such as sidewalks, trails and landscaping. |  | Michael Baker |  |  |  |  | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Jones-Bridge-Rd-Widening-(McGinnis-Ferry-to-Sargen | Sales Tax | $7,000,000 | $0 | $7,000,000 | Gray | Gray | Active | chris.haggard@johnscreekga.gov |  | 2022-08-22 14:55:49
JCR- 50 | TS0257 | Barnwell Road (Niblick Drive to Rivermont Parkway) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Johns Creek | Concept | Trail connectivity from Niblick Drive to Rivermont Parkway on the West side of Barnwell Road. |  | Thomas and Hutton | June, 2024 | August, 2024 |  |  |  | Sales Tax | $500,000 | $0 | $500,000 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-10-05 13:21:41 | Georgia | City of Johns Creek | 2022-03-31
JCR- 51 | TS0255 | Buice Road (Twingate Drive to Kingston Crossing) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Johns Creek | Design | Sidewalk connectivity from Twingate Drive to Kingston Crossing on the North side of Buice Road. |  | KCI | June, 2023 | August, 2023 |  |  |  | Sales Tax | $650,000 | $5,200 | $644,800 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-10-05 13:21:41 | Georgia | City of Johns Creek | 2022-03-31
JCR- 52 | TS0256 | Buice Road (Spruill Road to Johns Creek) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Johns Creek | Concept | Trail connectivity from Spruill Road to bridge over Johns Creek on the South side of Buice Road. |  | Benesch | June, 2024 | August, 2024 |  |  |  | Sales Tax | $500,000 | $0 | $500,000 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-10-05 13:21:41 | Georgia | City of Johns Creek | 2022-03-31
JCR- 53 | TS0258 | Town Center - Pedestrian Crossing | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Johns Creek | Concept | Pedestrian crossing on SR 141/ Medlock Bridge Road in the Town Center redevelopment area. |  | Michael Baker | September, 2024 | November, 2024 |  |  |  | Sales Tax | $6,000,000 | $0 | $6,000,000 |  |  | Active | chris.haggard@johnscreekga.gov |  | 2022-10-05 13:21:41 | Georgia | City of Johns Creek | 2022-03-31
JCR- 6 | JCR-003 | Jones Bridge Widening (Ph.1 - Waters to Buice; Ph. 2 - Buice to State Bridge) | Tier 1 | Congestion Relief | TSPLOST | Johns Creek | Land | This project will widen Jones Bridge Road from 2 to 4 lanes between Waters Road and State Bridge Road and may include improvements such as sidewalks, trails and landscaping. Phase 1 will include improvements between Waters Road to Buice Road. Phase 2 will include improvements between Buice Road to State Bridge Road |  | Kimley Horn Engineering | May, 2021 |  |  |  | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Jones-Bridge-Rd-Widening-(Waters-to-Buice;-Buice-t | Sales Tax | $11,000,000 | $558,620 | $10,441,380 | Green | Green | Active | chris.haggard@johnscreekga.gov | 2023 | 2022-01-11 14:48:15
JCR- 7 | JCR-004 | McGinnis Ferry Road Widening from Union Hill to Sargent Rd | Tier 1 | Congestion Relief | TSPLOST | Johns Creek | Land | This regional capacity enhancement project includes widening of McGinnis Ferry Road from 2-lanes to 4-lanes. The project is jointly funded by GDOT, Forsyth County, Alpharetta and Johns Creek. McGinnis Ferry Road is a major east/ west corridor connecting I-85 with GA 400. The project limits are from Seven Oaks Parkway/Brassfield Drive to Douglas Road. |  | Moreland Altobelli | December, 2020 | December, 2022 |  |  | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/McGinnis-Ferry-Road-Widening | Federal/State and Local | $7,500,000 | $1,995,280 | $5,504,720 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-01-11 15:17:30
JCR- 8 | JCR-005 | Haynes Bridge Road at Old Alabama Road Intersection Improvement | Tier 1 | Congestion Relief | TSPLOST | Johns Creek | Construction | The Haynes Bridge Corridor is an important collector connecting neighborhoods to the south with schools, GA 400, employment and commercial centers. This project improves the Haynes Bridge Road intersection to reduce congestion. The project will also include pedestrian improvements along Haynes Bridge Road. | Summit Construction and Development |  |  |  | April, 2023 | March, 2023 | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Haynes-Bridge-Rd-Widening-(Old-Alabama-to-Mansell) | Sales Tax | $5,000,000 | $487,714 | $4,512,286 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-08-22 15:09:10
JCR- 9 | JCR-009 | Barnwell Road at Holcomb Bridge Road Intersection Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST | Johns Creek | Construction | This project includes dual left turn lanes, a through lane, and a right-turn lane on Barnwell Road at SR 140/Holcomb Bridge Road. This project may include improvements including bike lanes, sidewalks, trails, landscaping and a pedestrian bridge over Hogan's Creek. | CW Matthews | DPE | December, 2019 | May, 2021 | July, 2023 | June, 2023 | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Barnwell-Rd-at-Holcomb-Bridge-Rd-Intersection-Impr | Federal/State and Local | $2,500,000 | $1,674,213 | $825,787 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-08-22 15:09:25
MIL- 10 | MIL-008 | Hopewell Road at Hamby Road Intersection Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST | Milton | Completed | Operational improvements at the intersection and may include turn lanes, traffic signal or roundabout | CMES | Barge Design Solutions | August, 2020 | February, 2018 | November, 2021 | October, 2021 | https://cleargov.com/georgia/fulton/city/milton/projects/1228/hopewell-road-at-hamby-road-_-tsplost | Sales Tax | $2,420,000 | $1,884,604 | $535,396 | Green | Green | Active | kathy.stallard@miltonga.gov |  | 2026-02-27 09:04:04
MIL- 11 | MIL-009 | SR 140 at Green Road Intersection Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST | Milton | Land | Operation improvements at the intersection that may include a traffic signal and interconnection to other signals on the SR 140 corridor |  | Practical Design Partners | January, 2027 | April, 2021 | July, 2028 | July, 2028 | https://cleargov.com/georgia/fulton/city/milton/projects/1213/sr-140-(arnold-mill-road)-at-green-road-_-tsplost | Sales Tax | $1,060,000 | $63,400 | $996,600 | Green | Green | Active | kathy.stallard@miltonga.gov |  | 2026-02-27 09:03:47
MIL- 12 | MIL-012 | Birmingham Road Middle Bridge | Tier 1 | Bridges | TSPLOST | Milton | Land | Bridge replacement with future trail accommodations |  | BM&K | August, 2026 | May, 2021 | October, 2027 | October, 2027 | https://cleargov.com/georgia/fulton/city/milton/projects/1217/birmingham-road-middle-bridge-_-tsplost | Sales Tax | $2,803,458 | $109,476 | $2,693,982 | Green | Green | Active | kathy.stallard@miltonga.gov |  | 2026-02-27 09:03:33
MIL- 13 | MIL-034 (Trail Planning) | Multiple Pedestrian and Bike Improvements within the City | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Milton | Completed | Milton Trail Blueprint, Central Milton Trail, and Milton Community Trail Prioritization Plan | N/A | Kimley-Horn | August, 2020 | June, 2018 |  | July, 2020 | https://www.cityofmiltonga.us/Home/ShowDocument?id=2859 | Sales Tax | $171,000 | $171,000 | $0 | Green | Green | Active | guest |  | 2021-09-30 18:34:16
MIL- 14 | MIL-002 | Bethany Road at Providence Road Intersection Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST | Milton | Bidding | Operational improvements that will address the all way stop controlled intersection and may include turn lanes, traffic signal or roundabout |  | KCI | February, 2026 | April, 2021 | November, 2027 | November, 2027 | https://cleargov.com/georgia/fulton/city/milton/projects/1194/bethany-road-at-providence-road-_-tsplost | Sales Tax | $2,200,000 | $146,350 | $2,053,650 | Green | Green | Active | kathy.stallard@miltonga.gov |  | 2026-02-27 09:06:53
MIL- 15 | MIL-010 | Freemanville Road at Redd Road Intersection Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST | Milton | Design | Operational improvements at the intersection that may include turn lanes, traffic signal, or roundabout |  | KCI | August, 2026 | April, 2021 | July, 2028 | July, 2028 | https://cleargov.com/georgia/fulton/city/milton/projects/1208/freemanville-road-at-redd-road-_-tsplost | Sales Tax | $1,020,000 | $83,991 | $936,009 | Green | Green | Active | kathy.stallard@miltonga.gov |  | 2026-02-27 09:08:02
MIL- 16 | MIL-039 | Paving | Tier 3 | Maintenance and Safety Enhancements | TSPLOST | Milton | Planning | Paving roadways in the City of Milton | [6 empty] | https://www.cityofmiltonga.us/home/showpublisheddocument/146/636970572854200000 | Sales Tax | $3,000,000 | $0 | $3,000,000 | Gray | Gray | Active | sara.leaders@cityofmiltonga.us |  | 2021-04-29 21:16:52
MIL- 17 | MIL-037 | Pedestrian Improvements | Tier 2 | Pedestrian and Bike Improvements | TSPLOST | Milton | Planning | Pedestrian Improvements | [6 empty] | https://www.cityofmiltonga.us/home/showpublisheddocument/144/636970572851530000 | Sales Tax | $2,100,000 | $0 | $2,100,000 | Gray | Gray | Active | sara.leaders@cityofmiltonga.us |  | 2021-04-29 21:17:22
MIL- 18 | MIL-040 | Quick Response Projects | Tier 3 | Quick Response | TSPLOST | Milton | Planning | Small traffic operations or safety improvement projects within the existing right of way | [6 empty] | https://www.cityofmiltonga.us/home/showpublisheddocument/148/636970572857130000 | Sales Tax | $775,160 | $0 | $775,160 | Gray | Gray | Active | sara.leaders@cityofmiltonga.us |  | 2021-04-29 21:15:52
MIL- 19 | MIL-041 | Bridge Repair and Replacement | Tier 3 | Bridges | TSPLOST | Milton | Planning | Bridge repair and replacement in the City of Milton | [6 empty] | https://www.cityofmiltonga.us/home/showpublisheddocument/150/636970572860100000 | Sales Tax | $791,865 | $0 | $791,865 | Gray | Gray | Active | sara.leaders@cityofmiltonga.us |  | 2021-04-29 21:15:31
MIL- 20 | MIL-042 | Pedestrian Improvements | Tier 3 | Pedestrian and Bike Improvements | TSPLOST | Milton | Planning | Pedestrian improvements in the City of Milton | [6 empty] | https://www.cityofmiltonga.us/home/showpublisheddocument/152/636970572863130000 | Sales Tax | $1,000,000 | $0 | $1,000,000 | Gray | Gray | Active | sara.leaders@cityofmiltonga.us |  | 2021-04-29 21:15:10
MIL- 21 | MIL-031 (Interim) | Morris Road at Webb Road Roundabout (Interim Improvement Before Widening) | Tier 1 | Operation and Safety Improvements | TSPLOST | Milton | Completed | The overall project description is for a proposed widening from Webb Road to Bethany Bend tying into McGinnis Ferry Road widening at Bethany Bend. With recent signal improvements at Bethany Bend and Morris Road/McGinnis Ferry Road and upcoming interchange addition at GA 400 and McGinnis Ferry Road, an interim intersection improvement project was designed for the existing four way stop controlled intersection of Morris Road at Webb Road. Much of the project uses existing intersection footprint and converts the stop controlled intersection into a roundabout. The project will allow for future expansion with the upcoming widening project. | CMES | BM&K | March, 2018 | January, 2018 | October, 2018 | October, 2018 | https://cleargov.com/georgia/fulton/city/milton/projects/1212/morris-road-improvements-_-tsplost | Sales Tax | $400,000 | $363,289 | $36,711 | Green | Green | Active | sara.leaders@cityofmiltonga.us |  | 2021-04-29 21:48:52
MIL- 22 | MIL-034 (Cogburn) | Cogburn Road Sidewalks | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Milton | Completed | Sidewalks, curb and drainage improvements along both sides of Cogburn Road from Bethany Bend to Oakstone Glen and Devonshire Farms | DAF Concrete | Wolverton | August, 2020 | January, 2019 | December, 2021 | November, 2021 | https://cleargov.com/georgia/fulton/city/milton/projects/1197/cogburn-road-sidewalks-_-tsplost | Sales Tax | $763,178 | $635,579 | $127,599 | Green | Green | Active | kathy.stallard@miltonga.gov |  | 2026-02-27 09:08:56
MIL- 23 |  | Cox Road Intersection Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Milton | Design | Safety and Operational Improvements at several intersections along Cox Road |  | Pond and Company | July, 2026 | January, 2023 | December, 2027 | December, 2027 |  | Sales Tax | $6,000,000 | $0 | $6,000,000 | Green | Green | Active | kathy.stallard@miltonga.gov |  | 2026-02-27 09:10:08 | Georgia | City of Milton | 2022-03-31
MIL- 24 |  | Intersection Efficiency Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Milton | Planning | Intersection Efficiency Improvements - Various Locations Webb at Cogburn - Turn Lane Improvements |  | Pond and Company | September, 2023 | January, 2024 | July, 2024 |  |  | Sales Tax | $3,000,000 | $0 | $3,000,000 | Green | Green | Active | Robert.Dell-Ross@miltonga.gov |  | 2023-04-07 08:35:11 | Georgia | City of Milton | 2022-03-31
MIL- 25 |  | Bike Accomodations | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Milton | Planning | Bike Accommodations - Location TBD | [7 empty] | Sales Tax | $2,000,000 | $0 | $2,000,000 | Green | Green | Active | Robert.Dell-Ross@miltonga.gov |  | 2023-04-07 10:03:19 | Georgia | City of Milton | 2022-03-31
MIL- 26 |  | Intersection Safety Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Milton | Planning | Intersection Safety Improvments - Location TBD | [7 empty] | Sales Tax | $3,000,000 | $0 | $3,000,000 | Green | Green | Active | Robert.Dell-Ross@miltonga.gov |  | 2022-10-10 17:28:47 | Georgia | City of Milton | 2022-03-31
MIL- 27 |  | Pedestrian Enhancements/Streetscape | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Milton | Planning | Pedestrian Enhancements and Streetscape - Location TBD | [7 empty] | Sales Tax | $1,000,000 | $0 | $1,000,000 | Green | Green | Active | Robert.Dell-Ross@miltonga.gov |  | 2023-04-07 10:26:42 | Georgia | City of Milton | 2022-03-31
MIL- 28 |  | Community Trail Prioritization | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Milton | Planning | Community Trail Prioritization - Location TBD | [7 empty] | Sales Tax | $3,000,000 | $0 | $3,000,000 | Green | Green | Active | Robert.Dell-Ross@miltonga.gov |  | 2022-10-10 17:39:48 | Georgia | City of Milton | 2022-03-31
MIL- 29 |  | City Wide | Tier 1 | Bridges | TSPLOST2 | Milton | Planning | Bridges - Various Locations Bridge Maintenance Prioritization |  | Pond and Company | July, 2023 | March, 2023 | July, 2024 |  |  | Sales Tax | $4,000,000 | $0 | $4,000,000 | Green | Green | Active | Robert.Dell-Ross@miltonga.gov |  | 2023-04-07 08:36:58 | Georgia | City of Milton | 2022-03-31
MIL- 30 |  | Road Paving | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | Milton | Planning | Citywide Road Resurfacing - Location TBD | [7 empty] | Sales Tax | $5,000,000 | $0 | $5,000,000 | Green | Green | Active | Robert.Dell-Ross@miltonga.gov |  | 2022-10-10 17:41:49 | Georgia | City of Milton | 2022-03-31
MIL- 31 |  | Local Road Safety | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | Milton | Design | Citywide Local Road Safety Plan Implementation - Various Locations Bethany Bend at Serenade Court - Sidewalk and RRFB Connection (KCI) SR 372 roundabouts - RRFB Install (Keck and Wood) |  | KCI Technologies, Keck and Wood | June, 2023 | January, 2023 | October, 2023 | February, 2024 |  | Sales Tax | $3,000,000 | $23,328 | $2,976,672 | Green | Green | Active | Robert.Dell-Ross@miltonga.gov |  | 2023-04-07 08:35:27 | Georgia | City of Milton | 2022-03-31
MIL- 32 |  | City Wide | Tier 2 | Operation and Safety Improvements | TSPLOST2 | Milton | Planning | Tier 2 Operations and Safety Improvements - Location TBD | [7 empty] | Sales Tax | $3,000,000 | $0 | $3,000,000 | Green | Green | Active | Robert.Dell-Ross@miltonga.gov |  | 2022-10-10 18:05:46 | Georgia | City of Milton | 2022-03-31
MIL- 33 |  | City Wide | Tier 2 | Pedestrian and Bike Improvements | TSPLOST2 | Milton | Planning | Tier 2 Pedestrian and Bike Improvements - Location TBD | [7 empty] | Sales Tax | $2,410,202 | $0 | $2,410,202 | Green | Green | Active | Robert.Dell-Ross@miltonga.gov |  | 2022-10-10 17:24:13 | Georgia | City of Milton | 2022-03-31
MIL- 34 |  | City Wide | Tier 3 | Operation and Safety Improvements | TSPLOST2 | Milton | Planning | Tier 3 Operations and Safety Improvements - Location TBD | [7 empty] | Sales Tax | $2,000,000 | $0 | $2,000,000 | Green | Green | Active | Robert.Dell-Ross@miltonga.gov |  | 2022-10-10 17:25:05 | Georgia | City of Milton | 2022-03-31
MIL- 35 |  | City Wide | Tier 3 | Pedestrian and Bike Improvements | TSPLOST2 | Milton | Planning | Tier 3 Pedestrian and Bike Improvements - Location TBD | [7 empty] | Sales Tax | $2,410,202 | $0 | $2,410,202 | Green | Green | Active | Robert.Dell-Ross@miltonga.gov |  | 2022-10-10 17:26:05 | Georgia | City of Milton | 2022-03-31
MIL- 36 |  | City Wide | Tier 3 | Quick Response | TSPLOST2 | Milton | Planning | Tier 3 Quick Response Projects - Location TBD | [7 empty] | Sales Tax | $1,000,000 | $0 | $1,000,000 | Green | Green | Active | Robert.Dell-Ross@miltonga.gov |  | 2022-10-10 17:26:55 | Georgia | City of Milton | 2022-03-31
MIL- 4 | MIL-038/ALP-005 | Windward Parkway Business District/Union Hill Road Capacity Improvements | Tier 1 | Congestion Relief | TSPLOST | Milton | Planning | See Project ALP-005 This capacity improvement is intended to relieve congestion through Windward's business district east of Union Hill Road, complementing the concurrent Alpharetta bond project and interchange enhancement efforts west of GA 400. Project will add a travel lane in each direction and enhance the bicycle and pedestrian accommodations. | [6 empty] | https://www.cityofmiltonga.us/home/showpublisheddocument/118/636970572819630000 | Sales Tax | $500,000 | $0 | $500,000 | Green | Green | Inactive | Robert.Dell-Ross@miltonga.gov |  | 2023-04-14 09:59:25
MIL- 5 | MIL-031 | Morris Road Widening | Tier 1 | Congestion Relief | TSPLOST | Milton | Construction | The overall project description is for a proposed widening from Webb Road to Bethany Bend tying into McGinnis Ferry Road widening at Bethany Bend. The cross section is proposed as a 4 lane divided roadway with landscaped median/turn lanes and multiuse trail including intersection improvements at Webb Road. |  | Pond & Company | September, 2023 | July, 2017 | August, 2026 | August, 2026 | https://cleargov.com/georgia/fulton/city/milton/projects/1212/morris-road-improvements-_-tsplost | Sales Tax | $10,363,837 | $972,739 | $9,391,098 | Green | Green | Active | kathy.stallard@miltonga.gov |  | 2026-02-27 09:11:19
MIL- 6 | MIL-001 | Hopewell Road at Bethany Bend/Way Intersection Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST | Milton | Completed | Operational improvements that will address the intersections of Hopewell Rd with Bethany Bend, Bethany Oaks Pointe, and Bethany Way and may include turn lanes, traffic signals or roundabouts | Vertical Earth | Pond & Company | March, 2021 | July, 2017 | March, 2023 | April, 2023 | https://cleargov.com/georgia/fulton/city/milton/projects/1210/hopewell-road-at-bethany-bend_or_bethany-way-_-tsplost | Sales Tax | $4,100,000 | $3,315,108 | $784,892 | Green | Green | Active | kathy.stallard@miltonga.gov |  | 2026-02-27 09:11:48
MIL- 7 | MIL-004 | Freemanville Road at Birmingham Road Intersection Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST | Milton | Completed | Operational improvements that will address the all way stop controlled intersection and may include turn lanes, traffic signal or roundabout |  | CHA | December, 2021 | March, 2020 | September, 2023 | September, 2023 | https://cleargov.com/georgia/fulton/city/milton/projects/1205/freemanville-road-at-birmingham-road-_-tsplost | Sales Tax | $1,990,000 | $300,738 | $1,689,262 | Green | Green | Active | kathy.stallard@miltonga.gov |  | 2026-02-27 09:12:07
MIL- 8 | MIL-005/MIL-030 | Northeast Crabapple Connector Road | Tier 1 | Congestion Relief | TSPLOST | Milton | Completed | New alignment roadway from proposed improved intersection at Mayfield Rd and Charlotte Dr (Project MIL-005) to roundabout at SR 372/ Birmingham Hwy at McFarlin Ln | CMES | Pond & Company | October, 2018 | July, 2017 | February, 2021 | March, 2021 | http://miltonintersectionprojects.com/northeast-crabapple-connector-road/ | Sales Tax | $7,199,218 | $3,100,860 | $4,098,358 | Green | Green | Active | guest |  | 2021-09-30 18:26:57
MIL- 9 | MIL-006 | Hopewell Road at Thompson Road/South Thompson Road Intersection Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST | Milton | Completed | Realignment of offset intersections and operational improvements that may include turn lanes, traffic signal, or roundabout | CMES | Barge Design Solutions | August, 2020 | February, 2018 | November, 2021 | October, 2021 | https://cleargov.com/georgia/fulton/city/milton/projects/1180/hopewell-road-at-thompson-road-_-tsplost | Sales Tax | $3,580,000 | $2,606,130 | $973,870 | Green | Green | Active | kathy.stallard@miltonga.gov |  | 2026-02-27 09:12:39
MP- 3 |  | City Wide | Tier 1 | Quick Response Projects | TSPLOST2 | Mountain Park | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Mountain Park | 2022-03-31
MP- 4 |  | City Wide | Tier 2 | Quick Response Projects | TSPLOST2 | Mountain Park | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Mountain Park | 2022-03-31
MP- 5 |  | City Wide | Tier 3 | Quick Response Projects | TSPLOST2 | Mountain Park | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Mountain Park | 2022-03-31
MTP- 1 | Russell Road Pipe Replacement | Russell Road Pipe Replacement | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Mountain Park | Bidding | Russell Road located in the City of Mountain Park has two 30 inch pipes that are deteriorated with the bottoms of the corrugated metal pipe gone. This is a very deep fill section and the pipes are over 20 below the surface of the road. The road is also the only way in and out for the houses past the pipes and if the road were to fail they would be forced to use the Dam emergency access road. The City of Mountain Park desires to have these pipes replaced while also keeping the road open to the public. | TBD | Integrated Science and Engineering | December, 2021 | January, 2022 | March, 2022 | February, 2022 |  | Sales Tax | $300,000 | $0 | $300,000 | Green | Green | Active | djohnson@intse.com | 2021 | 2021-09-30 13:18:50
MTP- 2 | Mountain Park | Pipe Lining Various Pipes under Public Roads | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Mountain Park | Design | Mountain Park desires to use the remaining portion of the first wave of TSPLOST toward the relining of storm pipes that cross under several significant roads within the City Limits. The pipes have already been inspected and identified and should be out to bid by Jan. 2022 | TBD | Integrated Science and Engineering | December, 2021 | January, 2022 | March, 2022 | February, 2022 |  | Sales Tax | $165,308 | $0 | $165,308 | Green | Green | Active | djohnson@intse.com | 2022 | 2021-09-30 13:20:10
PA- 10 | PA-304 | Quick Response Projects | Tier 3 | Quick Response | TSPLOST | Palmetto | Planning | Quick Response Projects in City of Palmetto | [7 empty] | Sales Tax | $77,577 | $0 | $77,577 | Gray | Gray | Active | whshell@citypalmetto.com
PA- 11 | PA-201 | Maintenance and Safety Enhancements | Tier 2 | Maintenance and Safety Enhancements | TSPLOST | Palmetto | Planning | Maintenance and Safety Enhancements in City of Palmetto | [7 empty] | Sales Tax | $488,884 | $0 | $488,884 | Gray | Gray | Active | whshell@citypalmetto.com
PA- 12 | PA-202 | Operations and Safety | Tier 2 | Operation and Safety Improvements | TSPLOST | Palmetto | Planning | Operations and Safety in City of Palmetto | [7 empty] | Sales Tax | $18,118 | $0 | $18,118 | Gray | Gray | Active | whshell@citypalmetto.com
PA- 13 | PA-203 | Pedestrian/Bike/Streetscape Projects | Tier 2 | Pedestrian and Bike Improvements | TSPLOST | Palmetto | Planning | Pedestrian/Bike/Landscape/Streetscape Projects in City of Palmetto | [7 empty] | Sales Tax | $70,915 | $0 | $70,915 | Gray | Gray | Active | whshell@citypalmetto.com
PA- 14 | PA-204 | Quick Response Projects | Tier 2 | Quick Response | TSPLOST | Palmetto | Planning | Quick Response Projects in City of Palmetto | [7 empty] | Sales Tax | $75,000 | $0 | $75,000 | Gray | Gray | Active | whshell@citypalmetto.com
PA- 15 |  | Resurfacing | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | Palmetto | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Palmetto | 2022-03-31
PA- 16 |  | City Wide | Tier 1 | Quick Response Projects | TSPLOST2 | Palmetto | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Palmetto | 2022-03-31
PA- 17 |  | Resurfacing | Tier 2 | Maintenance and Safety Enhancements | TSPLOST2 | Palmetto | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Palmetto | 2022-03-31
PA- 18 |  | City Wide | Tier 2 | Quick Response Projects | TSPLOST2 | Palmetto | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Palmetto | 2022-03-31
PA- 19 |  | Resurfacing | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | Palmetto | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Palmetto | 2022-03-31
PA- 2 | PA-101 | Maintenance and Safety Enhancements | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Palmetto | Completed | Maintenance and Safety Enhancements in City of Palmetto Resurfacing roads: Johnson Road, Hutcheson Ferry Road, Green Springs Terrace, Green Springs Court, Fair Street, Sable Drive, Laurel Drive, Tiffany Lane, Phipps Road, Waterworks Road | E R Snell |  |  | December, 2018 | June, 2019 | June, 2019 |  | Sales Tax | $2,770,344 | $807,605 | $1,962,739 | Green | Green | Active | hanson@citypalmetto.com | 2019 | 2021-05-04 14:38:41
PA- 20 |  | City Wide | Tier 3 | Quick Response Projects | TSPLOST2 | Palmetto | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Palmetto | 2022-03-31
PA- 3 | PA-111 | Operations and Safety- Phipps Rd/Fayetteville Rd Intersection | Tier 1 | Operation and Safety Improvements | TSPLOST | Palmetto | Planning | Operations and Safety in City of Palmetto Round-about for the intersection of Phipps Road and Fayetteville Road |  | Gresham Smith | December, 2020 | December, 2021 | June, 2022 |  |  | Sales Tax | $102,671 | $19,228 | $83,443 | Gray | Gray | Active | hanson@citypalmetto.com |  | 2021-05-04 15:37:27
PA- 4 | PA-112/113 | Pedestrian/Bike/Streetscape Projects | Tier 1 | Operation and Safety Improvements | TSPLOST | Palmetto | Planning | Pedestrian/Bike/Landscape/Streetscape Projects in City of Palmetto | [7 empty] | Sales Tax | $401,850 | $0 | $401,850 | Gray | Gray | Active | whshell@citypalmetto.com
PA- 5 | PA-101 | Maintenance and Safety Enhancements | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Palmetto | Planning | Maintenance and Safety Enhancements in City of Palmetto | [7 empty] | Sales Tax | $2,770,344 | $0 | $2,770,344 | Gray | Gray | Active | whshell@citypalmetto.com
PA- 6 | PA-114 | Quick Response Projects | Tier 1 | Quick Response | TSPLOST | Palmetto | Planning | Quick Response Projects in City of Palmetto | [7 empty] | Sales Tax | $425,000 | $0 | $425,000 | Gray | Gray | Active | whshell@citypalmetto.com
PA- 7 | PA-301 | Maintenance and Safety Enhancements | Tier 3 | Operation and Safety Improvements | TSPLOST | Palmetto | Planning | Maintenance and Safety Enhancements in City of Palmetto | [7 empty] | Sales Tax | $488,884 | $0 | $488,884 | Gray | Gray | Active | whshell@citypalmetto.com
PA- 8 | PA-302 | Operations and Safety | Tier 3 | Operation and Safety Improvements | TSPLOST | Palmetto | Planning | Operations and Safety in City of Palmetto | [7 empty] | Sales Tax | $18,118 | $0 | $18,118 | Gray | Gray | Active | whshell@citypalmetto.com
PA- 9 | PA-303 | Pedestrian/Bike/Streetscape Projects | Tier 3 | Pedestrian and Bike Improvements | TSPLOST | Palmetto | Planning | Pedestrian/Bike/Landscape/Streetscape Projects in City of Palmetto | [7 empty] | Sales Tax | $70,915 | $0 | $70,915 | Gray | Gray | Active | whshell@citypalmetto.com
ROS- 10 |  | Intersection and Corridor Improvements | Tier 3 | Operation and Safety Improvements | TSPLOST | Roswell | Planning | General intersection and corridor improvements, including geometric redesign, reconstruction of corridors as complete streets, mini-roundabouts and full roundabouts. Specific corridors under consideration include but are not limited to Nesbit Ferry Road, enhancements to Old Alabama Road (in conjunction with GDOT), and the Myrtle Street extension. Program is subject to availability of additional funding remaining after Tier 1 and Tier 2 projects are completed. | [6 empty] | https://www.roswellgov.com/government/departments/transportation/t-splost-projects | Sales Tax | $14,011,490 | $0 | $14,011,490 | Gray | Gray | Active | dcox@roswellgov.com |  | 2023-04-14 16:19:52
ROS- 11 |  | Old Alabama Rd Multi-use Trail (Market Blvd to Holcomb Woods Pkwy) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Roswell | Concept | Multi-use path on Old Alabama Road from Market Blvd to Holcomb Woods Pkwy. |  | NV5 (concept) | July, 2024 |  |  |  | https://www.roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $2,000,000 | $0 | $2,000,000 | Green | Green | Active | dcox@roswellgov.com |  | 2024-03-05 17:14:22 | Georgia | Old Alabama Rd | 2022-03-31
ROS- 12 |  | Old Alabama Rd Multi-use Trail (Holcomb Woods Pkwy to Big Creek Park) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Roswell | Concept | Multi-use trail (one side of road) between Holcomb Woods Parkway northward to Big Creek Park entrance. |  | NV5 (concept) |  |  |  |  | roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $640,000 | $0 | $640,000 | Green | Green | Active | dcox@roswellgov.com |  | 2023-08-04 09:01:57 | Georgia | Old Alabama Rd | 2022-03-31
ROS- 13 |  | Woodstock Road Multi-Use Trail | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Roswell | Design | Project will add a new multi-use trail along Woodstock Road from Canton Street to SR-92 / Woodstock Rd / Crossville Rd. |  | KCI Technologies Inc. | December, 2024 |  |  |  | https://www.roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $7,142,635 | $64,006 | $7,078,629 | Green | Green | Active | dcox@roswellgov.com |  | 2023-08-04 09:06:03 | Georgia | Woodstock Road | 2022-03-31
ROS- 14 |  | Holcomb Bridge Road Multi-Use Trail (Boston Market to Martin Landing Dr) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Roswell | Planning | Multi-use trail (one side of road) | [6 empty] | roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $1,600,000 | $0 | $1,600,000 |  |  | Active | dcox@roswellgov.com |  | 2023-04-13 17:03:23 | Georgia | Holcomb Bridge Road | 2022-03-31
ROS- 15 |  | Holcomb Bridge Road Multi-Use Trail (Martins Landing Dr to Eves Rd) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Roswell | Planning | Multi-use trail (one side of road) | [6 empty] | roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $2,800,000 | $0 | $2,800,000 |  |  | Active | dcox@roswellgov.com |  | 2023-04-13 17:02:53 | Georgia | Holcomb Bridge Road | 2022-03-31
ROS- 16 |  | River Eves Elementary School Multi-use Trail (off system trail) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Roswell | Planning | Multi-Use Trail | [6 empty] | roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $700,000 | $0 | $700,000 |  |  | Active | dcox@roswellgov.com |  | 2023-04-13 17:02:09 | Georgia | River Eves Elementary School | 2022-03-31
ROS- 17 |  | Chattahoochee River Parks Multi-Use Trail Rehab | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Roswell | Planning | Milling and replacement of the existing asphalt trail surface, including restoration and repairs to certain portions of the boardwalk system prone to flood impacts. | [6 empty] | roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $2,195,750 | $0 | $2,195,750 |  |  | Active | dcox@roswellgov.com |  | 2023-04-13 17:01:32 | Georgia | City of Roswell | 2022-03-31
ROS- 18 |  | Riverside Road Corridor Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Roswell | Design | The Riverside Road Corridor Improvements will reconstruct the roadway corridor to include new sidewalks, bike lanes, and a multi-use trail between Riverside Park and Old Alabama Road near the GA-400 underpass and Don White Park. |  | Michael Baker Int'l | June, 2024 |  |  |  | https://www.roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $8,775,000 | $188,394 | $8,586,606 | Green | Green | Active | dcox@roswellgov.com |  | 2023-08-04 11:23:41 | Georgia | Riverside Road | 2022-03-31
ROS- 19 |  | Nesbit Ferry Rd ΓÇô Corridor Improvement with Johns Creek | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Roswell | Concept | Project will construct new operational improvements and some pedestrian facilities in various locations between SR-140/Holcomb Bridge Road and a point near Old Alabama Road in Johns Creek. The project runs along the city boundary between Roswell and Johns Creek. City of Johns Creek is the lead on the project and is paying the majority of the project costs, Roswell's share is only $1,000,000 million. |  | Practical Design Partners |  |  |  |  | https://www.roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $1,000,000 | $0 | $1,000,000 | Green | Green | Active | dcox@roswellgov.com |  | 2023-08-04 11:25:11 | Georgia | Nesbit Ferry Rd | 2022-03-31
ROS- 2 |  | Big Creek Parkway | Tier 1 | Operation and Safety Improvements | TSPLOST | Roswell | Design | This project is being constructed in 2 Phases. Phase 1 will widen Warsaw Road near Holcomb Bridge Road (SR 140) and add New (dual) left turn lanes on SR 140 Holcomb Bridge Road turning onto Warsaw Road. The project will also add new dual left turn lanes from southbound Warsaw Road turning left onto Holcomb Bridge Road eastbound. Phase 1 construction began in Spring 2021 and utility work is underway. Phase 1 of the project is currently on schedule and on budget. Phase 2 will construct a new two-lane Complete Street Roadway including bike lanes, sidewalks, and multi-use path from Warsaw Road moving east on new alignment before crossing over GA-400 and then connecting to Old Alabama Road near Holcomb Woods Parkway. Design on Phase 2 is continuing and Construction is anticipated to begin in 2023. Funding spent may include funds paid to contractors/consultants or indicate encumbered funds set aside for future payments. Phase 2 is currently more than 90 days behind schedule. In December of 2023, the Mayor and Council voted to modify the project alignment back to the original 2016 alignment. |  | Gresham Smith and Partners | December, 2026 | April, 2027 | December, 2030 |  | https://www.roswellgov.com/government/departments/transportation/t-splost-projects | Sales Tax | $43,536,802 | $5,598,604 | $37,938,198 | Red | Red | Active | dcox@roswellgov.com |  | 2024-03-05 17:03:04
ROS- 20 |  | Corridor Improvements for Grimes Bridge, Dogwood, Old Dogwood Roads | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Roswell | Concept | The project will examine the feasibility of improvements to both Grimes Bridge Road and portions of Dogwood Road. Potential improvements may include new multi-use trail, sidewalks, or intersection improvements |  | VHB | July, 2025 |  |  |  | https://www.roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $10,500,000 | $0 | $10,500,000 | Green | Green | Active | dcox@roswellgov.com |  | 2024-03-05 17:08:17 | Georgia | Grimes Bridge | 2022-03-31
ROS- 21 |  | Big Creek Pkwy phase 2 ΓÇô Warsaw Connection | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Roswell | Planning | Extend Big Creek Parkway to Warsaw Road with bike/pedestrian accommodations. Please note this is in connection with the Big Creek Parkway project listed in TSPLOST 1 |  |  | December, 2026 | April, 2027 | December, 2030 |  | roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $5,000,000 | $0 | $5,000,000 |  |  | Active | dcox@roswellgov.com |  | 2024-03-05 17:13:11 | Georgia | Warsaw | 2022-03-31
ROS- 22 |  | Old Ellis Rd Extension | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Roswell | Planning | Extend Old Ellis Road to Sun Valley Road, multi-use trail, sidewalk, bike lane, and intersection improvements | [6 empty] | roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $6,000,000 | $0 | $6,000,000 |  |  | Active | dcox@roswellgov.com |  | 2023-04-13 16:59:45 | Georgia | Old Ellis Rd | 2022-03-31
ROS- 23 |  | Cox Road Intersection Improvements (at Etris Rd and at King Rd) | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Roswell | Concept | Project will construct new intersection improvements on Cox Road at both King Road and at Etris Road.. Per Agreement with City of Milton, Milton is lead on project |  | Pond |  |  |  |  | https://www.roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $1,000,000 | $0 | $1,000,000 | Green | Green | Active | dcox@roswellgov.com |  | 2024-03-05 17:11:41 | Georgia | Cox Road | 2022-03-31
ROS- 24 |  | Norcross Street Bridge Replacement | Tier 1 | Bridges | TSPLOST2 | Roswell | Concept | Bridge Replacement of Norcross Street bridge over Hog Waller Creek |  | Barge Design Solutions | December, 2026 |  |  |  | roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $4,200,000 | $0 | $4,200,000 |  |  | Active | dcox@roswellgov.com |  | 2024-03-05 17:06:40 | Georgia | Norcross Street | 2022-03-31
ROS- 25 |  | Pine Grove Rd / Magnolia St Corridor Improvements (Mimosa Blvd to Lake Charles Rd) | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Roswell | Concept | Corridor project along the Pine Grove Road corridor that will include improvements son portions of the project such as Multi-use trail, sidewalk, and intersection improvements |  | Gresham Smith | December, 2025 |  |  |  | https://www.roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $6,900,000 | $0 | $6,900,000 |  |  | Active | dcox@roswellgov.com |  | 2024-03-05 17:10:15 | Georgia | Pine Grove Rd | 2022-03-31
ROS- 26 |  | Pine Grove Rd Corridor Improvements (Lake Charles Rd to Cobb County) | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Roswell | Concept | Improvements on the Pine Grove Road corridor may include improvements on portions of the roadway such as Multi-use trail, sidewalk, and intersection improvements |  | Gresham Smith | December, 2025 |  |  |  | roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $7,935,000 | $0 | $7,935,000 |  |  | Active | dcox@roswellgov.com |  | 2024-03-05 17:10:54 | Georgia | Pine Grove Rd | 2022-03-31
ROS- 27 |  | Bike/Ped Master Plan/Creek way Trails Implementation such as Hog Wallow Creek Trail | Tier 2 | Pedestrian and Bike Improvements | TSPLOST2 | Roswell | Planning | Bicycle and pedestrian improvements as identified by Mayor and Council which could include sidewalks, multi-use trails, bike lanes, creek way trails, and other enhancements | [6 empty] | https://www.roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $3,877,000 | $0 | $3,877,000 |  |  | Active | dcox@roswellgov.com |  | 2023-04-13 16:55:50 | Georgia | City of Roswell | 2022-03-31
ROS- 28 |  | Intersection Improvements | Tier 2 | Operation and Safety Improvements | TSPLOST2 | Roswell | Planning | Intersection improvements as identified by Mayor and Council which could include turn lane improvements, operational improvements and roundabouts | [6 empty] | https://www.roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $3,550,891 | $0 | $3,550,891 |  |  | Active | dcox@roswellgov.com |  | 2023-04-13 16:52:39 | Georgia | City of Roswell | 2022-03-31
ROS- 29 |  | Big Creek Greenway Boardwalk Repairs | Tier 2 | Maintenance and Safety Enhancements | TSPLOST2 | Roswell | Planning | Approximately 4,000 feet of elevated boardwalk in high prone flooding areas along the Big Creek Greenway | [6 empty] | https://www.roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $5,523,000 | $0 | $5,523,000 |  |  | Active | dcox@roswellgov.com |  | 2023-04-13 16:54:43 | Georgia | Big Creek Greenway | 2022-03-31
ROS- 3 |  | Oxbo Road at SR9 Intersection Improvement | Tier 1 | Operation and Safety Improvements | TSPLOST | Roswell | Construction | Redesign of the intersection of Oxbo Road and SR 9 creating a full intersection and adding a new traffic signal. The new intersection will be rebuilt just south of the existing SR 9 at Oxbo Road intersection. The project also extends Oxbo Road west to connect directly to Mimosa Blvd which provides connectivity. The project also will link Oxbo Road to Pleasant Hill Street and Elm Streets. Funding spent may include funds paid to contractors/consultants or indicate encumbered funds set aside for future payments. | ER Snell | Clark Patterson Lee, Inc. | June, 2019 | November, 2019 | December, 2022 | December, 2022 | https://www.roswellgov.com/government/departments/transportation/t-splost-projects | Sales Tax | $12,500,000 | $11,620,368 | $879,632 | Red | Red | Active | dcox@roswellgov.com |  | 2023-04-14 16:17:38
ROS- 30 |  | Bridge Replacement | Tier 3 | Bridges | TSPLOST2 | Roswell | Planning | Bridge replacements as identified by Mayor and Council | [6 empty] | https://www.roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $3,500,000 | $0 | $3,500,000 |  |  | Active | dcox@roswellgov.com |  | 2023-04-13 16:49:07 | Georgia | City of Roswell | 2022-03-31
ROS- 31 |  | Intersection Improvements | Tier 3 | Operation and Safety Improvements | TSPLOST2 | Roswell | Planning | Intersection improvements as identified by Mayor and Council which could include turn lane improvements, operational improvements and roundabouts | [6 empty] | https://www.roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $2,500,000 | $0 | $2,500,000 |  |  | Active | dcox@roswellgov.com |  | 2023-04-13 16:46:58 | Georgia | City of Roswell | 2022-03-31
ROS- 32 |  | Intelligent Transportation Systems - Master Plan Update and Implementation - Automated Vehicle Technology | Tier 3 | Operation and Safety Improvements | TSPLOST2 | Roswell | Planning | Update of City's ITS Master Plan and future implementation of the plan which could include automated vehicle technologies | [6 empty] | https://www.roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $3,000,000 | $0 | $3,000,000 |  |  | Active | dcox@roswellgov.com |  | 2023-04-13 16:45:30 | Georgia | City of Roswell | 2022-03-31
ROS- 33 |  | Bike / Ped Master Plan Implementation | Tier 3 | Pedestrian and Bike Improvements | TSPLOST2 | Roswell | Planning | Bicycle and pedestrian improvements as identified by Mayor and Council which could include sidewalks, multi-use trails, bike lanes, creek way trails, and other enhancements | [6 empty] | https://www.roswellgov.com/government/departments/transportation/tsplost2 | Sales Tax | $3,950,891 | $0 | $3,950,891 |  |  | Active | dcox@roswellgov.com |  | 2023-04-13 16:43:50 | Georgia | City of Roswell | 2022-03-31
ROS- 4 |  | Highway 9 Gateway | Tier 1 | Operation and Safety Improvements | TSPLOST | Roswell | Land | Reconstruction of SR 9 from the Chattahoochee River north to Historic Roswell Square at SR 120 / Marietta Highway with new connections to the National Park Service Vickery Creek Unit. The project will remove the old reversible lane signal system and add one new lane in the off-peak direction so the roadway will have two lanes in each direction at all times. The project will new roundabouts and grade separate the intersection of SR 9 and Riverside Road / Azalea Drive. The majority of the roadway project is being funded by Federal and State funds from GDOT. Funding spent may include funds paid to contractors/consultants or indicate encumbered funds set aside for future payments. GDOT is currently doing right-of-way acquisition on the project. |  | WSP | May, 2023 |  | December, 2025 |  | https://www.roswellgov.com/government/departments/transportation/t-splost-projects | Sales Tax | $3,000,000 | $176,640 | $2,823,360 | Green | Green | Active | dcox@roswellgov.com |  | 2023-04-14 16:17:53
ROS- 5 |  | Rucker Road Complete Street | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Roswell | Completed | Reconstruction of Rucker Road from Roswell/Alpharetta City Limit boundary to GA-140/Arnold Mill Road/Houze Road Intersection. The project will include the addition of a multi-use path and sidewalk enhancements. Funding spent may include funds paid to contractors/consultants or indicate encumbered funds set aside for future payments. | CW Matthews | TY Lynn | December, 2018 | March, 2019 | April, 2021 | April, 2021 | https://www.roswellgov.com/government/departments/transportation/t-splost-projects | Sales Tax | $2,264,327 | $2,090,663 | $173,664 | Red | Green | Active | dcox@roswellgov.com |  | 2023-04-14 16:18:26
ROS- 6 |  | Holcomb Bridge Interchange | Tier 1 | Operation and Safety Improvements | TSPLOST | Roswell | Planning | Design for projects from the Holcomb Bridge Road Corridor Study, possibly including reconstruction of the bridges or ramps at the GA-400 interchange at Holcomb Bridge Road. Roswell has partnered with GDOT to help provide TSPLOST funding for the Holcomb Bridge Road interchange within Roswell as part of their GA-400 Express Lane project. The funding is being used to fund additional improvements and have GDOT reconstruct the existing interchange at Holcomb Bridge Road. In summer of 2021, GDOT announced they would be revisiting their GA-400 Express Lane project's schedule as construction bids at that time were not accepted. As this project is tied to GDOT's project timeline, Roswell is continuing to coordinate with GDOT on their plans moving forward regarding their GA-400 Express Lane project. | [6 empty] | https://www.roswellgov.com/government/departments/transportation/t-splost-projects | Sales Tax | $6,000,000 | $0 | $6,000,000 | Gray | Gray | Active | dcox@roswellgov.com |  | 2023-04-14 16:18:44
ROS- 7 |  | Old Holcomb Bridge Road Bridge Replacement | Tier 1 | Bridges | TSPLOST | Roswell | Planning | This project is the anticipated replacement of weight-restricted bridge on Old Holcomb Bridge Road bridge over Big Creek. This project's scope has been merged into the work scope of the Big Creek Parkway project. Construction along Old Holcomb Bridge Road (as part of the Big Creek Parkway project) is anticipated to begin in 2022. |  | In House |  |  |  |  | https://www.roswellgov.com/government/departments/transportation/t-splost-projects | Sales Tax | $3,086,390 | $24,975 | $3,061,415 | Green | Green | Active | dcox@roswellgov.com |  | 2023-04-14 16:19:02
ROS- 8 |  | Sidewalk Repair and Complete Streets Program | Tier 2 | Pedestrian and Bike Improvements | TSPLOST | Roswell | Planning | General sidewalk repair and gap filling based on the sidewalk prioritization inventory conducted in 2015. Priorities include connecting residential, commercial, and civic uses and completing gaps in heavily traveled areas. Where applicable, also includes construction of complete streets along corridors of the Roswell Loop. Program is subject to availability of additional funding remaining after Tier 1 projects are completed. | [6 empty] | https://www.roswellgov.com/government/departments/transportation/t-splost-projects | Sales Tax | $7,000,000 | $0 | $7,000,000 | Gray | Gray | Active | dcox@roswellgov.com |  | 2023-04-14 16:19:19
ROS- 9 |  | Safety Improvements and Maintenance | Tier 2 | Maintenance and Safety Enhancements | TSPLOST | Roswell | Planning | General safety and maintenance projects, such as replacement of obsolete guardrails, replacement of weight-restricted bridges, minor intersection improvements, and road resurfacing and rehabilitation. Program is subject to availability of additional funding remaining after Tier 1 projects are completed. | [6 empty] | https://www.roswellgov.com/government/departments/transportation/t-splost-projects | Sales Tax | $6,956,422 | $0 | $6,956,422 | Gray | Gray | Active | dcox@roswellgov.com |  | 2023-04-14 16:19:36
UC- 10 | US-109 | Quick Response Projects | Tier 1 | Quick Response | TSPLOST | Union City | Completed | Quick Response Projects in Union City - Quick Response Projects | The Corbett Group | Atlas | March, 2019 | April, 2019 | August, 2019 | August, 2019 | https://www.unioncityga.org/departments/public-services/capital-projects | Sales Tax | $235,687 | $107,077 | $128,610 | Green | Green | Active | Lonnie Ferguson |  | 2023-02-27 15:31:46
UC- 11 | UC-201 | Maintenance and Safety Enhancements | Tier 2 | Maintenance and Safety Enhancements | TSPLOST | Union City | Planning | Maintenance and Safety Enhancements in Union City - Resurfacing | [7 empty] | Sales Tax | $300,000 | $0 | $300,000 | Gray | Gray | Active | lferguson@unioncityga.org |  | 2021-05-04 21:09:25
UC- 12 | UC-202 | Operations and Safety | Tier 2 | Operation and Safety Improvements | TSPLOST | Union City | Planning | Operations and Safety in Union City - Jonesboro Road (SR 14 to Buffington Rd) | [7 empty] | Sales Tax | $841,152 | $0 | $841,152 | Gray | Gray | Active | lferguson@unioncityga.org |  | 2021-05-04 21:09:43
UC- 13 | UC-203 | Operations and Safety Improvements | Tier 2 | Operation and Safety Improvements | TSPLOST | Union City | Planning | Operations and Safety in Union City - Highpoint Road (SR 14 to Dodson Rd) | [7 empty] | Sales Tax | $711,150 | $0 | $711,150 | Gray | Gray | Active | lferguson@unioncityga.org |  | 2021-05-04 21:08:42
UC- 14 | UC-204 | Operations and Safety | Tier 2 | Operation and Safety Improvements | TSPLOST | Union City | Planning | Operations and Safety in Union City - Oakley Rd from Jonesboro Rd/SR 138 south to the city limits | [7 empty] | Sales Tax | $295,775 | $0 | $295,775 | Gray | Gray | Active | lferguson@unioncityga.org |  | 2021-05-04 21:09:06
UC- 15 | UC-205 | Operations and Safety | Tier 2 | Operation and Safety Improvements | TSPLOST | Union City | Planning | Operations and Safety in Union City - Gresham St at Jonesboro Rd Improvements | [7 empty] | Sales Tax | $558,831 | $0 | $558,831 | Gray | Gray | Active | lferguson@unioncityga.org |  | 2021-05-04 21:10:03
UC- 16 | UC-206 | Quick Response Projects | Tier 3 | Quick Response | TSPLOST | Union City | Design | Quick Response Projects in Union City - Quick Response Projects | TBD | Atlas | April, 2021 | August, 2021 | February, 2023 | March, 2023 |  | Sales Tax | $235,686 | $0 | $235,686 | Red | Green | Active | lferguson@unioncityga.org | 2022 | 2021-02-02 19:53:06
UC- 17 | UC-301 | Maintenance and Safety Enhancements | Tier 3 | Maintenance and Safety Enhancements | TSPLOST | Union City | Planning | Maintenance and Safety Enhancements in Union City - Resurfacing | [7 empty] | Sales Tax | $1,715,484 | $0 | $1,715,484 | Gray | Gray | Active | lferguson@unioncityga.org |  | 2021-05-04 21:10:21
UC- 18 | UC-302 | Bridges | Tier 3 | Bridges | TSPLOST | Union City | Planning | Bridge Improvement in Union City - McClure at Line Creek | [7 empty] | Sales Tax | $44,000 | $0 | $44,000 | Gray | Gray | Active | lferguson@unioncityga.org |  | 2021-05-04 21:10:39
UC- 19 | UC-303 | Bridges | Tier 3 | Bridges | TSPLOST | Union City | Planning | Bridge Improvement in Union City - Peters Rd at Broadnax Creek | [7 empty] | Sales Tax | $44,000 | $0 | $44,000 | Gray | Gray | Active | lferguson@unioncityga.org |  | 2021-05-04 21:10:55
UC- 2 | UC-101 | Congestion Relief/Roadway Projects | Tier 1 | Congestion Relief | TSPLOST | Union City | Design | Congestion Relief in Union City - I-85/SR 138 Interchange (PARTIAL FUNDING) | TBD | WSP USA | August, 2023 | December, 2023 | December, 2025 | November, 2025 | http://www.dot.ga.gov | Sales Tax | $5,000,000 | $1,065,284 | $3,934,716 | Green | Red | Active | Lonnie Ferguson | 2026 | 2023-02-27 15:30:54
UC- 20 | UC-304 | Bridges | Tier 3 | Bridges | TSPLOST | Union City | Planning | Bridge Improvement in Union City - Highpoint Rd at Deep Creek | [7 empty] | Sales Tax | $44,000 | $0 | $44,000 | Gray | Gray | Active | lferguson@unioncityga.org |  | 2021-05-04 21:11:09
UC- 21 | UC-305 | Bridges | Tier 3 | Bridges | TSPLOST | Union City | Planning | Bridge Improvement in Union City - Buffington Rd at Shannon Creek | [7 empty] | Sales Tax | $44,000 | $0 | $44,000 | Gray | Gray | Active | lferguson@unioncityga.org |  | 2021-05-04 21:11:22
UC- 22 | UC-306 | Operations and Safety | Tier 3 | Operation and Safety Improvements | TSPLOST | Union City | Planning | Operations and Safety in Union City - Buffington Road (SR 138 to Flat Shoals Rd) | [7 empty] | Sales Tax | $670,350 | $0 | $670,350 | Gray | Gray | Active | lferguson@unioncityga.org |  | 2021-05-04 21:52:28
UC- 23 | UC-307 | Pedestrian/Bike/Landscape/Streetscape Projects | Tier 3 | Pedestrian and Bike Improvements | TSPLOST | Union City | Design | Pedestrian/Bike Improvements in Union City - Roosevelt Hwy (US29) (Lower Dixie Lake Road to Stonewall Tell Road) | TBD | Atlas | April, 2021 | July, 2021 | November, 2020 | December, 2021 |  | Sales Tax | $496,069 | $0 | $496,069 | Green | Green | Active | lferguson@unioncityga.org | 2021 | 2021-02-02 19:59:33
UC- 24 | UC-308 | Quick Response Projects | Tier 3 | Quick Response | TSPLOST | Union City | Planning | Quick Response Projects in Union City - Quick Response Projects | [7 empty] | Sales Tax | $26,814 | $0 | $26,814 | Gray | Gray | Active | lferguson@unioncityga.org |  | 2021-05-04 21:52:43
UC- 25 |  | Dixie Lake Road at SR14/Roosevelt Highway Intersection Improvements | Tier 1 | Congestion Relief | TSPLOST2 | Union City | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Dixie Lake Road | 2022-03-31
UC- 26 |  | Raymond Drive & Raymond Terrace Resurfacing & Sidewalk Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Union City | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | Raymond Drive | 2022-03-31
UC- 27 |  | Resurfacing of Various Corridors | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | Union City | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Union City | 2022-03-31
UC- 28 |  | Union City Pedestrian & Cyclist Greenway Trail | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Union City | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Union City | 2022-03-31
UC- 29 |  | City Wide | Tier 1 | Quick Response Projects | TSPLOST2 | Union City | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Union City | 2022-03-31
UC- 3 | UC-102 | Maintenance and Safety Enhancements | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Union City | Construction | Maintenance and Safety Enhancements in Union City - Resurfacing at Various Locations | Stewart Brothers Inc. | Atlas | April, 2022 | May, 2020 | April, 2023 | April, 2023 | https://www.unioncityga.org/departments/public-services/capital-projects | Sales Tax | $9,511,323 | $3,693,395 | $5,817,928 | Green | Green | Active | Lonnie Ferguson | 2023 | 2023-02-27 15:12:47
UC- 30 |  | Pedestrian Improvements on Various Corridors | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Union City | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Union City | 2022-03-31
UC- 31 |  | Resurfacing of Various Corridors | Tier 2 | Maintenance and Safety Enhancements | TSPLOST2 | Union City | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Union City | 2022-03-31
UC- 32 |  | SR138 Sidewalks & Gateway Improvements | Tier 2 | Pedestrian and Bike Improvements | TSPLOST2 | Union City | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | SR138 | 2022-03-31
UC- 33 |  | Union City Pedestrian & Cyclist Greenway Trail | Tier 2 | Pedestrian and Bike Improvements | TSPLOST2 | Union City | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Union City | 2022-03-31
UC- 34 |  | Resurfacing of Various Corridors | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | Union City | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Union City | 2022-03-31
UC- 35 |  | Union City Pedestrian & Cyclist Greenway Trail | Tier 3 | Pedestrian and Bike Improvements | TSPLOST2 | Union City | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Union City | 2022-03-31
UC- 36 |  | Pedestrian Improvements on Various Corridors | Tier 3 | Pedestrian and Bike Improvements | TSPLOST2 | Union City | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Union City | 2022-03-31
UC- 37 |  | City Wide | Tier 3 | Quick Response Projects | TSPLOST2 | Union City | Planning | [8 empty] | Sales Tax |  |  | $0 |  |  | Active |  |  |  | Georgia | City of Union City | 2022-03-31
UC- 4 | UC-103 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | Union City | Completed | Operations and Safety in Union City - Flat Shoals Road Resurfacing and Streetscape Project (From Westbrook St to Oakley Rd) | Mullins Brothers Paving Contractors | Lowe Engineers | December, 2018 | April, 2019 | August, 2019 | April, 2020 | https://www.unioncityga.org/departments/public-services/capital-projects | Sales Tax | $418,624 | $995,318 | $-576,694 | Red | Green | Active | Lonnie Ferguson | 2020 | 2023-02-27 15:12:10
UC- 5 | UC-104 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | Union City | Design | Operations and Safety in Union City - Lancaster Lane (Shannon Pkwy to Shannon Way) | TBD | Atlas | April, 2023 | September, 2024 | April, 2023 | May, 2023 | https://www.unioncityga.org/departments/public-services/capital-projects | Sales Tax | $274,010 | $30,186 | $243,824 | Gray | Gray | Inactive | lferguson@unioncityga.org | 2023 | 2023-02-27 15:31:06
UC- 6 | UC-105 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | Union City | Design | Operations and Safety in Union City - Londonderry Way (SR 138 to Mall Blvd) | TBD | Atlas | August, 2022 | September, 2023 | July, 2024 | August, 2024 |  | Sales Tax | $566,210 | $104,761 | $461,449 | Yellow | Red | Active | Lonnie Ferguson | 2023 | 2023-02-27 15:11:34
UC- 7 | UC-106 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | Union City | Design | Operations and Safety in Union City - Goodson Rd from Union City Limits to Jonesboro Rd | Backbone Infrastructure | Keck & Wood, Inc | January, 2022 | July, 2022 | March, 2023 | April, 2023 |  | Sales Tax | $588,000 | $489,260 | $98,740 | Red | Green | Active | lferguson@unioncityga.org | 2023 | 2023-02-27 15:15:05
UC- 8 | UC-107 | Pedestrian/Bike/Landscape/Streetscape | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Union City | Completed | Pedestrian/Bike/Landscape/Streetscape in Union City - Christian City Multi-Use Trail | Sol Construction | Lowe Engineers | May, 2022 | June, 2022 | November, 2022 | December, 2022 | https://www.unioncityga.org/departments/public-services/capital-projects | Sales Tax | $525,000 | $1,141,187 | $-616,187 | Red | Green | Active | lferguson@unioncityga.org | 2022 | 2023-02-27 15:31:26
UC- 9 | UC-108 | Pedestrian/Bike/Landscape/Streetscape | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Union City | Completed | Pedestrian/Bike/Landscape/Streetscape in Union City - Lower Dixie Lake Rd Sidewalks | Magnum Paving | Atlas | August, 2022 | September, 2022 | November, 2022 | December, 2022 | https://www.unioncityga.org/departments/public-services/capital-projects | Sales Tax | $203,500 | $904,300 | $-700,800 | Red | Green | Active | Lonnie Ferguson | 2022 | 2023-02-27 15:25:30
[17 empty] | SUM = 1,336,287,302 | SUM = 142,586,760,300 | SUM = -141,250,472,998