## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 100 | RST 208 | Merrywood I-III (LL 159/162 Dist 13) | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | The primary work is to resurface the final asphalt topping layer. The roads (Merrywood Ct, Merrywood Dr, and Smokeridge Dr) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work includes all necessary preparation work (e.g., full depth patching and a single surface treatment). The roads will then have the final asphalt topping layer installed in a manner that will provide uniformity of the asphalt. Milling of the existing asphalt surface is not expected to be required for these roadways. | E R Snell | Not Applicable | Not Applicable | March, 2018 | August, 2018 | Not Applicable |  | Sales Tax | $94,383 | $97,351 | $-2,968 | Red | Green | Active | roussan.francois@fultoncountyga.gov | 2017 | 2021-05-03 16:40:02
[17 empty] | SUM = 94,383 | SUM = 97,351 | SUM = -2,968