## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 131 | RS 321 | Creel Crossing | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Planning | The roads (Lupine Court, Lupine Court Cul-de-Sac, Lupine Ridge Lane, Woodhue Court, and Woodhue Forest Lane) within the subdivision to be resurfaced may have either existing concrete curb and gutter sections or will be flush with the shoulder of the road. The work will include all necessary preparation work (e.g., full depth patching, milling, and single surface treatment). The roads will then be resurfaced in a manner that will provide uniformity of the asphalt. After resurfacing, all existing pavement markings such as line striping will be reinstalled. | CW Matthews | Not Applicable | Not Applicable |  | July, 2020 |  |  | Sales Tax | $80,455 | $67,533 | $12,922 | Green | Green | Inactive | roussan.francois@fultoncountyga.gov | 2019 | 2021-02-07 00:00:42
[17 empty] | SUM = 80,455 | SUM = 67,533 | SUM = 12,922