## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 268 | RS 422 | Jailette Estates | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Completed | Deep base repair as needed, milling and resurface Completed in 2021 under TSPLOST 1 -2020 | CW Mathews |  | Not Applicable | August, 2020 | April, 2021 | April, 2021 |  | Sales Tax | $125,000 | $125,000 | $0 | Green | Green | Inactive | jeff.mueller@cityofsouthfultonga.gov | 2021 | 2023-02-28 20:50:22 | Georgia | Jailette Estates | 2022-03-31
[17 empty] | SUM = 125,000 | SUM = 125,000 | SUM = 0