## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 272 | RS 427 | Loch Lomond | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | City of South Fulton | Bidding | Deep base repair as needed, milling and resurface Loch Lomond Trail, New Hope Rd (north side) to End |  |  | Not Applicable | April, 2025 | August, 2025 | August, 2025 |  | Sales Tax | $67,000 | $0 | $67,000 |  |  | Active | jeff.mueller@cityofsouthfultonga.gov | 2025 | 2023-02-28 21:27:50 | Georgia | Loch Lomond | 2022-03-31
[17 empty] | SUM = 67,000 | SUM = 0 | SUM = 67,000