## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 283 | T 276 | Cochran Road over Deep Creek | Tier 1 | Bridges | TSPLOST2 | City of South Fulton | Land | The proposed project will replace the bridge carrying Cochran Road over Deep Creek. The project begins 280 ft. south of the existing bridge and ends 280 ft. north of the existing bridge. This project would replace the existing substandard bridge over Deep Creek with a new structure and new roadway approaches. The proposed mainline will consist of two 11Æ-0ö travel lane and curb and gutter in each direction. Sidewalks will be constructed in each direction for the full project length. A 2.0Æ buffer will be provided between the sidewalk and curb. |  | Long Engineering | December, 2022 | March, 2023 | February, 2024 |  |  | Sales Tax | $1,530,000 | $160,000 | $1,370,000 |  | Yellow | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-03-02 20:49:31 | Georgia | Cochran Road | 2022-03-31
[17 empty] | SUM = 1,530,000 | SUM = 160,000 | SUM = 1,370,000