## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 288 | T 271 | Fairburn Rd | Tier 1 | Bridges | TSPLOST2 | City of South Fulton | Bidding | The project is located on Fairburn Road, starting at Cascade Road and continuing to North Utoy Creek. The typical section includes 12' travel lanes, curb and gutter, a 10-foot multi-use path on the West side and a 6-foot wide sidewalk behind a 2-foot stamped concrete strip on the east side of Fairburn Road. Improvements also include bridge replacements at North and South Utoy Creek with bottomless culverts and turning lane improvements at the Fairburn Road/Cascade Road intersection. |  | Qk4 | November, 2022 | March, 2023 | September, 2024 | September, 2024 |  | Sales Tax | $3,372,000 | $37,000 | $3,335,000 |  | Yellow | Active | jeff.mueller@cityofsouthfultonga.gov | 2023 | 2023-03-02 20:58:17 | Georgia | Fairburn Rd | 2022-03-31
[17 empty] | SUM = 3,372,000 | SUM = 37,000 | SUM = 3,335,000