## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 51 | C2223 | Improved Crossing from Parking Deck to north side of Milton Ave | Tier 1 | Pedestrian Improvements | TSPLOST2 | Alpharetta | Completed | This project is for the construction of a midblock pedestrian crossing on Milton Avenue at Teasley Street, including a refuge area for pedestrians and installation of rectangular rapid flashing beacons (RRFBs). | Excellere Construction, LLC | PW | February, 2022 | October, 2022 | November, 2022 | November, 2022 | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3799/mid_block-crosswalk:-parking-deck-to-north-side-of-milton-ave-(tsplost_2;-tier_1) | Sales Tax | $212,300 | $212,300 | $0 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2022 | 2024-01-09 10:39:39 | Georgia | Milton Ave | 2022-03-31
[17 empty] | SUM = 212,300 | SUM = 212,300 | SUM = 0