## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 53 | C2221 | Mid-Block Crosswalk (Alpharetta Elementary School) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Alpharetta | Completed | This project is for the construction of a midblock pedestrian crossing on Mayfield Road at the intersection with the school entrance. The design includes installation of rectangular rapid flashing beacons (RRFBs). | Excellere Construction, LLC | PW | May, 2022 | July, 2022 | November, 2022 | August, 2022 | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3797/mid_block-crosswalk:-alpharetta-elementary-school-(tsplost_2,-tier_1) | Sales Tax | $113,037 | $113,037 | $0 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2022 | 2023-07-27 09:53:53 | Georgia | Alpharetta Elementary School | 2022-03-31
[17 empty] | SUM = 113,037 | SUM = 113,037 | SUM = 0