## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 55 | C2305 | Alpha Loop (Old Milton Pkwy to Northwinds Pkwy) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Alpharetta | Construction | This project is for the design and construction of the Alpha Loop Trail from the existing trail adjacent to the Chelsea Walk Subdivision to the existing trail off Northwinds Parkway. The trail is 12' wide and this particular section will consist of multiple bridges and a tunnel under Westisde Parkway. | Integrated Construction & Nobility (ICAN) |  | January, 2022 | September, 2022 | April, 2024 | April, 2024 | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3815/alpha-loop:-old-milton-pkwy-to-northwinds-(tsplost_2,-tier_1) | Sales Tax | $12,000,000 | $11,759,500 | $240,500 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2022 | 2024-01-09 10:22:36 | Georgia | Alpha Loop | 2022-03-31
[17 empty] | SUM = 12,000,000 | SUM = 11,759,500 | SUM = 240,500