## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 57 | C2227 | Mid-Block Crosswalk (Cogburn Road Park) | Tier 1 | Pedestrian Improvements | TSPLOST2 | Alpharetta | Completed | This project is for the construction of a midblock pedestrian crossing on Cogburn Road, in front of the Gatewood subdivision and Cogburn Road park. This includes a refuge area for pedestrians and installation of rectangular rapid flashing beacons (RRFBs). | Excellere Construction, LLC | PW | February, 2022 | September, 2022 | October, 2022 | October, 2022 | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3802/mid_block-crosswalk:-cogburn-rd-park-(tsplost_2,-tier_1) | Sales Tax | $149,401 | $149,391 | $10 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2022 | 2023-02-13 16:22:15 | Georgia | Cogburn Road Park | 2022-03-31
[17 empty] | SUM = 149,401 | SUM = 149,391 | SUM = 10