## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 60 | C2107 | North Point Pkwy Corridor | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Alpharetta | Design | This is to improve the safety, accessibility, and walkability of pedestrians along the North Point Parkway corridor from Mansell Road to Haynes Bridge Road. Some of the major elements that are considered in this project include reducing the number of travel lanes from 6 to 4 (both sides), 10' curb planter median bioswales, 12' multi-use trail, and 10' planting strip on both sides of the roadway. Also, energy efficient lighting, roadway condition monitoring, and green infrastructure monitoring systems are considered for this project. | TBD | Columbia Engineering | September, 2025 | November, 2022 | Not Applicable | Not Applicable | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3818/north-point-pkwy-corridor-(tsplost_2,-tier_1) | Sales Tax | $13,250,000 | $2,738,300 | $10,511,700 | Green | Green | Active | kmcdowell@alpharetta.ga.us | 2021 | 2024-01-09 10:19:35 | Georgia | North Point Pkwy | 2022-03-31
[17 empty] | SUM = 13,250,000 | SUM = 2,738,300 | SUM = 10,511,700