## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 62 | C2230 | Cumming St Corridor Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Alpharetta | Design | The project consists of design and construction of pedestrian and bike safety improvements along Cumming Street, between Highway 9 and Westside Parkway. The proposed project would add a sidewalk on the south side of Cumming Street: 1) from Cricket Lane to Clairmonte Ave, and 2) from where the sidewalk stops on the east side of Henderson Pkwy to Westside Pkwy. | Sol Construction LLC | Moffatt & Nichol | March, 2025 | July, 2022 | Not Applicable | August, 2026 | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3806/cumming-st-corridor-improvements-(tsplost_2,-tier_1) | Sales Tax | $7,758,000 | $4,562,000 | $3,196,000 | Green | Green | Active | imisbach@alpharetta.ga.us | 2022 | 2026-05-04 15:12:59 | Georgia | Cumming St | 2022-03-31
[17 empty] | SUM = 7,758,000 | SUM = 4,562,000 | SUM = 3,196,000