## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 68 | C2001 | Kimball Bridge Rd Widening (Verizon to Georgia Power driveways) | Tier 2 | Congestion Relief | TSPLOST2 | Alpharetta | Land | The project consists of widening Kimball Bridge Road between Verizon and Georgia Power driveways, on the west side of North Point Parkway, to provide a 4-lane section with appropriate pedestrian and bicycle facilities. Design, right-of-way and construction costs are estimated at $2 million and would be part of a future funding request. This improvement is on the approved TSPLOST 2 project list and funding may be available through TSPLOST 2 proceeds if revenue trends highlight collections in excess of what is needed to fund the currently appropriated TSPLOST 2 projects (Tier-1). | Gloson Enterprises | AECOM | February, 2024 | Not Applicable | Not Applicable | February, 2026 | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3807/kimball-bridge-rd-widening-_-verizon-to-georgia-power-driveways-(tsplost_2,-tier_2) | Sales Tax | $2,000,000 | $0 | $2,000,000 | Gray | Green | Active | imisbach@alpharetta.ga.us | 2022 | 2026-02-11 15:22:38 | Georgia | Kimball Bridge Rd | 2022-03-31
[17 empty] | SUM = 2,000,000 | SUM = 0 | SUM = 2,000,000