## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ALP- 70 | C3005 | Milling and Resurfacing | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | Alpharetta | Planning | This request is for the on-going maintenance of milling and resurfacing and preservation of city streets, funded through TSPLOST II. | Allied Paving | TBD | Not Applicable | Not Applicable | June, 2023 | Not Applicable | https://cleargov.com/georgia/fulton/city/alpharetta/projects/3813/milling-and-resurfacing-(tsplost_2,-tier_3) | Sales Tax | $2,500,000 | $0 | $2,500,000 | Gray | Gray | Active | kmcdowell@alpharetta.ga.us | 2022 | 2023-07-27 11:16:07 | Georgia | City of Alpharetta | 2022-03-31
[17 empty] | SUM = 2,500,000 | SUM = 0 | SUM = 2,500,000