## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CH- 10 |  | City Wide | Tier 1 | Project Management | TSPLOST2 | Chattahoochee Hills | Planning | traffic control, single pass chip seal, microsurfacing, thermoplastic solid traffic striping 5” white, thermoplastic solid traffic striping 5” yellow, thermoplastic traffic striping 24” white, thermoplastic skip traffic striping 5” white, and raised pavement markers single indicated on centerline for roadways identified by the engineers and public works director | Asphalt Paving Systems | Keck & Wood | June, 2024 | April, 2024 | June, 2024 | June, 2024 | https://www.chatthillsga.us/ | Sales Tax | $60,689 | $777 | $59,912 | Green | Green | Active | robbie.rokovitz@chatthillsga.us | 2024 | 2024-04-23 16:29:47 | Georgia | City of Chattahoochee Hills | 2024-04-23
[17 empty] | SUM = 60,689 | SUM = 777 | SUM = 59,912