## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CH- 13 |  | City Wide | Tier 2 | Project Management | TSPLOST2 | Chattahoochee Hills | Planning | deep patching on Rico Road (SFP to Hutcheson Ferry Road) utilizing 19mm asphalt, a 4” wide milling head at a depth of 4”, as well as 4” paint to repair existing striping damaged during construction | Piedmont Paving | Keck & Wood | August, 2024 | May, 2024 | August, 2024 | August, 2024 | https://www.chatthillsga.us/ | Sales Tax | $88,459 | $777 | $87,682 | Green | Green | Active | robbie.rokovitz@chatthillsga.us | 2024 | 2024-04-23 16:29:23 | Georgia | City of Chattahoochee Hills | 2024-04-23
[17 empty] | SUM = 88,459 | SUM = 777 | SUM = 87,682