## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CH- 14 |  | City Wide | Tier 3 | Maintenance and Safety Enhancements | TSPLOST2 | Chattahoochee Hills | Construction | deep patching on Rico Road (SFP to Hutcheson Ferry Road) utilizing 19mm asphalt, a 4” wide milling head at a depth of 4”, as well as 4” paint to repair existing striping damaged during construction | Piedmont Paving | Keck & Wood | August, 2024 | May, 2024 | August, 2024 | August, 2024 | https://www.chatthillsga.us/ | $269,180 from TSPLOST & $1,500.000 from Capital | $1,769,180 | $0 | $1,769,180 | Green | Green | Active | robbie.rokovitz@chatthillsga.us | 2024 | 2024-04-23 16:38:59 | Georgia | City of Chattahoochee Hills | 2024-04-23
[17 empty] | SUM = 1,769,180 | SUM = 0 | SUM = 1,769,180