## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
FA- 27 | 25-004 | City Wide Road Resurfacing | Tier 1 | Roadway Projects | TSPLOST2 | Fairburn | Construction | The City of Fairburn will accept sealed bids from qualified Contractors for furnishing all labor, equipment, and materials necessary to complete 4.1 mi of Roadway Improvements ON VARIOUS CITY ROADS Contract #25-004. The work includes milling, temporary traffic control, asphalt paving, manhole adjustments and associated tasks. The scope of Add Alternate #1 consists of the paving of the VETERANS OF FOREIGN WARS (VFW) parking lot located at 1699 Park Rd. Fairburn, GA 30213. All work must be completed within one hundred and twenty (120) calendar days of the Notice to Proceed (NTP). | TRIPLE R CONSTRUCTION | In-house | June, 2025 | July, 2025 | November, 2025 | October, 2025 | Fairburn | Sales Tax | $1,688,078 | $0 | $1,688,078 | Green | Green | Active | anthony.belcher@fairburn.com | 2025 | 2025-08-01 13:45:39 | Georgia | City of Fairburn | 2022-03-31
[17 empty] | SUM = 1,688,078 | SUM = 0 | SUM = 1,688,078