## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
FA- 34 | 23-002 | Pedestrian and Bike Improvements (Phase 2) | Tier 2 | Pedestrian and Bike Improvements | TSPLOST2 | Fairburn | Completed | SOUTHEAST BROAD STREET PEDESTRIAN IMPROVEMENTS PROJECT #23-002. The work includes the removal of existing curb & gutter, sidewalk and driveway aprons as required, installation of new curb & gutter, installation of new sidewalk, replacement of existing sidewalk as required, installation of new driveway aprons, and the installation of new ADA handicap ramps. The contract will also include preparation of sub-grade, saw-cutting and demolition of existing asphalt and concrete, as well as clean up and backfilling. | The Corbet Group | Moreland Altobelli | November, 2022 | January, 2023 | May, 2023 | April, 2023 |  | Sales Tax | $678,277 | $678,277 | $0 | Green | Green | Inactive | anthony.belcher@fairburn.com | 2023 | 2025-07-02 16:33:59 | Georgia | City of Fairburn | 2022-03-31
[17 empty] | SUM = 678,277 | SUM = 678,277 | SUM = 0