## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
HA- 7 |  | Paving & Drainage | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | Hapeville | Construction | City Wide Paving of selected streets | Vertical Earth Paving |  | December, 2023 | April, 2024 | October, 2026 | October, 2026 |  | Sales Tax | $1,000,000 | $252,802 | $747,198 | Green | Green | Active | lsudduth@hapeville.org |  | 2025-09-22 12:15:11 | Georgia | City of Hapeville | 2022-03-31
[17 empty] | SUM = 1,000,000 | SUM = 252,802 | SUM = 747,198