## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
HA- 11 |  | Traffic Signal and Signage Improvement Project | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Hapeville | Completed | Installation of new traffic signal heads and new School Zone Flashers | Sunbelt |  | July, 2022 | September, 2022 | September, 2026 | January, 2026 |  | Sales Tax | $60,200 | $106,106 | $-45,906 | Red | Green | Active | lsudduth@hapeville.org |  | 2025-09-22 11:56:16 | Georgia | N. Fulton and King Arnold Intersection | 2022-03-31
[17 empty] | SUM = 60,200 | SUM = 106,106 | SUM = -45,906