## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSF- 18 | RS 375 | Ponderosa Pines | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | City of South Fulton | Completed | Bluebonnet Circle, Bluebonnet Court, Bluebonnet Trail and Devilla Court within the subdivision will be resurfaced. The work will include all the necessary preparation work which may include full depth of pavement patching, removal of the top asphalt layer (milling), and a surface treatment prior to final topping. The road will then be resurfaced with a uniform layer of asphalt in manner so as to provide uniformity of depth and a smooth transition to existing. After resurfacing, all existing pavement markings such as line striping, crosswalks etc. will be reinstalled. |  | Not Applicable | Not Applicable |  | November, 2020 |  |  | Sales Tax | $97,695 | $81,583 | $16,112 | Green | Green | Active | roussan.francois@fultoncountyga.gov | 2019 | 2021-05-03 20:02:51
[17 empty] | SUM = 97,695 | SUM = 81,583 | SUM = 16,112