## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
MIL- 31 |  | Local Road Safety | Tier 1 | Maintenance and Safety Enhancements | TSPLOST2 | Milton | Design | Citywide Local Road Safety Plan Implementation - Various Locations Bethany Bend at Serenade Court - Sidewalk and RRFB Connection (KCI) SR 372 roundabouts - RRFB Install (Keck and Wood) |  | KCI Technologies, Keck and Wood | June, 2023 | January, 2023 | October, 2023 | February, 2024 |  | Sales Tax | $3,000,000 | $23,328 | $2,976,672 | Green | Green | Active | Robert.Dell-Ross@miltonga.gov |  | 2023-04-07 08:35:27 | Georgia | City of Milton | 2022-03-31
[17 empty] | SUM = 3,000,000 | SUM = 23,328 | SUM = 2,976,672