## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
MIL- 34 |  | City Wide | Tier 3 | Operation and Safety Improvements | TSPLOST2 | Milton | Planning | Tier 3 Operations and Safety Improvements - Location TBD | [7 empty] | Sales Tax | $2,000,000 | $0 | $2,000,000 | Green | Green | Active | Robert.Dell-Ross@miltonga.gov |  | 2022-10-10 17:25:05 | Georgia | City of Milton | 2022-03-31
[17 empty] | SUM = 2,000,000 | SUM = 0 | SUM = 2,000,000