## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 5 | TS107 | SCOOT Upgrade | Tier 1 | Operation and Safety Improvements | TSPLOST | Sandy Springs | Completed | Adaptive signal upgrade for 16 intersections. | RJ Haynie | WSP | May, 2019 | July, 2018 | June, 2021 | June, 2021 |  | Sales Tax | $1,484,961 | $1,484,961 | $0 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2021 | 2022-07-29 17:51:46
[17 empty] | SUM = 1,484,961 | SUM = 1,484,961 | SUM = 0