## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 37 | S2103 | Johnson Ferry Rd at Peachtree Dunwoody Rd Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Sandy Springs | Concept | Intersection improvement at Johnson Ferry Road and Peachtree Dunwoody Road |  | KCI |  | February, 2023 |  |  |  | Sales Tax | $3,000,000 | $47,378 | $2,952,622 | Green |  | Active | ajohnson@sandyspringsga.gov |  | 2025-06-18 16:13:32 | Georgia | Johnson Ferry Rd | 2022-03-31
[17 empty] | SUM = 3,000,000 | SUM = 47,378 | SUM = 2,952,622