## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 38 | S2105 | Roswell Road North Boulevard Project | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Sandy Springs | Design | Streetscape, access management and intersection improvements on Roswell Road from Dunwoody Place to the Chattahoochee River |  | Heath & Lineback | July, 2028 | July, 2024 | March, 2030 | March, 2030 |  | Sales Tax | $8,800,000 | $202,822 | $8,597,178 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2030 | 2026-03-06 15:35:20 | Georgia | Roswell Road | 2022-03-31
[17 empty] | SUM = 8,800,000 | SUM = 202,822 | SUM = 8,597,178