## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 41 | S2122 | Glenridge Dr., Hammond to south of Wellington Trace | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Land | Multi-Use Trail on Glenridge Drive from Wellington Place to Hammond Drive |  | Holt | November, 2025 | April, 2024 | August, 2027 | August, 2027 |  | Sales Tax | $2,500,000 | $371,771 | $2,128,229 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2027 | 2026-03-06 15:36:11 | Georgia | Glenridge Dr | 2022-03-31
[17 empty] | SUM = 2,500,000 | SUM = 371,771 | SUM = 2,128,229