## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 44 | S2193 | Hammond Drive Widening | Tier 1 | Congestion Relief | TSPLOST2 | Sandy Springs | Land | Project provides multi-modal opportunities within the approximately 0.75 mile corridor between Boylston Drive and Glenridge Drive including increased vehicular capacity, roundabouts, transit/shuttle provisions, multi-use trails, sidewalks, wide median, and other attributes. |  | Gresham Smith | August, 2025 | June, 2022 | June, 2029 | June, 2029 |  | Sales Tax | $35,000,000 | $11,874,378 | $23,125,622 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2029 | 2026-03-06 15:48:01 | Georgia | Hammond Drive | 2022-03-31
[17 empty] | SUM = 35,000,000 | SUM = 11,874,378 | SUM = 23,125,622