## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 46 | S2132 | Riverside Road Bridge Over Chattahoochee Tributary | Tier 1 | Bridges | TSPLOST2 | Sandy Springs | Design | Riverside Road Bridge Over Chattahoochee Tributary |  | Heath & Lineback | May, 2026 | May, 2023 | May, 2028 | May, 2028 |  | Sales Tax | $2,400,000 | $372,212 | $2,027,788 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2026 | 2026-03-06 15:39:29 | Georgia | 6545 Riverside Drive, Sandy Springs | 2022-03-31
[17 empty] | SUM = 2,400,000 | SUM = 372,212 | SUM = 2,027,788