## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
EP- 4 | EP-004 | Ale Circle Realignment and Desert Drive N Extension | Tier 1 | Operation and Safety Improvements | TSPLOST | East Point | Land | The project is in "Land Acquisition and Environmental Permitting" and the purpose of this project is to reduce traffic and safety issue at the intersection of Washington Road & Camp Creek Pkwy. |  | Lowe Engineers | June, 2018 | January, 2022 | November, 2022 | November, 2022 | http://www.eastpointcity.org | Sales Tax | $1,850,000 | $176,000 | $1,674,000 | Green | Red | Active | guest | 2018 | 2021-10-11 22:05:54
[17 empty] | SUM = 1,850,000 | SUM = 176,000 | SUM = 1,674,000