## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 55 | S2167 | Mt. Vernon Highway Sidewalk (Glen Errol Road to Ex. SW at 500 Mt. Vernon Highway) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Mt. Vernon Highway Sidewalk (Glen Errol Road to Ex. SW at 500 Mt. Vernon Highway) | Sol Construction | NV5 | November, 2023 | December, 2022 | March, 2024 | March, 2024 |  | Sales Tax | $370,000 | $169,046 | $200,954 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2024 | 2024-07-22 13:46:00 |  | 550 Mount Vernon Hwy, Atlanta, GA 30327
[17 empty] | SUM = 370,000 | SUM = 169,046 | SUM = 200,954