## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 58 | S2170 | Mt. Vernon Highway Sidewalk (Ex. SW at DeClaire Court to Long Island Drive) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Mt. Vernon Highway Sidewalk (Ex. SW at DeClaire Court to Long Island Drive) | Lagniappe | Kimley Horn | July, 2024 | January, 2023 | June, 2024 | June, 2024 |  | Sales Tax | $215,000 | $139,602 | $75,398 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2024 | 2025-07-17 14:22:20 |  | 5970 Long Island Dr, Sandy Springs, GA 30328
[17 empty] | SUM = 215,000 | SUM = 139,602 | SUM = 75,398