## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 59 | S2172 | Glenridge Drive Sidewalk (Canopy Drive to Glenridge Close Court) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Design | Glenridge Drive Sidewalk (Canopy Drive to Glenridge Close Court) |  | Heath & Lineback | August, 2024 | December, 2022 | March, 2025 | March, 2025 |  | Sales Tax | $225,000 | $70,560 | $154,440 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2025 | 2024-03-29 10:51:54 |  | 6449 Glenridge Dr, Sandy Springs, GA 30328
[17 empty] | SUM = 225,000 | SUM = 70,560 | SUM = 154,440