## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 60 | S2177 | Powers Ferry Road (New Northside Drive to 6201 Powers Ferry Road) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Powers Ferry Road (New Northside Drive to 6201 Powers Ferry Road) | Vertical Earth | NV5 | September, 2023 | December, 2022 | February, 2025 | December, 2024 |  | Sales Tax | $385,000 | $278,960 | $106,040 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2025 | 2025-06-18 16:23:24 |  | 6201 Powers Ferry Rd NW, Sandy Springs, GA 30339
[17 empty] | SUM = 385,000 | SUM = 278,960 | SUM = 106,040