## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 61 | S2179 | Spalding Drive (Nesbit Ferry to Spalding Lake Court) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Spalding Drive (Nesbit Ferry to Spalding Lake Court) | Zaveri | Heath & Lineback | November, 2024 | December, 2022 | April, 2025 | March, 2025 |  | Sales Tax | $550,000 | $325,489 | $224,511 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2025 | 2025-07-17 14:23:02 |  | 5040 Spalding Dr, Sandy Springs, GA 30350
[17 empty] | SUM = 550,000 | SUM = 325,489 | SUM = 224,511