## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 62 | S2168 | Hilderbrand Police gym to Roswell Road (both sides) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Hilderbrand Police gym to Roswell Road (both sides) | Zaveri | NV5 | February, 2025 | December, 2022 | August, 2025 | July, 2025 |  | Sales Tax | $520,000 | $442,270 | $77,730 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2025 | 2025-12-11 08:39:33 |  | 218 Hilderbrand Dr, Atlanta, GA 30328
[17 empty] | SUM = 520,000 | SUM = 442,270 | SUM = 77,730