## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
EP- 5 | EP-177 | Washington Road Sidewalk | Tier 1 | Pedestrian Improvements | TSPLOST | East Point | Construction | The Project was bid Out for Construction. The lowest apparent bidder was DAF Concrete. Project is for new installation of sidewalk along the Washington Road corridor from I-285 to Delowe Drive. | DAF Concrete, LLC | Moreland Altobelli (ATLAS) | June, 2018 | June, 2021 | June, 2022 | June, 2022 | http://www.eastpointcity.org | Sales Tax | $1,993,420 | $322,000 | $1,671,420 | Green | Green | Active | Cadell Hall | 2021 | 2021-10-11 22:09:50
[17 empty] | SUM = 1,993,420 | SUM = 322,000 | SUM = 1,671,420