## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 63 | S2163 | Northland Drive (Landmark Drive to Ex. SW at Northland Ridge Trail) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Northland Drive (Landmark Drive to Ex. SW at Northland Ridge Trail) | Construction 57 | Heath & Lineback | April, 2024 | December, 2022 | November, 2024 | October, 2024 |  | Sales Tax | $195,000 | $176,156 | $18,844 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2024 | 2025-06-18 16:19:56 |  | 4906 Northland Dr, Atlanta, GA 30342
[17 empty] | SUM = 195,000 | SUM = 176,156 | SUM = 18,844