## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 65 | S2186 | Mt. Paran Road and Powers Ferry Road (Rebel Trail to Carol Lane) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Bidding | Mt. Paran Road and Powers Ferry Road (Rebel Trail to Carol Lane) |  | Kimley Horn | December, 2025 | January, 2023 | February, 2027 | February, 2027 |  | Sales Tax | $2,400,000 | $272,558 | $2,127,442 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2027 | 2026-03-06 15:46:32 |  | 385 Mt Paran Rd NW, Atlanta, GA 30327
[17 empty] | SUM = 2,400,000 | SUM = 272,558 | SUM = 2,127,442