## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 67 | S2184 | Jett Ferry Road/Spalding Drive (Jett Ferry Court to Dunvegan Close) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Construction | Jett Ferry Road/Spalding Drive (Jett Ferry Court to Dunvegan Close) | Sol Construction | Kimley Horn | June, 2026 | December, 2021 | September, 2026 | September, 2026 |  | Sales Tax | $700,000 | $148,431 | $551,569 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2026 | 2026-03-06 15:44:03 |  | 3245 Spalding Dr, Sandy Springs, GA 30350
[17 empty] | SUM = 700,000 | SUM = 148,431 | SUM = 551,569