## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
EP- 6 | EP-325 | N Commerce Dr @ Redwine Rd improvements | Tier 1 | Operation and Safety Improvements | TSPLOST | East Point | Land | The project is in "Land Acquisition". The propose of the project is intersection safety and improvements, Engineering Design and Land Acquisition. |  | Moreland Altobelli (ATLAS) | June, 2020 | January, 2022 | December, 2022 | December, 2022 | http://www.eastpointcity.org | Sales Tax | $350,000 | $63,225 | $286,775 | Green | Red | Active | guest | 2021 | 2021-10-11 22:21:13
[17 empty] | SUM = 350,000 | SUM = 63,225 | SUM = 286,775