## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
JCR- 44 | TS0242 | Sargent Road at Ashwick Place Intersection Improvement | Tier 1 | Operation and Safety Improvements | TSPLOST2 | Johns Creek | Design | Operational improvement at the intersection of Sargent Road at Ashwick Place. |  | Lowe Engineers | March, 2024 | May, 2024 |  |  |  | Sales Tax | $2,500,000 | $0 | $2,500,000 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-10-05 13:10:07 | Georgia | City of Johns Creek | 2022-03-31
[17 empty] | SUM = 2,500,000 | SUM = 0 | SUM = 2,500,000