## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
JCR- 51 | TS0255 | Buice Road (Twingate Drive to Kingston Crossing) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Johns Creek | Design | Sidewalk connectivity from Twingate Drive to Kingston Crossing on the North side of Buice Road. |  | KCI | June, 2023 | August, 2023 |  |  |  | Sales Tax | $650,000 | $5,200 | $644,800 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-10-05 13:21:41 | Georgia | City of Johns Creek | 2022-03-31
[17 empty] | SUM = 650,000 | SUM = 5,200 | SUM = 644,800