## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
EP- 7 | EP-176 | Ben HIll Sidewalk | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | East Point | Design | The plan is to design new sidewalk installation and road enhancement with Intersection improvements. |  | Prime Engineering | April, 2021 | October, 2021 | February, 2022 | December, 2021 | http://www.eastpointcity.org | Sales Tax | $1,160,000 | $274,467 | $885,533 | Green | Green | Active | guest | 2020 | 2021-08-17 20:30:14
[17 empty] | SUM = 1,160,000 | SUM = 274,467 | SUM = 885,533