## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 72 | S2188-3 | Glenridge Drive at Messina Way | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | This sidewalk will provide a connection between the existing sidewalk at Spalding Trace to Messina Way | Blount Construction | NV5 |  | January, 2023 | March, 2024 | March, 2024 |  | Sales Tax | $65,000 | $19,225 | $45,775 | Green |  | Active | ajohnson@sandyspringsga.gov | 2024 | 2024-03-29 14:20:18 |  | 7001 Glenridge Dr, Sandy Springs, GA 30328
[17 empty] | SUM = 65,000 | SUM = 19,225 | SUM = 45,775