## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 73 | S2188-4 | River Exchange Drive Sidewalk | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | The project will add 10'-wide sidepath along the west side of River Exchange Dr. from Spalding Dr. North to the entrance of Crooked Creek Park. The project will also provide 6'-wide sidewalk from the entrance of Crooked Creek Park north to tie into existing sidewalk. | Sol Construction | NV5 | September, 2023 | January, 2023 | July, 2024 | June, 2024 | Sandy Springs | Sales Tax | $165,000 | $150,324 | $14,676 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2024 | 2024-06-21 15:10:43 | Georgia | 3101 River Exchange Dr, Sandy Springs
[17 empty] | SUM = 165,000 | SUM = 150,324 | SUM = 14,676