## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 74 | S2188-5 | Windsor Parkway, YMCA to Peachtree Dunwoody Road | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | The project will add 525 LF of sidewalk to the north side of Windsor Parkway from the intersection of Peachtree Dunwoody Road to the YMCA entrance |  | NV5 | September, 2023 | January, 2023 | July, 2024 | June, 2024 |  | Sales Tax | $205,000 | $133,136 | $71,864 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2024 | 2024-06-21 15:11:12 | Georgia | 940 Windsor Pkwy, Sandy Springs, GA 30342
[17 empty] | SUM = 205,000 | SUM = 133,136 | SUM = 71,864