## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
EP- 8 | EP-006 | Dodson Drive Resurfacing | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | East Point | Completed | The project is in design for roadway resurfacing. The projects listed below were grouped together for solicitation: EP-152 $190,000; EP-133 $419,667; EP-132 $26,000; EP-136 $189,000; EP-153 $174,500; EP-154 $52,800; EP-155 $248,000 EP-156 $311,500 EP-157 $84,500 EP-135 $32,000 EP-137 $120,000 EP-138 $405,000 EP-144 $65,000 EP-147 $442,700 EP-160 $341,500 EP-162 $41,500 EP-168 $82,500 EP-148 $116,000 EP-173 $51,000 EP-175 $296,000 EP-140 $300,000 EP-151 $280,000 EP-304 $385,000 EP-103 $336,667 EP-106 $393,333 | Mullin's Brothers Paving | Griffin & Davis Consulting | June, 2018 | February, 2020 | November, 2020 | December, 2020 | http://www.eastpointcity.org | Sales Tax | $5,384,167 | $5,384,167 | $0 | Green | Green | Active | guest | 2020 | 2021-10-11 22:24:39
[17 empty] | SUM = 5,384,167 | SUM = 5,384,167 | SUM = 0